## Phase 1 Fin Rescue Makana
PHASE 1: FINANCIAL RESCUE
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR ONE: GOVERNANCE
1 | Unauthorised, Irregular, Fruitless and Wasteful expenditure | Non-reporting, no consequence management, disciplinary board not properly constituted, UIF&W not investigated to determine if any person is liable for the expenditure, as required by Section 32(2)(a) of the MFMA | Develop, approve and implement a policy governing irregular, unauthorised, fruitless and wasteful expenditure. | In-house | In-house | Chief Finance Officer | 01.06.2021 | 31.07.2021 | Policy in place and implementation | Approved policy and Council resolution
|  |  | Develop and implement UIF&W expenditure reduction plan. | In-house and NT-MFMA unit | In-house and NT-MFMA unit | Chief Finance Officer | 01.06.2021 | 31.08.2021 | UIF&W expenditure reduction plan implementation and percentage reduction in historical expenditure | Approved UIF&W expenditure reduction plan and Council resolution. Quarterly Council reports on progress
|  |  | Identify, investigate and report on irregular, unauthorised, fruitless and wasteful expenditure as per legislation | In-house | In-house | Council, MPAC, Disciplinary Board | 01.06.2021 | 31.11.2021 | Quarterly reports on UIF&W expenditure and investigations | Council approved quarterly reports, MPAC oversight reports, Disciplinary Board's reports and related resolutions
|  |  | Implement Consequence management for UIF&W | In-house | In-house | Disciplinary Board, Executive Mayor and MM | 01.06.2021 | 31.11.2021 | Transgressors disciplined | Written outcome of disciplinary hearings
2 | System of Delegations | Inadequate separation of powers and functions between Council, Executive and administration; No clear distinction of legislative and delegated powers for elected and appointed officals; No clarity on lines of accountability; generic powers to directors an error; No powers delegated to CFO; Ultra vires delegations | Review system of delegations | In-house | In-house | Senior Manager: Legal Services | 01.06.2021 | 31.11.2021 | Systems of delegations in place | Approvved system of delegations and Council resolution.
|  |  | Sign-off of sub-delegations | In-house | In-house | MM | 31.11.2021 | 31.12.2021 | Sub-delegations in place | Signed sub-delegations and acknowledgement of receipt
3 | Contract Management | Contracts not adhering to procurement legislation, payment of service providers not made in thirty days, High percentage of contracted services, poor internal controls, non submission of monthly performance monitoring reports on contracts, unnecessary deviations | Audit and review all contracts | In-house | In-house | Director: Corporate Services and CFO | 01.06.2021 | 31.11.2021 | No irregular, unnecessary or expired contracts, and contracts register in place | Audit and review report. Council resolution.
|  |  | Identify goods and services required on an ongoing basis and appoint service providers on three year contracts | In-house | In-house | CFO | 01.06.2021 | 31.11.2021 | Reduction in operational costs, Reduction in irregular deviations | Reduction in procurement costs as per procurement plan, and appointment letters.
|  |  | Submission of monthly performance monitoring reports on contracts | In-house | In-house, Contracted Services | CFO | 01.06.2021 | 31.11.2021 Monthly | value for money, compliance with legislation | Monthly performance monitoring reports
|  |  | Review annual procurement plan | In-house | In-house | CFO | 01.06.2021 | 31.07.2021 | Reduction in operational costs related to procurement | Approved reviewed procurement plan and Council resolution
4 | Litigation and Contingent liability | No litigation strategy, pending litigation matters; financial exposure through contingent liability, | Develop litigation strategy | In-house | In-house | Head: Legal Services | 01.06.2021 | 31.11.2021 Monthly | Litigation Strategy in place. Reduction in legal costs. | Approved Litigation Strategy. Annual Financial Statement.
|  |  | Report to Council on diagnostic analysis of root causes of litigations and claims | In-house | In-house | Head: Legal Services | 01.06.2021 | 31.08.2021 | Root causes identified and Integrated Plan in place to mitigate against such identified root causes | Diagnostic analysis report and Council resolution
|  |  | Conduct a legal assessment on reasonable prospects of success on all pending litigations | In-house | In-house | Head: Legal Services | 01.06.2021 | 31.11.2021 | Reduction in contingent liability | Report on legal assessment and Council resolution.Proof of settlement of matters
|  |  | Development and implementation of MFMA Legal compliance matrix | In-house | In-house and NT-MFMA unit | Head: Legal Services | 01.06.2021 | 31.07.2021, Monthly | Legislative compliance | Institutionalised MFMA legal compliance matrix and AG annual audit reports
|  |  | Review business plan for legal services unit | In-house | In-house | MM/Director: Corporate Services | 01.06.2021 | 31.08.2021 | Focused and efficient rendition of legal support ot political and administrative components of municipality. | Approved reviewed business plan and Council resolution
5 | Risk and internal Audit | Insufficient focus and pre-emptive measures; misdiagnosis of risks; No periodic reporting on fraud and corruption matters reported through hotline; Non implementation of appropriate risk management activities; Internal audit unit not adequately resourced; internal control deficiencies; recommendations of audit committee not fully implemented; regression in audit findings; no oversight over performance management system | Review of corporate risks | In-house | In-house | Acting General Manager: Internal Audit | 01.06.2021 | 31.08.2021 | Reviewed corporate risks | Reviewed corporate risks, and Council resolution
|  |  | Quarterly reports on internal audit and risk management | In-house | In-house | Acting General Manager: Internal Audit | Quarterly | Quarterly |  | Quarterly reports and Council resolutions
|  |  | Update and report progress on implementation of AG audit action plan | In-house |  | Acting General Manager: Internal Audit | 01.06.2021 | 01.07.2021, Quarterly | Improved governance and accountability | Approved updated AG audit action plan and Council resolution. Progress reports to Council
|  |  | Quarterly progress reports on implementation of remedial actions to mitigate against corporate risks and annual audit plan | In-house | In-house | Acting General Manager: Internal Audit | 01.06.2021 | Quarterly | Effective management of identified risks | Quarterly reports and Council resolutions
|  |  | Approval of annual audit plan and risk management documents |  |  | Manager: Internal Audit | 01.06.2021 | 31.06.2021 | Policies and plans in place | Approved annual audit plan and risk management documents, and related Council resolutions
7 | Governance Oversight Structures
|  | Limited oversight by Council over executive and administration, No investigation on UIF&W expenditure | Development, approval and implementation of annual institutional calendar for meetings for council and committees | In-house | In-house | Director: Corporate Services | 01.06.2021 | 31.06.2021 | Schedule of meetings in place and adhered to. | Approved schedule of meetings and Council resolution, Minuites and agendas of meetings
|  |  | Review terms of reference for MPAC to add more oversight responsibilities | In-house | In-house and COGTA | Director: Corporate Services | 01.06.2021 | 31.11.2021 | Increased oversight by Council and its commitees over the Executive and administration. | Approved reviewed terms of reference and Council resolution.
|  |  | Increase frequency of meetings for MPAC | In-house | In-house | Director: Corporate Services | 01.06.2021 | 31.11.2021 | Increased oversight by Council and its commitees over the Executive and administration. | Approved annual schedule of Council and committee meetings and Council resolution
|  |  | Convene meetings of TROIKA | In-house | In-house and COGTA/SALGA | MM/Director: Corporate Services | 01.06.2021 | 31.11.2021 | Effective political and administrative interface | Minutes of meetings
|  |  | Develop, approval and implementation of annual institutional calender for TROIKA meetings | In-house | In-house | Director: Corporate Services | 01.06.2021 | 31.11.2021 | Organised and focused TROIKA | Approved schedule of meetings and Council resolution, Minuites and agendas of meetings
|  |  | Enforcement and monitoring of the code of conduct for councillors | In-House | In-house | Speaker of Council | 01.06.2021 | Monthly | Disciplined councillors and adherence to legal prescripts | Quarterly reports on compliance with code of conduct by Councillors
|  |  | Develop, approval and implementation of institutional calender of meetings for Executive management meetings | In-house | In-house | MM | 01.06.2021 | 31.06.2021, Monthly | Effective and efficient co-ordination of administration and service delivery | Minutes of meetings
|  |  | Schedule an induction for councillors on governance, financial management and oversight; | In-house | In-house and SALGA | Director: Corporate Services | 01.06.2021 | 31.11.2021 | Empowered Councillors to execute their responsibilities | Record of the Induction, Council approved programme and resolution, and attendance register.
8 | Information and Communication Technology | Lack of ICT general controls on ICT governance, user access management, programme change management, security management, ICT service continuity. | Implementation of ICT Governance framework more specifically general controls | In-house | In-house SALGA | Acting Senior Manager: ICT | 01.06.2021 | Monthly | Effective ICT general controls, assurance on confidentiality and integirty of data. | AG Audit report and internal quarterly audit reports
9 | Powers and Functions | Municipality mandated to provide library and vehicle licence services | Conduct an in-depth analysis of cost implications | In-house, PT | In-house, PT | CFO | 01.07.2021 | 30.10.2021 | All costs funded mandated agreement | Cost analysis report
|  |  | Re-negotiate mandate agreements | In-house, PT | In-house, PT | Head: Legal services and CFO | 30.10.2021 | 31.12.21 | Re-negotiated mandate agreements and all costs covered for mandate agreements | Signed re-negotiated agreements
PILLAR TWO: INSTITUTIONAL
1 | HR Strategy (HRD&M) | Current strategy / plan is outdated | Analyse HR Maturity level, identify gaps, drat the HRD&M | In-house, SALGA, CoGTA, NTMFRS | In-house | Exec. Dir. CS | 01.01.2022 | 30.06.2022 | Approved HRD&M | HR Maturity report, Council resolution | N/A
2 | Skills Audit | Skills audits have not been conducted except for WSP | Determine a sample, develop skills audit template and questionnaire, collate and analyse employees information, Produce skills audit | In-house, SALGA, CoGTA | In-house | Exec. Dir. CS | 01.01.2022 | 30.06.2022 | Completed skills audit | Analysis report, skills audit and Council report
3 | Minimum Competency Regulations | Not all affected employees have completed the Course. | Enroll all Senior Managers and affected personnel (s119-MFMA) | In-house | In-house - own budget, LGSETA | Exec. Dir: CS | 01.01.2022 | 31.11.2021 | Improved compliance | Proof of registration, results, certificates
4 | Employee Costs | Current costs are at 44% of the Opex. | Analyse of employees: age, ill health, redundancy. Develop Separation policy. Offer retrenchment packages | In-house MFRS Advisory Support | In-house MFRS Advisory Support | Exec. Dir: CS | 01.01.2022 | 30.06.2022 | Reduction in employee costs | Progress reports, staff establishment reports, Approved policy | Reduced employee costs by 5%
5 | Performance Management | PMS is not cascaded to lower levels below MM and direct reports | Cascade PMS from level 2 to 4 | In-house, Support from NTMFRS/ SALGA/CoGTA | In-house | Exec Director: CS | 01.01.2022 | 30.06.2022 | Imporoved performnace, service delivery and audity outcome | Approved PMS Policy, PM Agreements and Evaluation reports
6 | Organisation Structure | Current structure was last reviewed in Oct 2019. Current employee costs are at 44 % Current Structure is bloated (top heavy) | Conduct an assessment of current structure, Conduct staff verification Assess powers/functions Draft review of structure Develop options on cost reduction, Develop Placement Policy/ Plan LLF consultations | In-house | In-house | MM, Exc. Director: CS | 31.11.2021 | 30.06.2022 | Functions properly aligned to strategic objectives and legal mandate Improved service delivery Achieved affordability Achieved completeness of employee costs | Approved organisation structure, Council resolution | Reduced employee costs by 5%
PILLAR THREE: FINANCIAL MANAGEMENT
1 | Funded budget | Funded 2020/21 MTREF Budget | Compile the 2021/22 MTREF Budget in line with reviewed targets for realistically anticipated revenue and expenditure trends and ensure the budget to be cash funded | In-house capacity available | EC PT Support (including Budget Review) NT Budget Circular | MM, CFO, PT | 01.05.2021 | 30.06.2021 | Funded 2021/22 Budget | Funded 2021/22 Budget
|  |  | Austerity and cost cutting measures to be reflected in the 2021/22 Budget. | Best-Practise Advise | NT 2019 Cost Containment Regulations | MM, CFO, PT | 01.05.2021 | 30.06.2021 | Cost containment report in support of the budget | Cost containment report in support of the budget
|  |  | Council adopt funded 2021/22 MTREF Budget | In-house | EC PT Support | Council | 01.05.2021 | 30.06.2021 | Adopted 2021/22 funded budget | Council Resolution pertaining to funded budget
|  |  | Implementation and monitoring of the approved budget for 2021/22. | In-house mSCOA compliant system with spending limits aligned to approved budget | EC PT Support | MM, CFO | 01.07.2021 | 31.12.2021 | Sec 71 reports reflecting revenue and expenditure in accordance with the adopted funded budget Savings in identified intervention areas and increase in actual revenue Strict controls over revenue and expenditure consistent with delegations and approved budget. Reduction in deviations, irregular, fruitless and wasteful and unauthorised expenditure to acceptable norm | Sec 71 reports reflecting revenue and expenditure in accordance with the adopted funded budget MFMA Sec 52(d) reports with variance analysis
2 | Cost Containment measures not implemented | Cost containment measures not implemented | Review and update Cost Containment Policy for Council adoption | In-house capacity available | NT 2019 Cost Containment Regulations | MM, CFO | 01.062021 | 31.07.2021 | Cost Containment Policy approved | Approved cost containment policy | Targeted ratios:  Cash Coverage: 1 Month  Current Ratio: 1.5:1 (Norm = 1.5:2.1)
|  | Cash Cost Coverage = 0 month | Implement approved Cost Containment Policy (Month 2-6) | In-house capacity available | NT 2019 Cost Containment Regulations | MM, CFO | 01.08.2021 | 31.12.2021 | Approved cost containment policy implemented | Monthly financial impact report on the implemented cost containment policy
|  |  | Develop and implement specific strategy to reduce employee cost (Overtime, etc) | In-house capacity available | NT 2019 Cost Containment Regulations | MM, CFO | 01.07.2021 | 31.12.2021 | Reduced employee costs | Approved Organisational structure in line with the strategy
|  |  | Conditional grant expenditure to not exceed allocation | In-house capacity available | NT 2019 Cost Containment Regulations | MM, CFO, Technical Director | 01.07.2021 | 31.12.2021 | Effective management of grants and unspent grant allocations. System to ensure unspent grant monies can be identified at any time and are cash backed | Monthly conditional grant expenditure report
3 | Cash Flow Management | Current ratio=0,29 | Develop and implement a robust cash management tool | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.06.2021 | 30.06.2021 | Improved Cash Flow Position Cash coverage above 1 month Reduced creditors and debtors | Cash flow management SOPs | Property Rates: Bill 100% of Valuation Roll Value reconciled with billing system Service Charges: 2020/21: 100% of Budget 2021/22: 2020/21 Budget + CPI + Growth 2022/23: 2021/22 Budget + CPI + Growth 2023/24: 2022/23 Budget + CPI + Growth Achieve collection rates: 2020/21: 85% 2021/22: 88% 2022/23: 90% 10% reduction in unbilled consumption
|  |  | Compile a cash-flow projection for the financial year upon completion of the 2021/22 Budget, showing realistic monthly projections | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.06.2021 | 30.06.2021 | 2020/21 cash flow projection compiled | Cash flow management plan
|  |  | Management of the cash-flow daily with weekly reporting to the MM and management meetings | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | Weekly cash flow management reports | Weekly cash flow management report. Attendance register and minutes of meetings
|  |  | Ensure that all contracts are current. Continue to review committed contracts to determine which contracts have lapsed or which can be cancelled without the risk of legal action against ADM | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | Monthly report on contracts | Contract register. Monthly report on the status of all contracts.
|  |  | Continue to investigate contingent liabilities and meetings with claimants to be held where legal action can be suspended to resolve claims amicably | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | Monthly report and minutes of meetings on contingent liabilities | Contingent liabilities register with monthly progress report
4 | Trading debtors and collection rates | Collection Rate = 90% | Implement the credit control and debt collection policy | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | Achieved collection rate of 95%. Reduced government debt by 20%.. Reduce Business debts by 10%. Reduce Household debts by 2.5% (Month 2-6) | Monthly billing and collection report. Monthly debtors report showing reduced debtors balances. | Reduced government debts by 20% per month. Reduced business debts by 10% per month. Reduced households debt by 2.5% per month
|  | Ineffective revenue management system and lack of capacity within the Revenue unit | Review Revenue Management System, Policies and Capacity to improve efficiencies | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | Reviewed revenue management system and policies | Reviewed SOPs
|  | Outdated revenue enhancement strategy | Review and update revenue enhancement strategy to improve billing, collection and ensure disposal of redundant assets | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | Reviewed and updated revenue enhancement strategy | Effective Revenue enhancemenrt strategy
|  | State organs owe the municpality R30 million as at 31 December 2020 | Reconcile government debts and enter into payment agreements (Month 2) | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | Reduced government debts. | Government debt payment agreements. | Reduced Government debt by R5 million per month from July 2021 to December 2021
|  | Businesses and others owe the municpality R59 million as at 31 December 2020 | Reconcile business and othersdebts and enter into payment agreements (Month 2) | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | Reduced business debts. | Business debt payment agreements. | Reduced Businesses and other debt by R5 million per month from July 2021 to December 2021
|  | Housegolds owe the municpality R611 million as at 31 December 2020 | Reconcile households debts and enter into payment agreements (Month 2) | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | Reduced household debts. | Household debt payment agreements. | Reduced households debt by R15 million per month from July 2021 to December 2021
|  |  | Conduct a meter audit to determine the condition of current meters, identify faulty meters for repair and for the planning of new meters | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | Meter audit report | Meter audit report
|  |  | Repair and replacement of faulty meters | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | Meter replacement report. | Meter replacement report.
|  |  | Identification and registration of Indigent Households for free basic services (to reduce debtors) | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | Updated indigent register. | Updated indigent register.
5 | Expenditure/ Creditor Management | Not all Top 10 Creditors paid within 30 Days | Prepare creditors reconciliation for bulk suppliers (Month 1) | In-house capacity available |  | MM, CFO. Risk Manager | 01.07.2021 | 31.12.2021 | Creditor Payment Ratio of 30 Days. Enhance Service Delivery. Prevented Fruitless & Wasteful Expenditure. | Monthly creditors age analysis report showing decreasing balances | Pay 20% of outstanding operational invoices per month as per agreement
|  |  | Enter into / re-negotiate payment plans with major creditors (Month 1) | In-house capacity available | EC PT Support | MM, CFO. | 01.07.2021 | 31.12.2021 | Signed realistic payment plans | Signed payment plan | 100% adherence to payment arrangements Councillor REM: 100% per Gazetted, subject to FRP Progress Achieve expenditure financial targets per FRP and Budget parameters
|  |  | Pay bulk purchase invoices within 30 days of receiving invoice (Months 2-6) | In-house capacity available |  | MM, CFO. | 01.07.2021 | 31.12.2021 | Payments strictly in accordance with payment plans | Monthly payment plan report
|  |  | Manage contingent liabilities to minimise the exposure of financial risk | In-house capacity available |  | MM, CFO. | 01.07.2021 | 31.12.2021 | Updated contingent liabilities register | Updated contingency liabilities register
|  | Weak internal controls in SCM processes that enable UIF&W to be incurred | Council to resolve on MPAC reports on UIF&W incurred up to end of 2019/20 | In-house capacity available | NT UIF&W Regulation | MM, CFO. | 01.07.2021 | 31.12.2021 | Reduced UIF&W | Monthly UIF&W report
|  |  | Council to resolve on MPAC reports on UIF&W incurred up to end of 2020/21 | In-house capacity available | NT UIF&W Regulation | MM, CFO. | 01.07.2021 | 31.12.2021 | UIF&W monthly report | Monthly UIF&W report
|  |  | Adoption of reviewed SCM policy by Council | In-house capacity available |  | MM, CFO. | 01.07.2021 | 31.12.2021 | Reviewed SCM policy adopted by Council | Adopted SCM policy
|  |  | Procure goods and services in line with SCM policy and regulations | In-house capacity available | PT support | MM, CFO. | 01.07.2021 | 31.12.2021 | Adherence to the Municipality’s adopted Supply Chain Management Policy. Goods and services procured where the appropriate supporting documentation is not in place, to be considered irregular and recoverable from the Official concerned. | SCM deviation report
|  |  | Incur expenditure in terms of the approved 2021/22 budget | In-house capacity available |  | MM, CFO. | 01.07.2021 | 31.12.2021 | Strict controls over revenue and expenditure consistent with delegations and approved budget. Reduction in deviations, irregular, fruitless and wasteful and unauthorised expenditure to acceptable norm | Monthly Sec 71 expenditure report. MFMA Sec 52(d) reports with variance analysis
6 | Ring-fenced Conditional Grants (CGs) | Unspent Conditional grants | Maintain a separate bank account for the ring-fencing of Conditional Grants | In-house capacity available | PT Advisory and monitoring support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | 100% Unspent Conditional Grants cash-backed. 100% DORA Compliance | Ring fenced Conditional grants account cash backing conditional grants fund balance | 100% cash-backed
|  |  | Maintain the ring-fencing of grant allocation in accordance with NT guidelines | In-house capacity available | PT Advisory and monitoring support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | 100% Unspent Conditional Grants cash-backed. 100% DORA Compliance | Ring fenced Conditional grants account cash backing conditional grants fund balance
|  |  | Spend conditional grants strictly in accordance with DORA requirements | In-house capacity available | PT Advisory and monitoring support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | 100% Unspent Conditional Grants cash-backed. 100% DORA Compliance | Ring fenced Conditional grants account cash backing conditional grants fund balance
|  |  | An effective grant management system put in place to ensure that conditional grants are only used for their intended purpose - ring fencing of grant money. | In-house capacity available | PT Advisory and monitoring support | MM, CFO, S56 Managers | 01.07.2021 | 31.12.2021 | 100% Unspent Conditional Grants cash-backed. 100% DORA Compliance | Ring fenced Conditional grants account cash backing conditional grants fund balance
PILLAR FOUR: SERVICE DELIVERY
1 | Asset Management | Limited management of assets based on conditional assessments on asset register. Poor asset management strategies | Review, update and implementation of Asset Maintenance and Renewal policy and strategy. | In-house | In-house, Contracted Services | Director: Technical Services | 01.06.2021 | 31.11.2021 | Reviewed Asset Maintenance and Renewal Policy and strategy in place | Reviewed Asset Maintenance and Renewal Policy and strategy in place | GRAP Compliant Asset Register. Target 8% of Opex.
|  |  | Audit of current infrastructure (conditional assessment, determination of the remaining useful life) | In-house | In-house, Contracted Services | Technical Director, CFO | 01.06.2021 | 30.06.2022 | Complete and up to date asset data, including but not limited to asset classification, asset condition, determination of remaining useful life, and asset revaluation if still usable after end of life. | GRAP compliant asset register | GRAP Compliant Asset Register.
|  |  | Asset Register compliance with GRAP. Update and maintain Asset Register. | In-house | In-house, Contracted Services | Technical Director, CFO | 01.06.2021 | 30.06.2022 | Grap Compliant Asset Register | GRAP compliant asset register | GRAP Compliant Asset Register
|  |  | Work In Progress Management (Record keeping for WIP, Componentization of Assets as part of the consultant's scope of work) | In-house | In-house, Contracted Services | Technical Director, CFO | 01.06.2021 | 30.06.2022 | Asset componentization report for all new infrastructure. Consultant scope of work must incorporate elements of asset management and final payments must not be made without asset componentization report on asset delivered. | GRAP compliant asset register | GRAP Compliant Asset Register
2 | Frictionless Payments | Municipality is loosing revenue because it does not have cost reflective tariffs for service provision and has limited revenue collection platforms | Enable Mobile Application and USSD (Unstructured Supplementary Service Data) enquiries from customers for utility bills | In-house | In-house, Contracted Services | MM, CFO | 01.06.2021 | 31.11.2021 | Ability of customers to make payments on multiple mobile platforms | Mobile account enquiry and payment platform | Target a 95% collection rate by increasing a collection rate by atleast 5% per month.
|  |  | Enable use of airtime to pay for minicipal payments | In-house | In-house, Contracted Services | MM, CFO | 01.06.2021 | 31.11.2021 | Ability of customers to make payments using airtime | Mobile payment platform | Target a 95% collection rate by increasing a collection rate by atleast 5% per month.
|  |  | Enable e-services on including payment of municipal bills on the municipal website | In-house | In-house, Contracted Services | MM, CFO | 01.06.2021 | 31.11.2021 | e-services page on the www.makana.gov.za website | e-service portal on the municipal website | Target a 95% collection rate by increasing a collection rate by atleast 5% per month.
|  |  | Institute compulsory debit orders for defaulting domestic debtors | In-house | In-house, Contracted Services | MM, CFO | 01.06.2021 | 31.11.2021 | Debit order register | Debit order register | Target a 95% collection rate by increasing a collection rate by atleast 5% per month.
3 | Electricity Supply | Outstanding Eskom debt, electricity losses above the norm, there is no master plan in place, inadequate staff to implement maintenance plan, GMR non-compliance. | Maintain Eskom payments as per payment plan and pay current account. | In-house | In-house, Contracted Services, ESKOM | MM, Technical Director, CFO | 01.06.2021 | 31.11.2021 | Proof of payment in line with the payment plan | Proof of payment in line with the payment plan | Complete Eskom payment by March 2022
|  |  | Develop a Energy Demand Side Management (EDMS) strategy to reduce electricity losses to below 10%. | In-house | In-house, Contracted Services | MM, Technical Director | 01.06.2021 | 31.11.2021 | EDMS Strategy Document | EDMS Strategy Document
|  |  | Implementation of the EDMS strategy | In-house | In-house, Contracted Services | MM, Technical Director | 01.06.2021 | 31.11.2021 | Baseline Assessment and retrofit schedule. Implementation of cut-offs and removal of illegal connections register | Baseline Assessment and retrofit schedule. Implementation of cut-offs and removal of illegal connections register
|  |  | Training internal staff in order to comply with GMR requirements | In-house | In-house, Contracted Services | MM, Technical Director | 01.06.2021 | 31.11.2021 | HV Reg Certificates Trade Test Certificates | HV Reg Certificates Trade Test Certificates
|  |  | Enter into a credit control agreement with Eskom in Makana East |  | In-house, Contracted Services, ESKOM | MM, Technical Director | 01.06.2021 | 31.11.2021 | Credit control agreement | Credit control agreement
|  |  | Development of Electricity Master Plan (Waainek, Summit Substations) | In-house | In-house, Contracted Services | MM, Technical Director | 01.06.2021 | 31.11.2021 | Electricity Master Plan | Electricity Master Plan
|  |  | Distribution transformer refurbishment | In-house | In-house, Contracted Services | MM, Technical Director | 01.06.2021 | 31.11.2021 | Distribution transformer refurbishment plan and progress report | Distribution transformer refurbishment plan and progress report
4 | Bulk Water Supply | Inadequate Water Supply | Development of Water Service Delivery Plan | In-house | In-house | MM, Technical Director | 01.06.2021 | 30.06.2022 | Draft Water and Sanitation Master Plan | Water and Sanitation Master Plan | Current reported water loss is below 30%. The municipality must maintain this below 30%
5 | Potable Water Supply | Severe Drought, Poor drinking water quality, Water Losses, Water Shortages, Lack of water balance accounting, Revenue Collection. | Develop a framework for implementation of a drought levy in severe drought conditions | In-house | In-house | MM, CFO, Technical Director | 01.06.2021 | 31.11.2021 | Dynamic Tariff Model Developed | Dynamic Tariff Model | Cost reflective tariffs
|  |  | Develop a water conservation and demand strategy. | In-house | In-house, Contracted Services | Director: Technical Services | 01.06.2021 | 30.06.2022
|  |  | Implement water conservation and demand strategy. | In-house | In-house, Contracted Services | Director: Technical Services | 01.06.2021 | 30.06.2022 | WCDM Strategy developed | WCDM Strategy developed | Current reported water loss is below 30%. The municipality must maintain this below 30%
|  | High water losses, unnaccounted for water and non-revenue water | '- Identify top 100 consumers in the municipality per category - Ensure all top consumers have functional meters - Read all top consumer meters on a monthly basis | In-house & WSIG Funding | In-house & contracted services | Director: Technical Services | 01.11.2020 | 30.09.21 | Top 100 Consumers identified and meters functional and read | Monthly meter readings
|  |  | - Install check meters on strategic billing (Amatola Water) meters; - Installation and monitoring of zone meters (Makana East and Makana West) | In-house & WSIG Funding | In-house & contracted services | Director: Technical Services | 01.11.2020 | 30.06.21 | Installation of 20 Check meters | GPS co-ordinates and photos of meter installations
|  |  | Calibration of Bulk Meters @ WTW | In-house & WSIG Funding | In-house & contracted services | Director: Technical Services | 01.11.2020 | 30.12.21 | Calibration of 10 Bulk Meters | 10 x Calibration certificates
|  |  | Installation of Billing meters in the peri-urban and rural areas (non revenue water and infill houses billing) | In-house & WSIG Funding | In-house & contracted services | Director: Technical Services | 01.11.2020 | 30.06.22 | 250 Billing meters installed | GPS co-ordinates of 250 billing meters
|  |  | Water Balancing Smart Meter Monitoring | In-house & WSIG Funding | In-house & contracted services | Director: Technical Services | 01.11.2020 | 30.06.22 | Electronic Water balance for Alice | Water Balance report for Alice
|  |  | Calculation and reporting on a monthly basis of water losses per water treatment plant. | In-house | In-house, Contracted Services | Director: Technical Services | 01.06.2021 | 31.11.2021 | Water Balance Calculation | Water Balance Report | Current reported water loss is below 30%. The municipality must maintain this below 30%
|  |  | Identify areas of largest losses and focus on actions to reduce losses in these areas | In-house | In-house, Contracted Services | Director: Technical Services | 01.06.2021 | 31.11.2021 | Area based water balance calculation | Area based water balance calculation | Current reported water loss is below 30%. The municipality must maintain this below 30%
|  |  | Audit Water Meters • Replace malfunctioning meters • Capture non-metered households | In-house | In-house, Contracted Services | Director: Technical Services | 01.06.2021 | 31.11.2021 | Meter audit report | Meter audit report | Meter audit report
|  |  | Implement a vigorous awareness campaign to educate all consumers of their obligations to pay timeously | In-house | In-house, Contracted Services | Director: Technical Services | 01.06.2021 | 31.11.2021 | Community Activations in each municipality per month | One activation per municipality per month | One activation per municipality per month
|  |  | Implement water restrictions and cut-offs to non-paying entities, companies; institutions and all other consumers and government departments | In-house | In-house, Contracted Services | Director: Technical Services | 01.06.2021 | 31.11.2021 | Cut-off lists for (1) governement departments, (2) business and industry and (3) other consumers | Cut-off lists for (1) governement departments, (2) business and industry and (3) other consumers | Target a 95% collection rate by increasing a collection rate by atleast 5% per month.
|  |  | Water Quality must comply to SANS 0214 | In-house | In-house, Contracted Services | Director: Technical Services | 01.06.2021 | 31.11.2021 | Comply with SANS 0214 | SANS 0214 Compliance Report | Comply with SANS 0214
|  |  | Adequate skilled, competent technical staff for maintenance and meter reading (artisans) in line with the Institutional Model on filling of critical vacancies and review of the organization structure. | In-house | In-house | Director: Technical Services; Corporate Services | 01.06.2021 | 31.11.2021 | Skills Audit Report and Workplace Skills Program | Skills Audit Report and Workplace Skills Program | Training to improve competency using available budget
6 | Sanitation Services (Waterborne and non-waterborne) | The municipality does not to operate its facilities in line with the National Water Act of 1998 (Act No. 36 of 1998, Government Notice No 1191) in accordance with the Permit requirements of Department of Water and Sanitation. | Emergency repairs and refurbishment of all water borne sanitation systems | In-house | In-house, Contracted Services | Director: Technical Services | 01.06.2021 | 31.11.2021 | Functional WWTW | Project Progress Report
7 | Fleet Management | Inadequate fleet to perform municipal functions optimally. | Develop a short-term fleet management and funding plan | In-house | In-house | MM, CFO, Technical Director, Corporate Services | 01.06.2021 | 30.11.2021 | Short Term Fleet Management and Funding Plan | Fleet Performance Progress Report
|  |  | Implement a Fleet Management System | In-house | In-house, Contracted Services | MM, CFO, Technical Director, Corporate Services | 01.06.2021 | 30.11.2021 | Fleet Management Parameters (fuel use, harsh braking, kilometers travelled, vehicle licensing, driver licensing, insurance, etc) | Fleet Performance Progress Report
|  | Inadequate maintenance of municipal fleet | Develop a high-level maintenance plan for on the critical fleet infrastructure assets and based on the conditional assessment on the asset register. | In-house | In-house | MM, CFO, Technical Director, Corporate Services | 01.06.2021 | 30.11.2021 | Conditional Assessment of Fleet. Maintenance Plan | Fleet Performance Progress Report
|  |  | Licences of redundant vehicles to be cancelled, new licences to be updated. | In-house | In-house | MM, CFO, Technical Director, Corporate Services | 01.06.2021 | 30.11.2021 | Up to date vehicle licensing register. | Fleet Performance Progress Report
|  |  | Insurance payments to be reviewed and paid, as necessary. Insurance claims to be submitted as necessary and costs recouped. | In-house | In-house | MM, CFO, Technical Director, Corporate Services | 01.06.2021 | 30.11.2021 | Insurance Management Parameters (payment of premiums, review of insurance premiums, claims management including recouping of funds from "at fault persons", paying liability if municipal at fault, etc) | Fleet Performance Progress Report
|  | Inadequate maintenance of municipal fleet | Ensure that the mechanical workshop is functional to repair vehicles and equipment internally | In-house | In-house | MM, CFO, Technical Director, Corporate Services | 01.06.2021 | 30.11.2021 | Functional Mechanical Workshop | Fleet Performance Progress Report
|  |  | Repair / salvage dysfunctional equipment | In-house | In-house | MM, CFO, Technical Director, Corporate Services | 01.06.2021 | 30.11.2021 | Items for repair and salvage | Fleet Performance Progress Report
|  |  | Auction off redundant equipment in line with legislation and policy | In-house | In-house | MM, CFO, Technical Director, Corporate Services | 01.06.2021 | 30.11.2021 | Items for disposal and auction date | Fleet Performance Progress Report
8 | Waste Management | Non-alignment of waste transfer system with regional waste management, land claims, land availability, availability of market for recyclable material and buffer zone encroachment. | Monitoring of compliance with Integrated Waste Management Plan (IWMP) of Makhanda Landfill Site | In-house | In-house | Technical Director | 01.06.2021 | 30.11.2021 | Council resolution from Mnquma Municipality accepting transfer of Eastern Regional Waste Site | Council resolution from Mnquma Municipality accepting transfer of Eastern Regional Waste Site
Monitoring of compliance with Integrated Waste Management Plan (IWMP) of Alicedale Landfill Site
Monitoring of compliance with Integrated Waste Management Plan (IWMP) of Riebeeck East Site
9 | Capital Expenditure | Grants are not fully spent and projects are not completed as planned | Monitoring of grant performance | In-house | In-house, Contracted Services | Director: Technical Services | 01.06.2021 | 30.11.2021 | 100% Grant Expenditure | Grant Expenditure and Project Progress Report
10 | Roads and Stormwater | Poor roads and stormwater conditions in the municipality | Implementation of the Rural Road Asset Management Program | In-house | In-house, Contracted Services | Director: Technical Services | 01.06.2021 | 30.11.2021 | Rural Road Asset Management Report | Rural Road Asset Management Report
11 | Reconciliation of Bulk Water and Electricity accounts | Overbilling of bulk water and electricity | - Reconcile billed consumption Department of Water and Sanitation. | In-house | In-house | Director: Technical Services / Corporate Services | 01.11.2020 | 30.12.21 | Reconciled billing report | List of all billing points
|  |  | - Reconcile all Amatola Water accounts; - Monitor Amatola Water monthly consumption | In-house | In-house | Director: Technical Services / Corporate Services | 01.11.2020 | 30.06.21 | Reconciled billing report | List of all billing points
|  |  | - Reconcile Eskom accounts with actual supply points meter readings | In-house | In-house | Director: Technical Services / Corporate Services | 01.11.2020 | 30.06.21 | Reconciled billing report | List of all billing points
12 | Reduction in the cost of water production | High unit cost of water production | - Optimise chemical dosage at water treatment works to ensure the most cost effective chemical is being used; | In-house | In-house | Director: Technical Services | 01.11.2020 | 30.09.21 | Reduced water production costs | Report on the reduction of chemical consumption
|  | Tariff is not cost reflective | - Investigate and develop water and sanitation tariff structure | MISA | MISA | Director: Technical Services | 01.11.2020 | 30.06.22 | Council approved tariff | Report on tariff setting
13 | Service Delivery Monitoring | No system to instantly monitor service delivery perfomance | Procurment / development of Project Management System | External / Service provider | Funding | Director: Technical Services | 01.11.2020 | 30.12.21 | Project Management System Procured / Developed | Project Management System
14 | Strengthen Coordination Forums | Non coordination and fragmented implementation of programmes and projects by different sector departments | Quarterly meetings with Sector Departments & key stakeholders | In-house | In-house | Director: Technical Services | 3rd Quarter 2021 | Ongoing | Quarterly meetings attended by Sector Departments and key stakeholders | Minutes and attendance register of quarterly meetings
15 | Funding for Sustainable water, electricity, waste management, fire and local economic development solutions | Insufficient water resources | Development of Business Plans for Sustainable for Sustainable water solutions / projects, lobbing stakeholders | COGTA, MISA, DWS, SALGA, National Treasury | DWS | Director: Technical Services | 01.07.2021 | 30.12.21 | Business Plans developed | Business Plans & letters to potential funders

## Phase 2 Stabilisation
PHASE 2: STABILIZATION
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR ONE: GOVERNANCE
1 | Unauthorised, Irregular, Fruitless and Wasteful expenditure | Non-reporting, no consequence management, disciplinary board not properly constituted) - UIFW not investigated to determine if any person is liable for the expenditure, as required by Section 32(2)(a) of the MFMA | Develop and implement UIF&W expenditure reduction plan. | In-house and NT-MFMA unit | In-house and NT-MFMA unit | Chief Finance Officer | 01.12.2021 | Monthly | UIF&W expenditure reduction plan implementation and percentage reduction in historical expenditure | Quarterly Council reports on progress on implementation of the reduction plan
|  |  | Implement measures to prevent and address unauthorised, irregular, fruitless and wasteful expenditure | In-house | In-house | MM, CFO, Directors | 01.12.2021 | Monthly | Percentage reduction in current UIF&W expenditure | AG Audit report and internal audit reports
|  |  | Identify, investigate and report on irregular, unauthorised, fruitless and wasteful expenditure as per legislation | In-house | In-house | Council, MPAC, Disciplinary Board | 01.12.2021 | Quarterly | Quarterly reports on UIF&W expenditure and investigations | Council approved quarterly reports, MPAC oversight reports, Disciplinary Board's reports and related resolutions
|  |  | Implement Consequence management | In-house | In-house | Disciplinary Board, Executive Mayor and MM | 01.12.2021 | Monthly | Transgressors disciplined | Written outcome of disciplinary hearings
2 | System of Delegations | Inadequate separation of powers and functions between Council, Executive and administration; No clear distinction of legislative and delegated powers for elected and appointed officals; No clarity on lines of accountability; generic powers to directors an error; No powers delegated to CFO; Ultra vires delegations | Update delegations register | In-house | In-house | Director: Corporate Services | 01.12.2021 | 31.12.2022 | Sub-delegations emanating from approved System of delegations signed-off by MM and Heads of Directorates | Approved system of delegations, signed-off sub-delegations. Updated delegations register
3 | Contract Management | Contracts not adhering to procurement legislation, payment of service providers not made in thirty days, High percentage of contracted services, poor internal controls, non submission of monthly performance monitoring reports on contracts, unnecessary deviations | Maintain an updated contract register | In-house | In-house | Director: Corporate Services and CFO | 01.06.2021 | 31.12.2022, Monthly | No irregular, unnecessary or expired contracts, and contracts register in place | Updated contract register
|  |  | Monitor deviations to identify other goods and services required on an ongoing basis and appoint service providers on three year contracts | In-house | In-house | CFO | 01.12.2021 | 31.12.2022, Monthly | Reduction in operational costs, Reduction in irregular deviations, compliance with legislation | Reduction in procurement costs as per procurement plan, and appointment letters
|  |  | Submission of monthly performance monitoring reports on contracts | In-house | In-house, Contracted Services | CFO | 01.06.2021 | 31.12.2022, Monthly | value for money, compliance with legislation | Monthly performance monitoring reports
|  |  | Implementation of contract management framework | In-house and COGTA/SALGA | In-house and COGTA/SALGA | CFO/Director: Corporate Services | 01.06.2021 | 31.12.2022 | Effective contract management and comliance with legislation. | AG audit reports and quarterly Internal audit reports
|  |  | Monitor implementation of approved annual procurement plan | In-house | In-house | CFO | 01.12.2021 | 31.12.2022 | Reduction in operational costs related to procurement | Approved reviewed procurement plan and Council resolution for 2022/23 financial year
4 | Litigation and Contingent liability | No litigation strategy, enormous increase in contingent liability, pending litigation matters, non-compliance with legislation | Monthly update litigation register | In-house | In-house | Director: corporate Services | 01.12.2021 | 31.12.2022, Monthly | Reduction in legal costs, updated litgation regster in place | Monthly updated litigation register
|  |  | Implementation of Council resolutions on diagnostic analysis of root causes of litigations and claims | In-house | In-house | Director: corporate Services | 01.06.2021 | 31.12.2022 | Mitigation against identified root causes. Reduction of contingent liability and financial exposure. | Annual financial statements and AG audit reports, and quarterly Internal Audit reports
|  |  | Conduct a legal assessment on reasonable prospects of success on new litigation matters | In-house | In-house | Director: corporate Services | 01.12.2021 | 31.12.2022 | Reduction in contingent liability | Assessment reports on new litigation matters. Proof of settlement of matters
|  |  | Implementation of MFMA Legal compliance matrix | In-house | In-house and NT-MFMA unit | Director: corporate Services | 01.12.2021 | 31.07.2022, Monthly | Legislative compliance | AG annual audit reports and quarterly internal audit reports
5 | Risk and internal Audit | Inaccurate and unreliable financial and performance information; Incomplete audit reviews, no adequate record keeping system, Ineffective implementation of forensic investigation reports, misdiagnosis of risks; Non implementation of appropriate risk management activities; internal control deficiencies; stagnant audit findings; no oversight over performance management system | Maintain an updated risk register | In-house | In-house | Manager: Internal Audit | 01.12.2021 | 31.12.2022 | Effective management of corporate risks | Updated risk register
|  |  | Quarterly reports on internal audit and risk management | In-house | In-house | Manager: Internal Audit | Quarterly | Quarterly |  | Quarterly reports and Council resolutions
|  |  | Report progress on implementation of AG audit action plan | In-house |  | Manager: Internal Audit | 01.12.2021 | 31.12.2022, Quarterly | Improved governance and accountability | Approved updated AG audit action plan and Progress reports to Council
|  |  | Quarterly progress reports on implementation of remedial actions to mitigate against corporate risks and annual audit plan | In-house | In-house | Manager: Internal Audit | 01.12.2021 | Quarterly | Effective management of identified risks | Quarterly reports and Council resolutions
|  |  | Approval of annual audit plan and risk management documents for 2022/23 financial year |  |  | Manager: Internal Audit | 01.06.2022 | 31.06.2022 | Policies and plans in place | Approved annual audit plan and risk management documents, and related Council resolutions
6 | By-laws and Enforcement | Redundant and outdated by-laws; No enforcement of by-laws and reporting on revenue generated | Enforcement of By-laws | In-house | In-house, NPA and Department of Justice | Director: Community safety | 01.12.2021 | Monthly | Effective enforcement of by-laws. Reduction in electricity and water losses. | Quarterly audited reports on revenue generated from enforcement of by-laws.
|  |  | Report on revenue generated | In-house | In-house | Director: Community safety | 01.12.2021 | Monthly | Increase in revenue | Quarterly audited reports on revenue generated from enforcement of by-laws.
7 | Governance Oversight Structures | Limited oversight by Council over executive and administration, No investigation on UIF&W expenditure | Development of annual schedule of meetings and adherence for council and committees for 2022/23 financial year | In-house | In-house | Director: Corporate Services | 01.06.2022 | 31.06.2022 | Schedule of meetings in place and adhered to. | Approved schedule of meetings and Council resolution
|  |  | Review terms of reference for MPAC to add more oversight responsibilities | In-house | In-house and COGTA | Director: Corporate Services | 01.06.2021 | 31.11.2021 | Increased oversight by Council and its commitees over the Executive and administration. | Approved reviewed terms of reference and Council resolution.
|  |  | Increase and monitor frequency of meetings for MPAC for 2022/23 financial year | In-house | In-house | Director: Corporate Services | 01.12.2021 | 31.12.2022, Quarterly | Increased oversight by Council and its commitees over the Executive and administration. | Approved annual schedule of Council and committee meetings and Council resolution
|  |  | Convene meetings of TROIKA | In-house | In-house and COGTA/SALGA | MM/Director: Corporate Services | 01.12.2021 | 31.12.2022 | Effective political and administrative interface | Minutes of meetings
|  |  | Maintain annual schedule of TROIKA meetings | In-house | In-house | Director: Corporate Services | 01.12.2021 | 31.12.2022 | Organised and focused TROIKA | Approved schedule of meetings and Council resolution
|  |  | Enforcement and monitoring of the code of conduct for councillors | In-House | In-house | Speaker of Council | 01.12.2021 | Monthly | Disciplined councillors and adherence to legal prescripts | Quarterly reports on compliance with code of conduct by Councillors
|  |  | Develop schedule and implementation of meetings for Executive management meetings | In-house | In-house | MM | 01.12.2021 | 31.12.2022, Monthly | Effective and efficient co-ordination of administration and service delivery | Approved schedule of meetings and Council resolution
|  |  | Develop and implement training programme for councillors on governance, financial management and oversight; | In-house | In-house | Director: Corporate Services | 01.12.2021 | 30.04.2022 | Empowered Councillors to execute their responsibilities | Council approved training programme and resolution, and attendance register.
8 | Information and Communication Technology | Lack of ICT general controls on ICT governance, user access management, programme change management, security management, ICT service continuity. | Implementation of ICT Governance framework more specifically general controls | In-house | In-house | Director: ICT | 01.12.2021 | Monthly | Effective ICT general controls, assurance on confidentiality and integirty of data. | AG Audit report and internal quarterly audit reports
|  |  | Monitor recruitment processes to maintain conduct cost-benefit analysis outcome and implementation | In-house | In-house | Director: ICT | 01.12.2021 | 31.12.2022 | Reduction in operational expenditure ad elimination of duplication between technology and available human resources | Annual financial statements and AG audit reports, and quarterly Internal Audit reports on employee related costs
PILLAR TWO: INSTITUTIONAL
1 | HR Strategy (HRD&M) | Current strategy / plan is outdated | Analyse HR Maturity level, identify gaps, drat the HRD&M | In-house, SALGA, CoGTA, NTMFRS | In-house | Exec. Dir. CS | 01.01.2022 | 30.06.2022 | Approved HRD&M | HR Maturity report, Council resolution | N/A
2 | Skills Audit | Skills audits have not been conducted except for WSP | Determine a sample, develop skills audit template and questionnaire, collate and analyse employees information, Produce skills audit | In-house, SALGA, CoGTA | In-house | Exec. Dir. CS | 01.01.2022 | 30.06.2022 | Completed skills audit | Analysis report, skills audit and Council report
3 | Minimum Competency Regulations | Not all affected employees have completed the Course. | Enroll all Senior Managers and affected personnel (s119-MFMA) | In-house | In-house - own budget, LGSETA | Exec. Dir: CS | 01.01.2022 | 31.11.2021 | Improved compliance | Proof of registration, results, certificates
4 | Employee Costs | Current costs are at 44% of the Opex. | Analyse of employees: age, ill health, redundancy. Develop Separation policy. Offer retrenchment packages | In-house MFRS Advisory Support | In-house MFRS Advisory Support | Exec. Dir: CS | 01.01.2022 | 30.06.2022 | Reduction in employee costs | Progress reports, staff establishment reports, Approved policy | Reduced employee costs by 5%
5 | Performance Management | PMS is not cascaded to lower levels below MM and direct reports | Cascade PMS from level 2 to 4 | In-house, Support from NTMFRS/ SALGA/CoGTA | In-house | Exec Director: CS | 01.01.2022 | 30.06.2022 | Imporoved performnace, service delivery and audity outcome | Approved PMS Policy, PM Agreements and Evaluation reports
6 | Organisation Structure | Current structure was last reviewed in Oct 2019. Current employee costs are at 44 % Current Structure is bloated (top heavy) | Conduct an assessment of current structure, Conduct staff verification Assess powers/functions Draft review of structure Develop options on cost reduction, Develop Placement Policy/ Plan LLF consultations | In-house | In-house | MM, Exc. Director: CS | 31.11.2021 | 30.06.2022 | Functions properly aligned to strategic objectives and legal mandate Improved service delivery Achieved affordability Achieved completeness of employee costs | Approved organisation structure, Council resolution | Reduced employee costs by 5%
PILLAR THREE: FINANCIAL MANAGEMENT
1 | Funded Budget Adjustment 2021/22 and MTREF Funded Budget for 2022/23 | Funded budget | Compile a 2021/22 adjustment budget in line with reviewed targets for realistically anticipated revenue and expenditure trends and mandatory budget prioritization provided in this financial recovery plan to ensure revised budget to be credible and cash funded and takes strategies of the plan into account | Budgeting skills | EC PT Support | MM, CFO, PT | 01.01.2022 | 31.12.2022 | Credible and funded 2021/22 adjustment budget. An adjustment budget that reflects realistically anticipated revenue and expenditure, austerity and cost cutting measures and cash funded budget. Credible budget baseline for future budgeting and long term financial planning. IDP and Budget related policies for 2019/20 MTREF consistent with the Financial Recovery Plan and Legislative Framework. | Funded 2021/22 Adjustment budget
|  |  | Austerity and cost cutting measures to be reflected in the 2021/22 Adjustment Budget. | Best-Practise Advise | NT 2019 Cost Containment Regulations | MM, CFO, PT | 01.01.2022 | 31.12.2022 | Cost containment report in support of the budget | Cost containment report in support of the budget
|  |  | Council adopt funded 2021/22 Adjustment Budget | In-house | EC PT Support | Council | 01.01.2022 | 31.12.2022 | Adopted 2021/22 funded adjustment budget | Adopted 2021/22 funded adjustment budget
|  |  | Implementation and monitoring of the approved adjustment budget for 2021/22. | In-house mSCOA compliant system with spending limits aligned to | EC PT Monitoring | MM, CFO, PT | 01.01.2022 | 31.12.2022 | Sec 71 reports compliant with the adopted 2021/22 funded adjustment budget. Savings in identified intervention areas and increase in actual revenue. Strict controls over revenue and expenditure consistent with delegations and approved budget. Reduction in deviations, irregular, fruitless and wasteful and unauthorised expenditure to acceptable norm. | Sec 71 monthly report showing income and expenditure within the funded budget MFMA Section 52(d) reports with variance analysis
|  |  | Develop the MTREF budget, policies, by-laws and IDP | In-house | In-house. EC PT Oversight | CFO, MM, S56 Managers | 01.01.2022 | 31.12.2022 | Compliant 2022/23 budget certified by Provincial Treasury | Funded and Compliant 2022/23 budget | Depreciation: 100% per GRAP 17 Standard (4) Debt Impairment: 100% - Budgeted Collection Rate (5) Contracted Services: <8% of OPEX(2022/23)
|  |  | Austerity and cost cutting measures to be reflected in the 2022/23 MTREF Budget. | Best-Practise Advise | NT 2019 Cost Containment Regulations | MM, CFO | 01.01.2022 | 31.12.2022 | Cost cutting report in support of the budget | Cost cutting report in support of the budget
|  |  | Council adopt funded 2022/23 MTREF Budget | In-house. | EC PT Support | Council | 01.01.2022 | 31.12.2022 | Adopted 2022/23 funded budget | Adopted 2022/23 funded budget
|  |  | Implementation and monitoring of the approved budget for 2022/23. | In-house. | EC PT Monitoring | MM, CFO | 01.01.2022 | 31.12.2022 | Sec 71 reports reflecting revenue and expenditure in accordance with the adopted funded budget. Savings in identified intervention areas and increase in actual revenue. Strict controls over revenue and expenditure consistent with delegations and approved budget. Reduction in deviations, irregular, fruitless and wasteful and unauthorised expenditure to acceptable norm | Sec 71 monthly report showing income and expenditure within the funded budget MFMA Section 52(d) reports with variance analysis
2 | Cash Flow Management | Liquidity challenges | Implementation of a credible cashflow projection for the 2021/22 MTREF budget including adjustments budget | In-house | EC PT Support | CFO, MM,S56 Managers | 01.01.2022 | 31.12.2022 | Improved Cash Flow Position | Cash flow management plan implementation report | Cash Balances Per Budget Funding Plan (1) Targeted ratios:- Cash Coverage: 1,5 (2) Current Ratio:- Norm = 1.5-2:1
|  |  | Management of the cash-flow on a daily basis with weekly reporting to the Administrator, MM and management meetings | In-house | EC PT Support | CFO, MM,S56 Managers | 01.01.2022 | 31.12.2022 | Weekly cash flow management reports | Weekly cash flow management report. Attendance register and minutes of meetings
|  |  | Implementation of cost containment measures | In-house | EC PT Support | CFO, MM,S56 Managers | 01.01.2022 | 31.12.2022 | Monthly cost savings report | Monthly financial impact report on the implemented cost containment policy
|  |  | Review all grant expenditure to ensure capital grant expenditure align with the grant conditions | In-house | EC PT Support | CFO, MM,S56 Managers | 01.01.2022 | 31.12.2022 | 100% Unspent Conditional Grants cash-backed. 100% DORA Compliance. | Monthly grant expenditure report
3. | Trading debtors and collection rate | Low collection Rate | Implement the credit control and debt collection policy | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.01.2022 | 31.12.2022 | Achieved collection rate of 85%. Reduced government debt by 10%. Reduce Business debts by 5%. Reduce Household debts by 2.5% (Month 1-12) | Monthly billing and collection report. Monthly debtors report showing reduced debtors balances. | Reduced government debts by 10% per month. Reduced business debts by 5% per month. Reduced households debt by 2.5% per month
|  | Government depts owe the municpality | Ensure government debts are paid as per the payment agreement | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.01.2022 | 31.12.2022 | Reduced government debts. | Monthly debt payment by government departments | Reduced Government debt by R1 million per month
|  | Businesses and others owe the municpality | Ensure businesses and other debts are paid as per the payment agreement | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.01.2022 | 31.12.2022 | Reduced business and other debts. | Monthly debt by businesses and others | Reduced Businesses and other debt by R5 million per month
|  | Housegolds owe the municpality | Ensure households debts are paid as per the payment agreement | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.01.2022 | 31.12.2022 | Reduced household debts. | Monthly debt payment by households | Reduced households debt by R10 million per month
|  |  | Repair and replacement of faulty meters | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.01.2022 | 31.12.2022 | Meter replacement report. | Meter replacement report.
|  |  | Identification and registration of Indigent Households for free basic services (to reduce debtors) | In-house capacity available | EC PT Support | MM, CFO, S56 Managers | 01.01.2022 | 31.12.2022 | Updated indigent register. | Updated indigent register.
4 | Revenue and Expenditure Management | Weak revenue and expendituire management | Implementation of revenue management (including data cleansing, tariff modelling, standard operating procedures, policies/ by-laws, credit control, debt collection and indigent management) | In-House, PT EC CoGTA | In-House. EC CoGTA Support Package for Revenue Project | CFO, MM, S56 Managers, Legal Services | 01.01.2022 | 31.12.2022 | Improved financial stability. Reduction in UIF&W. Accurate and complete consumer database. Increase in collection levels. | Data cleansing report. Monthly collection report with uncreased collection rate
|  |  | Expenditure management (including SCM, value for money, cost containment, efficiency and effectiveness) | In-House, PT EC CoGTA | In-House. EC CoGTA Support Package for Revenue Project | CFO, MM, S56 Managers, Legal Services | 01.01.2022 | 31.12.2022 | Sec 71 reports reflecting revenue and expenditure in accordance with the adopted funded budget. Savings in identified intervention areas and increase in actual revenue. Strict controls over revenue and expenditure consistent with delegations and approved budget. Reduction in deviations, irregular, fruitless and wasteful and unauthorised expenditure to acceptable norm | Sec 71 monthly report showing income and expenditure within the funded budget
|  |  | Cash management (ensuring that procurement is based on realistic cashflows) |  |  |  | 01.01.2022 | 31.12.2022 | Monthly cash flow management report
|  |  | Maintain robust cash management tool |  |  |  | 01.01.2022 | 31.12.2022 | Improved Cash Flow Position | Cash flow management SOPs
|  |  | Compile a cash-flow projection for the financial year upon completion of the 2022/23 Budget, showing realistic monthly projections |  |  |  | 01.01.2022 | 31.12.2022 | 2022/23 cash flow projection compiled | Cash flow management plan
|  |  | Management of the cash-flow daily with weekly reporting to the MM and management meetings |  |  |  | 01.01.2022 | 31.12.2022 | Weekly cash flow reports | Weekly cash flow management report. Attendance register and minutes of meetings
|  |  | Ensure that all contracts are current. Continue to review committed contracts to determine which contracts have lapsed or which can be cancelled without the risk of legal action against ADM |  |  |  | 01.01.2022 | 31.12.2022 | Monthly report on contracts | Contract register. Monthly report on the status of all contracts
|  |  | Continue to investigate contingent liabilities and meetings with claimants to be held where legal action can be suspended to resolve claims amicably |  |  |  | 01.01.2022 | 31.12.2022 | Monthly report and minutes of meetings on contingent liabilities | Contingent liabilities register with monthly progress report
5 | BTO Office | BTO not capacitated | Review of current delegations and sub-delegations for BTO staff | In-house. PT, CoGTA. | In-house. PT, CoGTA. | CFO, MM, Manager Corporate Services | 01.01.2022 | 31.12.2022 | Functional BTO. Increase in collection levels. Reduced billing queries. | Approved delegations
|  |  | Skills development of BTO staff and assigning of responsibilities to appropriately skilled staff |  |  | CFO, MM, Manager Corporate Services | 01.01.2022 | 31.12.2022 | Functional BTO. Increase in collection levels. Reduced billing queries.
|  |  | Ensure IT systems are utilised fully to assist with revenue management and enhancement. |  |  | CFO, MM, Manager Corporate Services | 01.01.2022 | 31.12.2022 | Functional BTO. Increase in collection levels. Reduced billing queries. | IT systems report
6 | FMCMM | FMCMM not implemented | Develop an action plan using the FMCMM template to address outcomes of the assessment |  |  | CFO, MM, Manager Corporate Services | 01.01.2022 | 31.12.2022 | FMCMM reports. Institutional health | FMCMM action plan
|  |  | Implementation of FMCMM action plan |  |  | CFO, MM, Manager Corporate Services | 01.01.2022 | 31.12.2022 | FMCMM reports. Institutional health | FMCMM action implementation report
7 | Supply Chain Management | Inadequate systems and procedures | Develop Standard Operating Procedures | In-house | In-house | CFO, MM, Manager Corporate Services | 01.01.2022 | 31.12.2022 | SCM SOP approved and implemented | Reviewed SOPs
|  |  | Review and updating of all financial internal controls including procurement, contract and supplier management |  |  | CFO, MM, Manager Corporate Services | 01.01.2022 | 31.12.2022 | SCM SOP approved and implemented | Reviewed financial policies and internal control measures
|  |  | Training of Bid Committees |  |  | CFO, MM, Manager Corporate Services | 01.01.2022 | 31.12.2022 | SCM SOP approved and implemented | Training report
|  |  | Improve SCM System |  |  | CFO, MM, Manager Corporate Services | 01.01.2022 | 31.12.2022 | SCM SOP approved and implemented
8 | Contract Management | Uneconomical contracting | Establishment of contract management sub-unit within SCM division | In-house | In-house | CFO, MM, Manager Corporate Services | 01.01.2022 | 31.12.2022 | Supplier performance reports. Value for money contracting | Improved contract register and the corresponding report
9 | MSCOA | Not MSCOA compliant | Establish a functional financial management and accounting system by implementing all mSCOA reforms. | In-house. NT MFIP. | In-house. NT MFIP. | In-house. NT MFIP. | 01.01.2022 | 31.12.2022 | Recorded MSCOA Progress. Financial system assessment report | mSCOA implementation progress report
|  |  | Ongoing implementation in line with Implementation Plan | In-house. NT MFIP. | In-house. NT MFIP. |  | 01.01.2022 | 31.12.2022 | mSCOA implementation report | mSCOA compliant report
10 | Internal Audit | Weak internal controls | Risk Based IA Plan | In-house | In-house | CFO | 01.01.2022 | 31.12.2022 | Reduced UIF&W report. Reduced AG findings | Reduced UIF&W report
11 | Financial Reporting | AFS Outsourced | Build internal capacity to prepare the AFS | In-house | In-house | CFO | 01.01.2022 | 31.12.2022 | Reduction in contracted services fees | AFS prepared internally
PILLAR FOUR: SERVICE DELIVERY
1 | Asset Management Master Plans | Lack of skills, Non-compliance with Asset Management Policy and Procedure Manual, Lack of asset replacement strategy. | Development and implementation of Asset Management policy and strategy. Development and implementation of a long-term Asset Management Master Plans that will investigate long term investments, replacement, maintenance and sustainability of the municipality, amongst others Development of Property Plant and Equipment maintenance plan Audit of current infrastructure to determine state, taking into consideration service backlogs and long-term strategy aligned to the operating model IDP, budget and long-term financial plan Update and maintain Asset Register Maintenance of Property Plant and Equipment through internal capacity and outsourced services Review contracts and tariffs on municipal buildings being leased and hired. | In-house | In-house | MM, CFO, Technical Director | 01.12.2021 | 30.11.2022 | Asset maintenance plans Approved building maintenance plan Update and maintained Asset Register | GRAP Compliant Asset Register Asset Management Plans | Target 8% of OPEX
2 | Roads and Stormwater | Road surface marking visibility | Implement the roads and stormwater master plan Develop and implement the Roads and Stormwater Maintenance plan Maintenance of roads infrastructure through internal capacity and outsourced services Rehabilitate roads as per Maintenance Plan | In-house | In-house | MM, Director: Technical Services | 01.12.2021 | 30.11.2022 | Approved Maintenance Plan Repaired roads Rehabilitated roads Completed roads projects | Rural Road Asset Management Report | N/A
3 | Portable Water Supply and Bulk Water | Poor drinking water quality, Water Losses, Water Shortages, Lack of accounting, Revenue Collection | Implement the Water Master Plan Development of WSDP Develop a Water Infrastructure Maintenance plans Develop and implement a Water Conservation and Water Demand Management Plan (municipal-wide) Network Maintenance and refurbishment • Review and update tariffs to set cost reflective sanitation tariffs Development of Bulk Services contribution policy and set bulk contribution fees Enforce Water by-laws • Disconnect illegal connections. Awareness Campaign maybe required with the assistance of political office. Enforce relevant fines Water quality management and compliance, with SANS 241 • Achieve Blue Drop Requirements. Monitor water quality constantly and introduce quick corrective measures Complete Water reticulation projects • Upgrading of water reticulation network • RBIG Grant project business plans | In-house | In-house, Contracted Services WCWDM Support | MM, Director: Technical Services | 01.12.2021 | 30.11.2022 | Efficient and sustainable water management Reduce water losses Provision of new water infrastructure while upgrading existing infrastructure Improved billing Updated tariffs, policy and by-laws Reduction in illegal connection Increase in revenues and improved cash flows Improved Blue drop status Quality water and an environment not harmful to human health and wellbeing Improve quantity and quality of municipal infrastructure and services Increase capacity of WTWs Sufficient and sustainable water supply by increasing storage facilities | WSDP Plan Water losses within 30% Compliance to SANS 0241 | WSIG and MIG to be fully uitilised
4 | Sanitation Services (Waterborne and VIP) | Treatment capacity, Poor Maintenance | Implement the sanitation master plan Develop a sanitation Infrastructure Maintenance plan Rehabilitate and develop sewer reticulation network in urban areas and peri-urban areas and commence billing Improve management of WWTW | In-house | In-house Approach MISA for capacity support | MM, Director: Technical Services | 01.12.2021 | 30.11.2022 | Improve the quantity and quality of municipal infrastructure and services Approved Maintenance Plan Enhanced lifespan of assets through proactive and preventative maintenance Reduction of current blockages Quality wastewater and an environment not harmful to human health and wellbeing | Plant Performance Report for WWTW Maintenance Plans | MIG to be fully utilised
5 | Fleet Management | Inadequate fleet to perform municipal functions optimally. | Develop and implement Fleet Management Strategy and Plan Development and implementation of the vehicle maintenance plan Develop and implement a insurance and fuel management policies Develop and implement vehicle replacement plan | In-house | In-house Provincial Support Package | MM, Director: Technical Services | 01.12.2021 | 30.11.2022 | Approved Fleet Management Strategy and Plan and implemented Developed planned service schedule, including costs Controlled and planned servicing and maintenance of vehicles Implemented functional Fleet and Fuel Management System Cost saving in fleet and fuel management Reduced theft and abuse Replacement of redundant/ obsolete fleet Reduced vehicle downtime and increased utilisation/ uptime Modernised and reliable feet | Fleet Performance Plan | In line with approved Budget and Mobilised Funding
6 | Fleet Maintenance | Inadequate maintenance of municipal fleet | Establish and equip workshop with basic tools and equipment and stock for priority, medium term operations Fleet maintenance team to comply to OHS standards All operable vehicles to be checked for roadworthiness repaired and certified as roadworthy. If unsalvageable then use as scrap parts or auction off vehicle in terms of legislation and policy. | In-house | In-house | MM, Director: Technical Services | 01.12.2021 | 30.11.2022 | Functional equipmentx Workshop operating at minimum OHS standards Valid roadworthy certificates for all operable vehicles | Fleet Performance Plan | N/A
7 | Project Management Unit (PMU) | Capacitation of the unit to achieve 100% expenditure on all capital execution projects | 100% expenditure and progress as per procurement and project implementation plan. | In-house | In-house | MM, Director: Technical Services | 01.12.2021 | 30.11.2022 | Improved forward planning and implementation of projects Improved service delivery |  | N/A
8 | Security Services | Municipal property must be protected from vandalism. | Develop Security Policy that covers internal and outsources security services. Review security strategy to incorporate the guarding of municipal property, staff, customers and equipment. | In-house | In-house | MM, Director: Technical Services | 01.12.2021 | 30.11.2022 | Asset Management Policy to include how assets within the municipality are protected. Asset Management Policy to include how assets within the municipality are protected. |  | N/A

## Phase 3 Sustainability
PHASE 3: SUSTAINABILITY
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR ONE: GOVERNANCE
PILLAR TWO: INSTITUTIONAL
PILLAR THREE: FINANCIAL MANAGEMENT
PILLAR FOUR: SERVICE DELIVERY