## Basic Service Delivery INF
Objective | Strategy |  | Key focus Areas | Budget | Source | Project/Program | Projects Register ID | Key Perfomance Indicator |  | Annual Target | Service Delivery Model | Milestones |  | Milestones |  | HALF YEAR REPORT: JULY - DECEMBER 2013 |  |  | Milestone | [6 empty] | Reponsible Directorate
[9 empty] | Annual Budget |  |  | Quarter 1 | Quarter 1 Actual | Quarter 1 | Quarter 2 Actual | Variance | Corrective action | Quarter 2 | Quarter 3 | Status | Progress | Quarter 4 | Progress | Reasons for Deviation | Corrective Action
Well structured, efficient provision of basic services and that supports sustainable human settlement by 2017 | Provide quality road and stormwater | KFA 1.1 | Roads and Stomwater | 400000 | Capital | Development Stormwater Master Plan and Design | IDP 1.00 | Compile a Stormwater Master Plan and Design |  | N/A
|  | KFA 1.1 | Roads and Stomwater | R 3000000-500 000 for EPWP | Operational | Construction of kerbs using EPWP Model | IDP 1.01 | Number of meters construcuted and number of temporal job created | 500000 | 150 Meters | Outsorced | 10% (Procument) | Advertised on 26/07/13 and busy with BEC |  |  |  | To be done in 2014/2015 FY | 50% Complete | 100% Complete |  |  | N/A | Not implemented due to financial situation of the municipality. |  |  | D. MLENZANA (S. TUTUSE)
|  |  |  | 2000000 | Capital | Resealing of roads | IDP 1.01 | No of square meters for SLURRY SEAL and number of temporal jobs created | 2000000 | 3500 m² | Outsorced | N/A | Advertised on 26/07/13 and busy with BEC |  |  |  | To be done in 2014/2015 FY | 10% (Procument) | 100% Complete |  |  | N/A | Not implemented due to financial situation of the municipality. |  |  | D. MLENZANA (S. TUTUSE)
[6 empty] | Repairs of sidewalks - Sani Street | IDP 1.03 | No of meters repairs | 500000 | 500 Meters | Outsorced | 10% (Procument) | Material has been Purchase Through the Annual Tender and Scope of work is complete |  |  |  | To be done in 2014/2015 FY | 50% Complete | 100% Complete |  |  | N/A | Not implemented due to financial situation of the municipality. |  |  | D. MLENZANA (S. TUTUSE)
|  |  |  | 1000000 | Capital | Construction of new sidewalks | IDP 1.04 | No of Km of Sidewalks Constructed and number of temporal job created | 500000 | 200 Meters | Outsorced | 10% (Procument) | Material has been Purchase Through the Annual Tender and Scope of work is complete |  |  |  | To be done in 2014/2015 FY | 50% Complete | 100% Complete |  |  | N/A | Not implemented due to financial situation of the municipality. |  |  | D. MLENZANA (S. TUTUSE)
Well structured, efficient provision of basic services and that supports Sustainable Human Settlement by 2017. | Provide quality road and stormwater | KFA 1.1 | Roads and Stomwater | 8384162 | MIG | Upgradiing and rehabitilation of roads | IDP 1.05 | SANI Street upgrade | 6000000 | 1500 Meters | Out-sourced | 10% (Procument) | Construiction Phase |  |  | PMU to report to the MM's office | Project in progress and funded from MIG 2013/14 (To be reported by MM's office) | 50% Partially complete | N/A | Not Achieved |  | N/A | Under construction. 55% complete. | Poor perfomance of the Contractor. | Schedule has been revised | D. MLENZANA (S. TUTUSE)
|  |  |  | 8725000 | National treasury | DISASTER 2013 | ADJ SDBIP | Repair/Reconstruct/ Rehabilitate ALL damaged roads & stormwater pipes. |  | 100 % Complete | Out-sourced | N/A | N/A | N/A | N/A | N/A | N/A |  | Procurement - 100% | Not Achieved | 100% complete | 100% Complete | The project is still at a procurement stage with the appointment of a contractor imminent. | Slow procurement processes. | Schedule has been revised . | D. MLENZANA (S. TUTUSE)
| Ensure that all communities of Makana have access, constant and safe provision to adequate basic services | KFA 1.4 | WATER AND SANITATION (administration) | R12 275 500.00 Plus R 43 000 000.00 | MIG/DBSA | Upgrading of bulk water James Kleyhans | IDP 1.13 | Installation of water pipe line and construction of a new reservoir | 37648625 | 9.2km Pipeline & 1x New Reservoir | Out-sourced | 75% Partially complete | Met - PMU to give exact progress |  |  | PMU to report to the MM's office |  | 100% Complete | N/A | Not Achieved | Pipeline is being constructed. | 100% | Construction | The contractor was unable to test the rising main and the new reservoir due to the water crisis in Makana. | Project was not completed and schedule will be revised. | PMU: MANAGER
|  |  |  | 2000000 | Operational | Replacement of AC pipes | IDP 1.14 | Replacement AC pipe | 940000 | 250 Meters | Out-sourced | 50% Partially complete | Not met |  |  |  | The sope was reduced due to budget issues | 75% Partially complete | Completion - 10% | Not Achieved | No budget allocated. | Completion - 90% | Contractor appointed but not given a go ahead due financial situation of the municipality. | Financial constraints affected the project. | Project will be implemented in 2014/15 financial under t.he MIG programme | D. MLENZANA (N. TSHICILELA)
[6 empty] | Manhole Covers - Sewer | IDP 1.15 | % of Manholes covered | 150000 | 10 Manhole Covers | Out-sourced | 10% (Procument) | Not Met |  |  |  | BSC is set to sit on Thursday | 100% Complete | Procurement - 100% | Achieved | 100% complete | Completion - 100% | Completed. The order was issued to the prefered supplier and 50 manhole covers were already delivered. | N/A | N/A | D. MLENZANA (N. TSHICILELA)
[6 empty] | Replacing Sewer Main - KwaThatha | IDP 1.16 | % of complete project | 800000 | Sewer Main Line installed | Out-sourced | 10% (Procument) | Not Met |  |  |  | Received funding from Dept. of Human Settlement under the Bucket Eradication Programme | 100% Complete | Procurement - 50% | Not Achieved | 75% complete | Procurement - 50% and Implementation - 50% | Contractor not appointed yet as the matter is still at procurement stage at the SCM office. | Late funding confirmation and slow procurement processes. | NURCHA has taken over as implementation agency. | D. MLENZANA (N. TSHICILELA)
[6 empty] | Replace mechanical screen with rotary drum | IDP 1.20 | % of complete project | 300000 | 1x rotary drum replaced | Out-sourced | 10% (Procument) | Not Met |  |  |  | Service provider to be appointed | 100% Complete | Procurement - 100% | Achieved | 100% | Completion - 100% | Not implemented due to financial situation of the municipality. | N/A | N/A | D. MLENZANA (N. TSHICILELA)
[6 empty] | Water Conservation & Demand Management - R3.0m | ADJ SDBIP | % of complete project |  | 100% complete | Out-sourced | N/A | N/A | N/A | N/A | N/A | We initially received R2.0m and later receive an additional R1.0m from DWA |  | Completion - 100% | Achieved | 100% complete | 100% complete | Completed. | N/A | N/A | D. MLENZANA (N. TSHICILELA)
[6 empty] | Rapid Response Unit (Repair major Leak) - R3.0m | ADJ SDBIP | % of complete project |  | 100% complete | Out-sourced | N/A | N/A | N/A | N/A | N/A | N/A |  | Completion - 100% | Achieved | 100% complete | 100% complete | Completed. | N/A | N/A | D. MLENZANA (N. TSHICILELA)
[6 empty] | Ward 12 Water Supply Project - R4.7m | ADJ SDBIP | % of complete project |  | Completion - 100% | Out-sourced | N/A | N/A | N/A | N/A | N/A | N/A |  | Completion - 50% | Achieved | 75% complete | Completion - 100% | Under construction. 85% complete. | N/A | N/A | D. MLENZANA (N. TSHICILELA)
[6 empty] | Refurbishment of the 13 air valves and 3 scour valves | ADJ SDBIP | % of complete project |  | Completion - 100% | Out-sourced | N/A | N/A | N/A | N/A | N/A | Received funding from Dept. of Planning & Treasury |  | Refurbishment - 50% | Not Achieved | 100% complete | 100% complete | Under construction. 85% complete. | Delays in delivery of the material on site | Schedule has been revised and the services providr has been | D. MLENZANA (N. TSHICILELA)
[6 empty] | Upgrade and retrofit filters | ADJ SDBIP | % of complete project |  | Completion - 100% | Out-sourced | N/A | N/A | N/A | N/A | N/A | Received funding from Dept. of Planning & Treasury |  | Refurbishment - 50% | Not Achieved | 100% complete | 100% complete | Under construction. 80% complete. | Delays were experienced in the delivery of the material on-site. | Schedule has been revised and the services provider has been appointed | D. MLENZANA (N. TSHICILELA)
[6 empty] | Upgrade of thelamina plates clarifiers and installation of | ADJ SDBIP | [9 empty] | Received funding from Dept. of Planning & Treasury |  | Refurbishment - 50% |  | 100% complete |  | Under construction. 80% complete. |  |  | D. MLENZANA (N. TSHICILELA)
[6 empty] | Installation of bulk and zonal meters | ADJ SDBIP | % of complete project |  | Refurbishment - 50% | Out-sourced | [5 empty] | Received funding from Dept. of Planning & Treasury |  | Procurement | Achieved | 100% complete | Refurbishment - 50% | Meters already delivered, installation to be undertaken. | N/A | N/A | D. MLENZANA (N. TSHICILELA)
|  |  | MIG PROJECTS | 1880000 | MIG | Conversion of VIP's Waterborne sanitation at Lower Makana | ADJ SDBIP | % Complete the projects | 2800000 | 1x waterborne sanitation corverted | Out-sourced | 50% Partially complete | [5 empty] | 75% Partially complete | 100% Complete | Not Achieved |  | 100% Complete | 98% Complete | There was a funding shortfall. | Sourcing funding | Technical and Infrastructure
|  |  |  | 10000000 | MIG | Extesion 6 Sewer reticulation Phase 2 - Stage 2 | ADJ SDBIP | % Complete the projects | 6446379.55 | 1x Ext. 6 Sewer Ret. Complete. | Out-sourced | 50% Partially complete | [5 empty] | 75% Partially complete | 100% Complete | Not Achieved |  | 100% Complete | Constraction iis on-site | Slow performance of the contractor due to none payment of service provider. | Service provider has been payed. Schedule has been revised | Technical and Infrastructure
|  |  |  | 3860000 | MIG | Construction of Oxidation ponds | ADJ SDBIP | Construction of Oxidation ponds at Riebeeck East | 2361740.51 | 1x Oxidation Pond constructed | Out-sourced | 50% Partially complete | [5 empty] | 75% Partially complete | 100% Complete | Not Achieved |  | 100% Complete | Project was didnt start at all | Service where terminate due to nunsubmission of contractual requirements by the service provder.funds where redirected to there project | There shortfoll in fundin due to change cost eastmate. The municipality is sourcing funding | Technical and Infrastructure
|  |  |  | 200000 | Capital | Extesion 6 Sewer reticulation Phase 2 - Stage 3 | ADJ SDBIP | % of complete project | 6000000 | 1x Ext. 6 Sewer Ret. Complete. | Out-sourced | 10% (Procument) | [5 empty] | 50% Partially complete | 100% Complete | Not Achieved |  | 100% Complete | Contract in on site | Slow procurement processes. | Schedule has been revised and the services provider has been appointed. | Technical and Infrastructure
|  |  |  | 100000 | Capital | Construction of Extension 6 Toilet Structures | ADJ SDBIP | % of complete project | 7802265 | 400 toilet structure constructed | Out-sourced | 10% (Procument) | [5 empty] | 50% Partially complete | 100% Complete | Not Achieved |  | 50% Complete | The Contractor is on site. | Delay due to procurement processes | Schedule has been revised and the services provider has been appointed. | Technical and Infrastructure
|  |  |  | 80000 | Capital | Social services Projects | ADJ SDBIP | % of complete project | 3987715 | 1x Recreation Centre constructed | Out-sourced | 10% (Procument) | [5 empty] | 50% Partially complete | 100% Complete | Not Achieved |  | 100% | Project is not completed. | Funds where redirected to water intervension | To be implemented in 2014/15 FY | Technical and Infrastructure
|  | KFA 1.5 | Electricity and Energy | 2372000 | Capital | Installation of a new 22 KV poweline | ADJ SDBIP | Installation of a new 22 KV poweline from Eskom point to the edge of Thomas Baines Reserve |  | Procurement, Delivered & Fixed. | Out-sourced | [5 empty] | Received funding from Dept. of Planning & Treasury |  | Scope of Work | Not Achieved | 100% complete | Procurement, Delivered & Fixed. | The tender closed and the contractor has been appointed | Delays in the signing of wayleave | To be implemented in 2014/15 FY | M. RADU (X. BOKWE)
[6 empty] | Supply & Install new transformer 1x H'poort (15MVA) | ADJ SDBIP | Installation of a new 22 KV poweline from Eskom point to the edge of Thomas Baines Reserve |  | Procurement, Delivered & Fixed. | Out-sourced | [5 empty] | Received funding from Dept. of Planning & Treasury |  | Scope of Work | Not Achieved | 100% complete | Procurement, Delivered & Fixed. | The tender closed and the contractor has been appointed | Delays in the procument processes | To be implemented in 2014/15 FY. | M. RADU (X. BOKWE)
[6 empty] | Supply & Install new transformer 1x J. Kleinyhans (1.5MVA) | ADJ SDBIP |  |  | Procurement, Delivered & Fixed. | Out-sourced | [5 empty] | Received funding from Dept. of Planning & Treasury |  | Scope of Work | Not Achieved | 100% complete | Procurement, Delivered & Fixed. | Procurement process has commenced. | Delays high demand and lead time | N/A | M. RADU (X. BOKWE)
[6 empty] | Reconstruct powerline | ADJ SDBIP | Reconstruct of Waainek to H'poort powerline |  | Procurement, Delivered & Fixed. | Out-sourced | [5 empty] | Received funding from Dept. of Planning & Treasury |  | Scope of Work | Not Achieved | 100% complete | Procurement, Delivered & Fixed. | Consultant has been appointed and the Designs have been completed. The tender documents were forwarded to the implementing agents, Amatola Water. | Delays in the procument processes | To be implemented in 2014/15 FY | M. RADU (X. BOKWE)
[6 empty] | Cabling and protection | ADJ SDBIP | Cabling and protection H'poort |  | Procurement, Delivered & Fixed. | Out-sourced | [5 empty] | Received funding from Dept. of Planning & Treasury |  | Scope of Work | Not Achieved | 100% complete | Procurement, Delivered & Fixed. | Material for the panels and cables has been delivered on site. The actual work to begin on 19 June 2014. | Delays in the procument processes | To be implemented in 2014/15 FY | M. RADU (X. BOKWE)
[6 empty] | Substation refurbishment (Summit, Sugar loaf, G'town) | ADJ SDBIP |  |  | Procurement, Delivered & Fixed. | Out-sourced | [5 empty] | Received funding from Dept. of Planning & Treasury |  | Scope of Work | Not Achieved | 100% complete | Procurement, Delivered & Fixed. | Project was not implemented due fincai constrans | Funding was redirected | To be implemented in 2014/15 FY | M. RADU (X. BOKWE)
[6 empty] | Upgrade of the PLC and Panel | ADJ SDBIP | Upgrade of the PLC and Panel of the Howiesons Poort Pump station |  | Delivered & Installed | Out-sourced | [5 empty] | Received funding from Dept. of Planning & Treasury |  | Procurement | Not Achieved | 100% complete | Delivered & Installed | Material for the panels and cables were delivered on site. The actual work began on 19 June 2014. | Delays in the procument processes | To be implemented in 2014/15 FY | M. RADU (X. BOKWE)
[6 empty] | Repair of the damaged pump | ADJ SDBIP | Repair of the damaged pump at James Kleynhans Pumpstation |  | Repair of the damaged pump by the end of thrid quarter | Out-sourced | [5 empty] | Received funding from Dept. of Planning & Treasury |  | Repairing | Achived | 100% complete | N/A | The pump was repaired at Suzler Pumps and was expected to be delivered on 30 June 2014. |  |  | M. RADU (X. BOKWE)
[6 empty] | Repair of the blown motor | ADJ SDBIP | Repair of the blown motor at HowiesonsPoort Pumpstation |  | Repair of the damaged pump by the end of thrid quarter | Out-sourced | [5 empty] | Received funding from Dept. of Planning & Treasury |  | Repairing | Achieved | 100% complete | N/A | Motor installed and commissioned. | N/A | N/A | M. RADU (X. BOKWE)
[6 empty] | Purchase of the pumpset(motor) | ADJ SDBIP | Purchase of the pumpset for the HowiesonsPoort Pumpstation |  | Delivered & Installed | Out-sourced | [5 empty] | Received funding from Dept. of Planning & Treasury |  | Procurement | Achieved | 100% complete | Delivered & Installed | Order was issued in September 2013 | N/A | N/A | M. RADU (X. BOKWE)
[6 empty] | Purchase of one pump | ADJ SDBIP | Purchase of one pump for the James Kleynhans Pumpstation |  | Delivered & Installed | Out-sourced | [5 empty] | Received funding from Dept. of Planning & Treasury |  | Procurement | Achieved | 100% complete | Delivered & Installed | Order was issued in September 2013 | N/A | N/A | M. RADU (X. BOKWE)
| Ensure well structured quality housed across municipality | KFA 1.6 | Housing provision | External Funded | Human Settlement | Housing development, Mayfiled phase II | IDP 1.33 | 1000 Units Housing Constructed & 1000 sites serviced | No budget | 1 000 Houses constructed & 1 000 site services | Out-sourced | 50% Partially complete | [5 empty] | 75% Partially complete | 100% Complete | Achieved | 75% complete | N/A | Project completed | N/A | N/A | Technical and Infrastructure

## Basic Service CSS
Objective | Strategy | KFA No | Key Focus Area | Project/ Programme | Projects Register ID | Key Performance Indicator | Annual Target | Service Develivery Model | Status Achieved or Not Achieved | Actual Perfomance | Deviation N/A | Corrective Action
Community of Makana have access to adequate facilities also live in a safe, secure and healthy environment by 2017 | Ensure safety and health enviroment for all communities | KFA 2.2 | TRAFFIC SERVICES (Roadworthy/Signage) | Road safety and Community awareness programs | IDP 2.09 | Number of awareness programmes organised. | All awareness programmes in the Plan are to be implemented as per schedule. | In-house | Achieved | 200 pupils trained | N/A | N/A
|  |  |  | Public awareness | IDP 2.10 | No of learners participating in the scholar education program | 200 | in-hose | Achieved | 200 pupils trained | N/A | N/A
|  | KFA 2.3 | ENVIRONMENTAL MANAGEMENT | Community engagement on environmental awareness programme | IDP 2.12 | No of environmental education programs implemented Qauterly | 8 | In-house | Achieved | 8 awareness education programmes were done | N/A | N/A
|  |  |  | Implementation of environmental education & training strategy (Eco Schools ) | IDP 2.13 | No of environmental programs implemented in schools Quaterly | Target 10 School | In partnership with Rhodes University | Not Achieved | Only support 8 schools. | Due to financial constraints, the Municipality could only support 8 schools. | Programme will be continued in the Next Financial year
|  |  |  | Stakeholders paricpation on environmental activities | IDP 2.14 | No of Environmental forum meetings held annually. | 4 | In-house | Not Achieved | 3 meetings took place. | N/A | N/A
|  |  |  | Establishment of environmental co-operatives. | IDP 2.15 | No of Co-operatives identified and registered. | None. | In-house | Not Achieved | Business plan had been submitted to the Portfolio Committee. | N/A | N/A
|  | KFA 2.4 | Fire and Rescue Services | Community awareness campagns | IDP 2.18 | No campaigns undertaken | 4 campaigns annually | In-house | Achieved | 4 Campaigns were undertaken | N/A | N/A
|  |  |  | Fire inspections undertaken at commercial and industrial premises. | IDP 2.19 | No inspections undertaken | 200 | In-house | Achieved | 215 Fire Safety Inspections were carried out | N/A | N/A
| Promote culture of reading and learning | KFA 2.5 | LIBRARY SERVICES | Outreach programmes | IDP 2.22 | Number of outreach programmes conducted | Three events were to be hosted. | In-house | Achieved | 4 events were conducted. | N/A | N/A
|  |  |  | Increase number of new library patrons. | IDP 2.24 | Increase on the number of new patrons registered on an annual basis | 10% increase in the number of patrons registered | In-house | Achieved | 10% Achieved. | N/A | N/A
|  |  | PARKS AND RECREATION (Sport/play ground) | Clean up project | IDP 2.28 | Mowing of verges | Mowing of all identified areas | Outsourced | Achieved | Identified areas mowed. | N/A | N/A
|  | KFA 2.7 | Commonage | Biodiversity Conservation | IDP 2.30 | Blocks cleared of Alien Invasion Plantspecies. | Issue contracts to Albany Working for Water each quarter | Service Level Aagreement with Albany Working for Water | Achieved | Identified Alien Invasive Plants cleared. | N/A | N/A
| Ensure Community safety | KFA 2.9 | Disaster Management and Community Safety | Implementation Community Awareness programme | IDP 2.34 | No of Community programmes implemented | 12 awarenes proggrammes were to have been initiated. | In-house | Not Achieved | 4 awareness programs were implemented. | Target was not achieved due to staff shortage. Currently the staff is shared i.e fire fighters. | Plan will be revised in the next financial year

## Local Economic Development
Objectives | Strategy | KFA NO | Key Focus Areas | Projects Register ID | Project/Program | Key Performance Indicator | Annual Target | Service Delivery Model | Status Achieved or Not Achieved | Actual Perfomance | Deviation N/A | Corrective Action
Promote and support agricultural development to stimulate economic growth and development that will result in the creation of jobs | Promote and support co-op development and capacity building | KFA 3.1 | Makana Micro agriculture | IDP 3.01 | a) Co-operative development and capacity building(b) | No of emerging farmers capacitated | 30 Emerging farmers trained | Service Provider | Achieved | 24 people were trained on forms of ownership. 39 were trained on SARS requirements and 10 were trained on the co-operatives development. | N/A | N/A
| Co-funding government projects |  |  | IDP 3.03 | Co-fund projects with other government Depts. (e.g. establishment of poultry abattoir) | No of projects co-funded | 1 project | In-house | Achieved | Land and eletricity. | N/A | N/A
| Promote and support emerging farmers |  |  | IDP 3.06 | To unlock and to facilitate land at Thornpark | Steps taken to unlock land for Thornpark | 12 emerging farmers farming at Thornpark | In house | Not achieved | The applications were not processed. | The applications were not processed due to the shortage of documents from emerging farmers. | Project will prioritised in the next financal year
|  |  |  | IDP 3.07 | Conduct audit/assessment on Makana Municipality commonages | No of stock owners given land on commonages | 10 stock owners on three commonages | In house | Not achieved | The commonage plan is still to be formulated by Parks Department. | Commonage plan has not been develoed | Project will prioritised in the next financal year
|  |  |  | IDP 3.08 | To promote and support commodity’s in Makana Areas | No of commodities to benefit from municipal programmes | 3 commodity groups from Municipality receive support | Service Provider /In house | Not Achieved | Commodities were identified . Awaiting Cacadu District to implement. | Delay by the CDM | More pressure will put on CDM in the next financial year
|  |  |  | IDP 3.09 | Facilitate access to finance for emerging farmers | No of walk-ins assisted in seeking access to finance | 12 referrals made | In house | Achieved | Ongoing | N/A | N/A
|  |  | Support Agri-cultural Infrastructure development. | IDP 3.11 | Infrastructure development for emerging farmers (e.g. Fencing for Thornpark Farm/ tunnel provided) | Infrastructure provided to emerging farmers | 25 hectares fenced , 2 tunnels provided to emerging farmers, construction of 3 broiler units, construction of 2 pig units | Service provider | Achieved | The contractor has been appointed and the project implementation has commenced | N/A | N/A
| Promote agricultural development |  |  | IDP 3.12 | Memorandum of Understanding (MOU) with strategic partners to promote agriculture. | No of MOU signed | 1 MOU signed | In house | Not achieved | There is a Memorandum of Understanding(MOU) in place but the parties have not yet signed. | Delay in signing of MOU | Project will be prioritised in the next financal year.
Promote and support enterprise development to stimulate economic growth and development that will result in the creation of jobs | Support enterprise development | KFA 3.2 | SMME Development | IDP 3.13 | Capacitate women and youth through training proegrammes | Number of youth and women owned enteprises capacitated through training programmes | 4 trainings conducted | Service provider | Achieved | Training conducted. The target was achieved. | N/A | N/A
|  |  |  | IDP 3.14 | Assist Small Medium and Micro Enterprises(SMME) and Co-operatives(Co-ops) with advise, information and business registrations | (Number of referrals)SMMEs and Co-Ops assisted with advice and information and business registrations | Number of SMMEs and Co-operatives-Walk-ins, Refferals for finance and support | Inhouse | Achieved | 10 Smme's were assisted with advice and information | N/A | N/A
|  |  |  | IDP 3.15 | Capacitate SMME's and Co-ops through training proegrammes | Number of SMMEs and Co-ops beneficiaries assisted through capacity building workshops | 4 workshops conducted | In-house | Achieved | No workshops were conducted. The target was achieved | N/A | N/A
|  |  |  | IDP 3.16 | Support SMME's through the Business Services Partnership Fund | Number of SMMEs supported through the Business Services Partnership Fund | 10 SMMEs benefit from the Business Partnership Fund | Inhouse and External Funding | Not achieved | No SMME benefited from the programme due to the moratorium placed on projects | Funding was not available | Project will prioritised in the next financal year
|  |  |  | IDP 3.17 | Establish an SMME Hive/Information Centre | Establishment of an SMME Hive/Information Centre | SMME Hive/Information Centre Established | Co-funding | Achieved | Memorandum Of Agreement was signed with Seda and the Directorate was only awaiting Finance to pay the invoice. The request to process the invoice was re-submitted to finance. | N/A | N/A
|  |  |  | IDP 3.18 | SMME market access study | SMME market access study | SMME Access Study Developed | Service provider | Achieved | The project was not implemented due to the moratorium. | N/A | The project will be placed on hold.
| Promore and support the development of the informal sector |  |  | IDP 3.20 | Informal Sector Development | Number of Hawkers and Informal Traders Capacitated | 20 Hawkers and Informal Traders Capacitated | In-House | Achieved | No capacity building took place. The target was achieved. | N/A | N/A
|  |  |  | IDP 3.21 | Enhace the growth and development of informal economy | Number of structures for informal sector created | 7 Hawker Stalls Constructed | Service provider | Not achieved | The project was submitted to Bid Evaluation Committee in May 2014. | Due to financial constraints, the project was delayed. | A memorandum will be written to the Municipal Manager requesting that the project be prioritised.
| Ensure the creation of 1000 jobs for the unemployed |  |  | IDP 3.22 | Facilitate the implementation of CWP | No of jobs created | 900 jobs created | In-house | Achieved | The participation rate for June is 1017. A XWP reference committee meeting held on the 16 May 2014. | N/A | N/A
|  |  |  | IDP 3.25 | Conduct assessment of business confidence | Number of business confidence levels assessement done | 2 Annual business confidence levels assessement done | In-house/service provider | Achieved | The Survey was conducted in April/May and a report was developed. | N/A | N/A
|  |  |  | IDP 3.26 | Implement the last phase of the NDPG | % Expenditure of the cial gazetted amount for the 2013/14 financial year | 90 % Expenditure | Contractors | Achieved | 100% of NDPG funding has been spent | N/A | N/A
|  |  |  | IDP 3.27 | Inner City Regeneration | Business plan for inner city regenration | Business plan for inner city regenration available in order to raise funding for the project | In-house/service provider | Not achieved | The Buiness Plan has not been formulated | PROJECT WAS NOT Implemented due to a moratorium on spending on internally funded projects | The project has been rebudgeted for in the 2014/15 financial year
| Support the Kaolin Mining Initiatives in the Municipality |  |  | IDP 3.28 | Establish a ceramic studio | A ceramic studio is established | Ceramic Studio Established | In-house/service provider | Achieved | Funding secured form Sea for the kaolin incubator. | N/A | N/A
|  |  |  | IDP 3.29 | Source Funding /Partnership for Kaolin Incubation Facility | R value of funsding support received for incubation centre | Funding Secured | In-house | Achieved | Machinery and equipment has been purchased. Project Manager appointed the only outstanding issue is the lease of the building to Zenzele TDC. | N/A | N/A
|  |  |  | IDP 3.30 | Training for Kaolin Mining Co-operatives | No of Kaolin Mining Co-ops trained | Support Kaolin Training Initiatives | In-house | Achieved | Support secured from ECDC for the training and quotation were solicited from service providers. | N/A | N/A
|  |  |  | IDP 3.31 | Support the Mining Trust | Formal agreement, expenditure reports to the Trust, financial statements from the Trust | Support to Makana Mining Trust | In-house | Not achieved | MoU was developed. The project was put on held due to the morotorium. | PROJECT WAS NOT Implemented due to a moratorium on spending on internally funded projects | The project has been rebudgeted for in the 2014/15 financial year
|  |  |  | IDP 3.32 | Secreteriat for the Kaolin Project Steering Committee | Minutes of PSC Meetings | 4 Kaolin Mining PSC held | In-house | Achieved | A Kaolin PSC was held on 16 of June 14 | N/A | N/A
Promote and support tourism and heritage development to stimulate economic growth and development that will result in the creation of jobs | Promotion of arts and culture to create jobs | KFA 3.3 | TOURISM DEVELOPMENT | IDP 3.33 | Creative City Project | Number of quick - win initiatives implemented through the streams | Successful implementation of Creative City Project | Partnership with National Arts Festival and Cacadu District Municipality | Not Achieved | None. The implementation of kick win initiatieves has not happened due to the Municipality's cash flow crisis | Due to the cash flow situation , the municipality has failed to provide funds to kick start the project . | The project has be rebudgeted for in the 2014/15 financial year
|  |  |  | IDP 3.34 | Craft Sector Development Programme | Number of crafters trained, craft route map and a brochure | Training of 20 crafters, production of a craft route map and a brochure | Service provider | Achieved (the training component) | 25 crafters were trained in the 2nd quarter ,however the brochure and a route map have not been produced due to the cash flow crisis in the municipality. | The route map and a brochure have not been produced due to the moratorium on spending on internally funded projects. | The project has be rebudgeted for in the 2014/15 financial year
|  |  |  | IDP 3.35 | National Arts Festival marketing programme | Number of people visiting the MM stand at the NAF | Marketing the Municipality at the NAF | In house and service provider | Achieved | The municipality had a stand at the 2014 NAF and shared it with 2 crafters | N/A | N/A
| Create jobs for emerging tourist guides |  |  | IDP 3.36 | Tourism Internship Programme | Portfolio Committee reports | 6 unemployed tourism graduates absorbed for experiential learning | Partnership with the National Arts Festival and Makana Tourism | Achieved | In partnership with the Albany Museum 6 unemployed tourism graduates were employed in September 2013 for a 12 month internship programme | N/A | N/A
|  |  |  | IDP 3.37 | Partnership opportunities with the Game Reserves | Report on potential partnership with the Game Reserves | identification of partnership opportunities with the Game Reserves | Service Provider | Achived | The study was completed in March and a report was submtted to the TCI Portfolio Committee meeting held in May | N/A | N/A
| Support to emerging tourism SMME's |  |  | IDP 3.39 | Community based tourism support programme | Number of tourism SMMEs and Projects supported | 2 SMMEs, 2 Events and 1 heritage project supported | In house | Not Achieved | None | Applications for funding were received and evaluated.However funds could not be transferred to the beneficiaries due to the municipal cash flow crisis. | Funding to support communty based arts initiatives has been allocated in the 2014/15 budget
| Provide tourism infrastructure | KFA 3.4 | TOURISM INFRASTRUCTURE | IDP 3.40 | Tourism Infrastructure Development | 3 tourism signboards installed | Installation of 3 tourism signs boards at various points in Makana | Service provider | Achieved | The project was completed in the 3rd quarter | N/A | N/A

## Financial Viability & Mngt
Objective | Strategy | KFA | Key Focus Area | Project/ Programme | Project ID Register | Key Performance Indicator | Annual Target | Service Delivery Model | Milestones |  |  |  | Reponsible Directorate | Status | Actual Performance | Reasons for Variance | Corrective Action
[9 empty] | Quarter 1 | Quarter 2 | Quarter 3 Target | Quarter 4
Achieve clean administration 2015 | Improve Revenue Generation and Management. | KFA 4.8 | Income and Revenue | Improve Revenue Enhancement | IDP 4.13 | % increase in the income and revenue | 85% by the end of the financial year (Receipted amount/Billed amount) | In- house | No of correct Bills sent current 68% | 72% | 80% | 85% | Finanancial Directorate | Not Achieved | Revenue collected at present amounts to 74% of bills sent out. Meter reading system flags suspiciously high meter readings. These are followed up continuously and incorrect readings are corrected through taking check readings. Faulty meters are reported to Technical. | Economic hardships faced by residents. Unwillingness to pay by those that can afford to pay. Unacceptably high distribution losses. Underground/faulty meters identified. Insufficient capacity to implement Credit Control Policy. | Urge residents to pay for services through improved credit control efforts. Urge poor residents to apply for indigent subsidy. Capacitate Credit Control Section. Appoint proffessional debt collector. Replace faulty meters.
[6 empty] | % increase in quality of meter reading | 75% by the end of the financial year (Receipted amount/Billed amount) | In- house | Quality to increase to 75% | Quality to increase to 75% | Quality to increase to 75% | Quality to increase to 75% | Finanancial Directorate | Not Achieved | An average of 58% of meters have been read for this year. Consumption of remaining meters are averaged. | Meters are underground/faulty. Insufficient number of meter readers. Restricted access to meters | Replace faulty meters. Uplift underground meters. Appoint meter readers/perform workstudy to determine efficiency. Urge residents to provide regular meter readings/access to meters.
[6 empty] | % increase in the Income from Rates with quality valuations | 100% by the end of the financial year (Receipted amount/Billed amount) | In-house | 85% correctness of billing | 87% correctness of billing | 90% correctness of billing | 100% | Finanancial Directorate | Not Achieved | Revenue from Rates collected amounts to 73% at present. | Economic hardships faced by residents. Unwillingness to pay by those that can afford to pay. Insufficient capacity to implement Credit Control Policy. | Urge residents to pay through improved credit control efforts. Urge poor residents to apply for indigent subsidy. Capacitate Credit Control Section. Appoint professional Debt Collector.
[6 empty] | Existance of a debt to income ratio of 34% | 30% by the end of the financial year (Total receipted amount/Total billed amount) | In-house | 36% | 35% | 34% | 30% | Finanancial Directorate | Not Achieved | At present this ratio is 3% | Low revenue collection rate, coupled to the resulting increased arrear debt in excess of R200 million | Intensify debt collecting efforts through outsourcing. Capacitate Credit Control for efficient implementation of policy
[6 empty] | Nett Debtors to Annual Operating Income | 15% (Outstanding debt/Annual Debtors billing) | In-house | 15% | 15% | 15% | 15% | Finanancial Directorate | Not Achieved | 12% | Low revenue collection rate, coupled to the resulting increased arrear debt in excess of R200 million | Intensify debt collecting efforts through outsourcing. Capacitate Credit Control for efficient implementation of policy
| Improve Expenditure Management | KFA 4.9 | Expenditure Management | Improve operating and capital expenditurtere expenditure | IDP 4.14 | Creditors Payment ratio to reduce to within 30 days | 30 days by the end of the financial year. | In-house | 85% | 65% | 50% | 30% | Finanancial Directorate | Not Achieved | Varies between 30 days and 180 days +, depending on availability of cash | Inadequate cash flow | Revenue collection needs to be improved, and stricter control over expenses such as travelling, overtime, fuel and other luxuries
| Ensure effective budgeting management |  | Budgeting and Financial Accounting |  |  | % of expenditure spend | 80% | In-house | 80% | 80% | 80% | 80% | All Directorate | Not Achieved | Expenditure % of the YTD budget spent amounts to 74% at present | Inadequate cash flow. Strict implementation of SCM processes | Improve cash flow. Continuous education on SCM processes/requirements

## Development Priorities Budget
Development Priroities Budget Allocation
No | Priority | Directorate | Budget
1 | Institutitonal and Tranformation Development | Corporate Services | 29357824
2 | Good Governance and Public Particpation | Municipal Manager, Executive Mayor and Speaker Offices | 9725736.8
3 | Local Economic Development | LED Directorate | 33125900
4 | Financial Viability | Budget and Treasury Directorate | 32413258
5 | Basic Services Develivery | Community and Social Development | 35013492
6 | Basic Services Develivery | Technical and Infrastracture | 421278955

## Institutional Development
Objective | Strategy | KFA No | Key Focus Area | Projects Register ID | Project/ Programme | Key Perfomance Indicator | Annual Target | Service Delivery Model | Status Achieved or Not Achieved | Actual Perfomance | Deviation/N/A | Corrective Action
Achieve clean administration 2015 | Effective management of Human resources management and organisational development | KFA 4.2 | Human Resources | IDP 4.03 | Wellness programmes | No. of wellness program implemented Quarterly | All Identified wellness programmes are to be implemented | In-house | Achieved | Programmes on Health Risk Assessments, Counselling, Community Engagement, Follow-up Care and Support and Programme Strengthening were implemented. | N/A | N/A
|  |  |  | IDP 4.04 | Training development | Identification of training needs | Annual review of Workplace Skills Plan. | In-house | Achieved | Annual Work Place Skills Plan was developed | N/A | N/A
|  |  |  | IDP 4.05 | Effective management of Employment Equity Plan | Review of Employment Equity Plan | Approved by Council | In partnership with Cacadu District Municipality | Not achieved | Employment Equity Plan was not revised. | Due to lack of internal Capacity | This willl be actioned in July by the Corporate Services Managers. Budget has been allocated for it.
|  | KFA 4.3 | Organisational designed | IDP 4.07 | Implementation of Organisational Development exercise | Review Organogram and alignment of the restructured functions | New organogram to be approved by Council by the third quarter | Outsourced | Not achieved | Organizational structure has been reviewed but not approved by Council. | The organogram was referred to the Local Labour Forum for more consultation | Would be prioritised in the next financial year.
|  |  |  | IDP 4.08 | Review of the HR Policies | Revised outstanding HR policies | Revised all HR policies identified | In-house | Achieved | All policies approved by Council. | N/A | N/A
| Effective and efficient management fo legal and labour relations | KFA 4.4 | Legal and Labour relations | IDP 4.09 | Operationalisation of Legal and labour relations | Review and restructure legal and labour relations unit | New unit structure to be approved by Council as part of revised Micro structure by the third quarter. | In-house | Achieved | Organizational structure has been reviewed and adopted by Council. | N/A | N/A
[6 empty] | Development of institutional compliance register | Institutional compliance register to be approved by Council in the Third Quarter | In-house | Not achieved | Register was not developed | Lack of internal capacity | It will be done in the 2014 -2015 financial year .
[6 empty] | Review the roles and function of Local Labour Forum (LLF). | Capacity building session for all LLF stakeholders to be facilitated by September 2013 | In-house | Not achieved | Session was not done due to lack of internal capacity | Lack of internal capacity | SA Local Governing Bargaining Council has scheduled a workshop on LLF.
[6 empty] | Capacitate employees on disciplinary code | Disciplinary code awareness sessions to be organised in the in two phases in the first and second quarter. | In-house | Not achieved. | In process. Phase one was conducted . | Second session was not done due lack of funding | Second session would be prioritised in the next financial year.
| Development of a functional and effective Perfomance Management System | KFA 4.5 | Performance Management | IDP 4.10 | Cascading Perfomance Management System. | Implement individual Performance Management System(PMS) to Directors, Managers and the staff reporting to them. | PMS is cascaded up-to HOD level and managers | In-house and partnership with CDM | Not achieved | No Performance Agreements were signed for Section 56 & 57 employees for the year 2013/2014 and that impacted on the cascading PMS which was not achieved. | Suspension of former Municipal Manager affected the processes. | Performance Agreements for 2014/2015 will be signed before 31 July 2014.
| Improved Integrated Development Planning | KFA 4.6 | Intergrated Development Planning | IDP 4.11 | Review Integrated Development Plan | Review of the IDP Objective and Strategies | IDP of 2014-2015 to be approved by Council by 31 May 2014 | In-house | Achieved | Approved by Council on the 23 May 2014. | N/A | N/A
| Provide reliable information Communication Technology | KFA 4.7 | Information Communication Technology | IDP 4.12 | Development of Disaster recovery and business Continuity plan | Installation of Hardware back-up system | Installation of Back-up types in March 2014 | Outsourced | Achieved | Service Provider appointed and will start by end July 2014. | N/A | N/A
[6 empty] | Installation of software back-up system | Installation of unified Email online back-system by September 2013 | Outsourced | Achieved | Unified email in place. | N/A | N/A

## Good Governance
Objective | Strategy | KFA NO | Key Focus Area | Projects Register ID | Project/ Programme | Key Performance Indicator | Annual Target | Service Delivery Model | Milestones |  |  |  | Responsible Directorate | Status | Actual Performance | Reason for Deviation | Corrective Action
[9 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Promote proper governance and public participation | Ensure stabiclity and well function of the Council strucutures | KFA 5.1 | Council and Committee meetings | IDP 5.01 | Functioning of Council | No of Council meetings | 4 Ordinary Council meetings to have set. | In-house | 1 | 1 | 1 | 1 | Manager Administration | Not Achieved | Only three Ordinary Council meetings were convened. | To many Special Council meetings organised. | Speaker to ensure that the meeting seat according to schedule
[6 empty] | No of Portfolio Committee meetings. | 48 | In-house | 12 | 12 | 12 | 12 | Manager Administration | Not Achieved | Several Portfolio Committees meetings were postponed because they were not quorating. | Portfolio where not seating according to schedule more special Engineering and FAME | Speaker to ensure that the meeting seat according to schedule
[6 empty] | Number of Mayoral Committee sittings. | 8 | In-house | 2 | 2 | 2 | 2 | Manager Administration | Not Achieved | Only four Mayoral Committee meetings were convened in the last financial year. | Portfolio Committee meetings where not sitting according to meeting schedule especially Engineering and FAME Commmittees and that impacted on the process. | Mayor to ensure that the meeting sit according to meeting schedule.
|  |  |  | IDP 5.02 | Functioning of the Audit Committee | No of Audit Committee meetings | 4 | In-house | 1 | 1 | 1 | 1 | MM's Office | Not Achieved | Only three meetings were held due to the resignation of key Committee members. | Resignation of a member and Chairperson | Appointment of two additional members will be prioritised
| Effective support to Councillours wellfare | KFA 5.4 | Councillor Support | IDP 5.04 | Capacity building of Councillors | No of capacity building sessions to be attended | 12 | Outsourced | 3 | 3 | 3 | 3 | Corporate and Shared services | Not Achieved | Only four Councillors attended training due to lack of funds. | Lack funding | To be prioritised in the next financial year
| Effective mitigation of identified risks | KFA 5.5 | Risk Management | IDP 5.05 | Functioning of Risk Management unit | Co-ordinate Risk Management Committee meetings | 4 Risk Committee meetings | In-House | First meeting | Second meeting | Third meeting | Fourth meeting | MM office | Not Achieved | Only one meeting was held on 16 October 2013 | 1. Chief Risk Officer resigned. 2. Meetings were not convened as per schedule | Appointment of Chief Risk Officer will be prioritised in the 2014/15
[6 empty] | Review Risk Management Committee Charter | Approved Risk Management Committee Charter | In-House | Review and present to Risk Management Committee | N/A | N/A | N/A | MM office | Not Achieved | Only one meeting was held on the 16 October 2013 that made recommendations but the next seating to approve didn’t convene | 1. Chief Risk Officer resigned. 2. Meetings were not convened as per schedule | Appointment of Chief Risk Officer will be prioritised in the 2014/15 2. Convening of meetings will be prioritised
[6 empty] | Review Risk Management Policy | Approved Risk Management Policy | In-House | Submit Policy for approval by Council | Communication of the policy to officials and implementation | N/A | N/A | MM office | Not Achieved | Only one meeting was held on the 16 October 2013 that made recommendations but the next seating to approve didn’t convene | 1. Chief Risk Officer resigned. 2. Meetings were not convened as per schedule | Appointment of Chief Risk Officer will be prioritised in the 2014/15 2. Convening of meetings will be prioritised
|  |  |  | IDP 5.06 | Establishment of Fraud Management Framework | Review Fraud Prevention Policy and Strategy | Review Fraud Prevention Policy and Strategy on an annual basis | In-House | Approved Fraud Prevention Policy and Strategy | Communication of the policy to officials and implementation | N/A | N/A | MM office | Achieved | Reviewed and Approved by Council Meeting of 13 August 2013 | N/A | N/A
|  |  |  | IDP 5.07 | Review Risk Management Strategy | Review Risk Management Strategy (Risk Identification and Assessment Metholodogies, Risk Appetite and Tolerance) | Approved Risk Management Strategy | In-House | Submit Strategy for approval by Council | Communication of the policy to officials and implementation | N/A | N/A | MM office | Not Achieved | Only one Risk Committee meeting was held on 16 October 2013 that made recommendations but the next sitting to approve the matter did not quorate. | 1. Chief Risk Officer resigned. 2. Meetings were not convened as per schedule | Appointment of Chief Risk Officer will be prioritised in the 2014/15 2. Convening of meetings will be prioritised
|  |  |  | IDP 5.08 | Mitigating risk and fraud at all levels | Annual Strategic Risk Assessment | Submit the Annual Strategic Risk Assessments to Council. | In-House | Approved strategic risk register | Risk Follow up report | Risk Follow up report | Risk Follow up report | MM office | Achieved | Annual Strategic Risk Assessment conducted on the 26 May 2014 | N/A | N/A
| Effective Monitoring and reporting of SDBIP performance |  |  | IDP 5.10 | Monitoring of SDBIP | No of SDBIP Institutitonal Scorecard reports | 4 | In-House | 1 | 1 | 1 | 1 | Corporate and Shared Services | Achieved | All four reports where done | N/A | N/A
[6 empty] | No of Monthly SDBIP reports to Portfolio Committees and Mayoral Committee. | 48 | 12 | 12 | 12 | 12 | 12 | Corporate and Shared Services | Not Achieved | Some Departments did not submit their SDBIP Monthly report to their Portfolio Committees. | Directorates did not submit SDBIP Monthly report to portfolio committees regulary | More control would be execised on during next financial year
[6 empty] | Monitor the performance of service providers | No of target met inline with terms of reference | In-House | N/A | Mid- Performance Assessment | N/A | Annual Performance Report | Corporate and Shared Services | Achieved | Mid-Performance Assessment was tabled to Council and Annual Performance Report has been developed. | N/A | N/A
| Enhance public participation | KFA 4.7 | Public Participation | IDP 5.14 | Community particpation in Municipal planning | No of ward plans revised and developed | 14 Ward plans | In-House | Review and develop of Ward plans Phase 1(Rural Areas) | Review and develop of Ward plans Phase 2(Urban areas) | 14 Ward plans approved by Council | Establishment ment of Ward Descresional Grant | Corporate and shared services | Not Achieved | Delay in the implementation of COGTA project | N/A | N/A
| To improve management and administration of legal and labour relations matters | KFA 4.10 | Legal & labour relations | IDP 5.17 | Improve turn-around time in responding to litigations | 10% reduction of litigation agaist Municipality | 10% decrease in legal cost agaist municipality annualy | In-House | Respond to compliants within 2 weeks after it has been received | Respond to compliants within 2 weeks after it has been received | Respond to compliants within 2 weeks after it has been received | Respond to compliants within 2 weeks after it has been received | MM office | Not achieved | Municipality was not able to decrease legal cost. | Municipality over spent legal costs allocation | N/A
|  | KFA 4.11 | Inter-Governmental Relationships (IGR) | IDP 5.18 | Facilitating mainstreaming and promoting IGR programe | Review of IGR Strategy/Policy By Decemebr 2013 | Revised Policy to be approved by Council by December 2013 | In-House | Table of Revised Policy to mayoral Committee for adoption | Table of Revised Policy to Council for Approval | N/A | N/A | MM office | Not achieved | Policy was not revised | Process of restructuring in the MM's Office affected the implementation of the review. | To be prioritised in 2014-2014 financial year
|  | KFA 4.12 | International Relationships (IR) | IDP 5.19 | Facilitating mainstreaming and promoting IR programe | Review of IR Strategy/ Policy | Revised Policy to be approved by Council by December 2013 | In-House | Table of Revised Policy to mayoral Committee for adoption | Table of Revised Policy to Council for Approval | N/A | N/A | MM office | Not achieved | Policy was not revised | Process of restructuring in the MM's Office affected the implementationof the review. | To be prioritised in 2014-2014 financial year
Support rural communities and vulnerable groups | Empower and support vulnerable groups | KFA 6.1 | Special Programmes | IDP 6.01 | Rural development Strategy | Development of rural development strategy | Revised Policy to be approved by Council by December 2013 | Partership with Rural development department | Appoint service provider | Table of Draft strategy to Mayoral committtee for adoption | Table of strategy to Council for approval | Prioritised programs for IDP/Budget | MM office | Not achieved | Strategy was not developed | Process of restructuring in the MM's Office affected the implementation of the review. | To be prioritised in 2014-2014 financial year
|  |  |  | IDP 6.02 | Development and review of vulnarabel group support plans | Development of youth, People with diability, women and children and review HIV/ sector plan | All sector plans to be approved by Council in end of the Financial year. | In-House | Review status quo and progress made is report to Mayoral committee | Draft plans are table to Mayoral committee | Sector plas are approved by Coucil | Prioritised programs for IDP/Budget | MM office | Not achieved | Sector plans where not developed | Process of restructuring in the MM's Office affected the implementation of the process. | To be prioritised in 2014-2014 financial year

## FInancial Viability (hidden)
Objective | Strategy | Budget | Strategy | KFA | Key Focus Area | Project/Program | Projects Register ID | Key Perofmance Indicator | Annual Target | Service Develivery Model | Status Achieved or Not Achieved | Actual Perfomance | Deviation/N/A | Corrective Action | Milestones |  |  |  | Reponsible Directorate
[15 empty] | Quarter 1 | Quarter 2 | Quarter 3 Target | Quarter 4
Achieve clean administration 2015 | Improve revenue generation and management. |  | To ensure that sustainable and improved revenue collection and generation | KFA 4.8 | Income and Revenue | Improve Revenue Enhancement | IDP 4.13 | % increase in the income and revenue | 85% by the end of the financial year | In- house |  |  |  |  | No of correct Bills sent current 68% | 72% | 80% | 85% | Finanancial Directorate
[8 empty] | % increase in quality of meter reading | 75% by the end of the financial year | In- house |  |  |  |  | Quality to increase to 75% | Quality to increase to 75% | Quality to increase to 75% | Quality to increase to 75% | Finanancial Directorate
[8 empty] | % increase in the Income from Rates with quality valuations | 100% by the end of the financial year | In-house |  |  |  |  | 85% correctness of billing | 87% correctness of billing | 90% correctness of billing | 100% | Finanancial Directorate
[8 empty] | Existance of a debt to income ratio of 34% | 30% by the end of the financial year | In-house |  |  |  |  | 36% | 35% | 34% | 30% | Finanancial Directorate
[8 empty] | Nett Debtors to Annual Operating Income | 15% | In-house |  |  |  |  | 15% | 15% | 15% | 15% | Finanancial Directorate
| Improve expenditure Management |  | Improve expenditure management strategies and effective supply chain management | KFA 4.9 | Expenditure Management | Improve operating and capital expenditurtere expenditure | IDP 4.14 | Creditors Payment ratio to reduce to within 30 days | 30 days by the end of the financial | In-house |  |  |  |  | 85% | 65% | 50% | 30% | Finanancial Directorate
| Ensure effective budgeting management |  |  |  | Budgeting and Financial Accounting |  |  | To ensure that the development and implementation of an IDP, Balanced Budget, Financial control and reporting | [6 empty] | 100% | 100% | 100% | 100% | Finanancial Directorate
[8 empty] | % of expenditure spend | 80% | In-house |  |  |  |  | 80% | 80% | 80% | 80% | All Directorate
[5 empty] | Financial Support and Risk Management |  |  | To provide an efficient and effecetive cash management and risk management system. | [6 empty] | 80% | 100% | 80% | 90% | Finanancial Directorate
| Ensure proper supply chain management |  |  |  | Supply chain management | [13 empty] | Finanancial Directorate
|  |  | Improve asset management stategies | KFA 4.10 | Asset Management | Updatied Asset regester |  | % of new asset cuptured in the asset register and lease assets are capitalised with 90 day | 100% | In-house |  |  |  |  | 100% | 100% | 100% | 100% | Finanancial Directorate

## Good Govanance and PP (hidden)
Objective | Strategy | KFA NO | Key Focus Area | Projects Register ID | Project/Program | Key Performance Indicator | Annual Target | Service Develivery Model | Status Achieved or Not Achieved | Actual Perfomance | Deviation/N/A | Corrective Action | Milestones |  |  |  | Reponsible Directorate
[13 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Promote proper governance and public particpation | Ensure stabiclity and well function of the Council strucutures | KFA 5.1 | Counill Committee | IDP 5.01 | Functioning of Council | No of Council meetings | 4 Ordinary Council | In-house | Achieved |  |  |  | 1 | 1 | 1 | 1 | Coporate and shared services
[6 empty] | No of Portfolio Committee | 48 | In-house |  |  |  |  | 12 |  | 12 | 12 | Coporate and shared services
[6 empty] | No Mayoral Committee | 8 | In-house |  |  |  |  | 2 | 2 | 2 | 2 | Coporate and shared sefvices
|  |  |  | IDP 5.02 | Functioning of the Audit Committee | No of Audit Committee meetings | 4 | In-house | Achieved |  |  |  | 1 | 1 | 1 | 1 | MM office
|  |  |  | IDP 5.03 | Functioning internal Audit | No of Internal audit and other activies conducted in accordance with audit plan | 18 | In-house | Not | Only two investigation conducted | Lack funding |  | 4 | 5 | 7 | 2 | MM office
| Effective support to Councillours wellfare | KFA 5.4 | Councillour support | IDP 5.04 | Capacity buiding of Councliours | No of capacity building attended(3 per quaterly) | 12 | Outsourcesd |  | Not all 12 Training planned where conducted | Lack funding | Will priorotiese in the nexte fiancial year | 3 | 3 | 3 | 3 | Coporate and shared services
Offices for ward councillors (ward 7,12)
| Effective mitigation of identified risk | KFA 5.5 | Risk Management | IDP 5.05 | Functioning of Risk Management unit | Co-ordinate Risk Management Committee meetings | 4 Risk Committee meetings | In-House |  | Only two whre conducted | Lack of comiittment | Will priorotiese in the nexte fiancial year | First meeting | Second meeting | Third meeting | Fourth meeting | Financial services
[6 empty] | Review Risk Management Committee Charter | Approved Risk Management Committee Charter | In-House |  |  |  |  | Review and present to Risk Management Committee | N/A | N/A | N/A | Financial services
[6 empty] | Review Risk Management Policy | Approved Risk Management Policy | In-House |  |  |  |  | Submit Policy for approval by Council | Communication of the policy to officials and implementation | N/A | N/A | Financial services
|  |  |  | IDP 5.06 | Establishment of fraud management framework | Review Fraud Prevention Policy and Strategy | Review Fraud Prevention Policy and Strategy on an annual basis | In-House |  |  |  |  | Approved Fraud Prevention Policy and Strategy | Communication of the policy to officials and implementation | N/A | N/A | Financial services
|  |  |  | IDP 5.07 | Review Risk Management Strategy | Review Risk Management Strategy (Risk Identification and Assessment Metholodogies, Risk Appetite and Tolerance) | Approved Risk Management Strategy | In-House |  |  |  |  | Submit Strategy for approval by Council | Communication of the policy to officials and implementation | N/A | N/A | Financial services
|  |  |  | IDP 5.08 | Mitigating risk and fraud at all levels | Annual Strategic Risk Assessment | Submit the annual strategic risk report counil | In-House |  |  |  |  | Approved strategic risk register | Risk Follow up report | Risk Follow up report | Risk Follow up report | Financial services
|  | KFA 5.6 | Monitoring and Evaluation | IDP 5.09 | Development of Monitorng and Evaluation policy framework | Development of Monitoring and Evaluation Policy Framework by the end December 2013. | Council Approves the Monitoting and Evaluation Policy is Approved by Council | In-House |  |  |  |  | Draft Monitoring and Evalution Policy Framework is table by Mayoral Committee for adoption | Monitoring and Evalution Policy Framework is table to Council for Approval | N/A | N/A | Coporate and shared services
| Effective Monitoring and reporting of SDBIP performance |  |  | IDP 5.10 | Monitoring of SDBIP | No of SDBIP Institutitonal Scorecard reports | 4 | In-House |  |  |  |  | 1 | 1 | 1 | 1 | Coporate and shared services
[6 empty] | No of target met per KPA | 80% | In-House |  |  |  |  | 80% | 80% | 80% | 80% | Coporate and shared services
[6 empty] | No of Monthly SDBIP report to Portfolio Committees and Mayoral Committee. | 48 | 12 |  |  |  |  | 12 | 12 | 12 | 12 | Coporate and shared services
[6 empty] | Monitor the performance of service providers | No of target met inline with terms of reference | In-House |  |  |  |  | N/A | Mid- Performance Assessment | N/A | Annual Performance Report | Coporate and shared services
|  |  |  | IDP 5.11 | Opion expressed by the AG | No of issue addressed in the Audit action plan are reported to Council | 4 Report to Council | In-House |  |  |  |  | 1 report | 1 report | 1 report | 1 report | Financial services
| Enhance public participation | KFA 4.7 | Public Participation | IDP 5.12 | Review of Public Participation Policy Framework | Development of Public particpation Policy Framework by the end financial year. | Public Participation policy Framework is Approved by Council | In-House |  |  |  |  | Draft Public Participation Policy Framework is table to Mayoral Committee for adoption | Draft Public Participation Policy Framework is table to Council for Approval | N/A | N/A | Coporate and shared services
|  |  |  | IDP 5.13 | Review and promote public particpation structures | Re-new of stakeholder forums | Stakeholders register is approved by Council by December 2013 | Update stakehoders register |  |  |  |  | Stakeholder register is approved by Council | N/A | N/A | N/A | Coporate and shared services
|  |  |  | IDP 5.14 | Community particpation in Municipal planning | No of ward plans revised and developed | 14 Ward plans | In-House |  |  |  |  | Review and develop of Ward plans Phase 1(Rural Areas) | Review and develop of Ward plans Phase 2(Urban areas) | 14 Ward plans approved by Council | Establishment ment of Ward Descresional Grant | Coporate and shared services
| To enhabce service delivery through effectives enforcement of by-laws and policies | KFA 4.8 | By-laws and Policies | IDP 5.15 | Review, develop and enforcing | No of by-laws and policies to revised, develop or enforcing | All policie and by-laws identified are approved by Councl at end of fincancial year | In-House |  |  |  |  | Action plan is table to FAME divided into three phases | Phase 1 | Phase 2 | Phase 3 | All Directorate
[5 empty] | Strengthened Monitoring and Evalaution System | Development of Monitoring and Evaluation Policy Framework | Monitoring and Evalaution Policy Framework is Approved by Council | [5 empty] | Draft Monitoring and Evalution Policy Framework is approved by Mayoral Committee | Monitoring and Evalution Policy Framework is approved by Mayoral Committee | N/A | N/A | MM office
| Improve communication internal and external | KFA 4.9 | Communcation Public relations & marketing | IDP 5.16 | Quaterly news letter | Quatelry news letter is produced a month after end of each quarter | 100% expenditure | In-House |  |  |  |  | First Quaterly news letter | Second Quaterly news letter | Third Quaterly news letter | Fourth Quaterly news letter | MM office
[5 empty] | Streamline public Participation activities | Review role and responsiblities of Public Participation and Establishsmen of ward public participation platforms | Public Participation forums are established in all wards. | In-House |  |  |  |  | Public Participation Policy workshop. And consultation on the establishment of Public Participation and Community Development Forums | Establishement of Public Participation and Development Forum and Ward Plans |  | N/A | MM office
|  |  | Customer care |  | Improve complaints management | Development of customer care management system | % completing of project | In-House
| To improve management and administration of legal and labour relations matters | KFA 4.10 | Legal & labour relations | IDP 5.17 | Improve turn-around time in responding to litigations | 10% reduction of litigation agaist Municipality | 10% decrease in legal cost agaist municipality annualy | In-House |  |  |  |  | Respond to compliants within 2 weeks after it has been received | Respond to compliants within 2 weeks after it has been received | Respond to compliants within 2 weeks after it has been received | Respond to compliants within 2 weeks after it has been received | MM office
|  | KFA 4.11 | Inter Governmental Relationships(IGR) | IDP 5.18 | Facilitating mainstreaming and promoting IGR programe | Review of IGR Strategy/Policy By Decemebr 2013 | Revised Policy is approved by Council in december 2013 | In-House |  |  |  |  | Table of Revised Policy to mayoral Committee for adoption | Table of Revised Policy to Council for Approval | N/A | N/A | MM office
|  | KFA 4.12 | International Relationships(IR) | IDP 5.19 | Facilitating mainstreaming and promoting IR programe | Review of IR Strategy/ Policy | Revised Policy is Approved by Council in december 2013 | In-House |  |  |  |  | Table of Revised Policy to mayoral Committee for adoption | Table of Revised Policy to Council for Approval | N/A | N/A | MM office
Support rural communities and vulnarabel groups | Empower and support vulnarable groups | KFA 6.1 | Special Programs | IDP 6.01 | Rural development Strategy | Development of rural development strategy | Council Approved by December 2013 | Partership with Rural development department |  |  |  |  | Appoint service provider | Table of Draft strategy to Mayoral committtee for adoption | Table of strategy to Council for approval | Prioritised programs for IDP/Budget | MM office
|  |  |  | IDP 6.02 | Development and review of vulnarabel group support plans | Development of youth, People with diability, women and children and review HIV/ sector plan | All sector plans are approved by Council in end of the Financial year. | In-House |  |  |  |  | Review status quo and progress made is report to Mayoral committee | Draft plans are table to Mayoral committee | Sector plas are approved by Coucil | Prioritised programs for IDP/Budget | MM office
[5 empty] | Women and Children | Mainstreaming gender policy guideline | Customisation of National guidelines

## Communiity and Social Services (hidden)
Objective | Strategy | KFA No | Key Focus Area | Project/Program | Projects Register ID | Key Performance Indicator |  | Annual Target | Service Develivery Model | Status Achieved or Not Achieved | Actual Perfomance | Deviation N/A | Corrective Action | Milestones |  |  |  | Reponsible Directorate
[7 empty] | Baseline | [6 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Community of Makana have access to adequate facilities also live in a safe, secure and healthy environment by 2017 | Ensure safety and health enviroment for all communities | KFA 2.1 | Enviromental health and Cleansing(Rufuse removal and dumping sites) | Ward clean-up campaign and community awareness programs | IDP 2.01 | Clean all 14 wards | Clean up projects is done on continues basis | 14 wards | Partnership with community |  |  |  |  | 5 Ward | 5 Ward | 5 Ward | 5 Ward | Community and Social services
|  |  |  | Erect of rumps and fencing at identified dumping spots | IDP 2.03 | Erecation of rumps and fencing | 52 Identified Dumping spots | Building five rumps | In-house |  |  |  |  | Planing and identificatin of 5 duping spots | Construction of rumps | N/A | N/A | Community and Social services
|  |  |  | Replacing of fleet equipment | IDP 2.04 | Purchasing of 1 x Tractor for Alicedale |  | % Complete of the project | Outsources |  |  |  |  | Draw up specification and approved Bid Committee | Puchasing of Tractor(oder is issued ) | Tractor is delivered | N/A | Community and Social services
[6 empty] | Purchasing of 1 x Roll on Container |  | % Complete of the project | Outsources |  |  |  |  | Draw up specification and approved Bid Committee | Puchasing of Roll on Container (Oderis issued ) | Roll on Container is delivered | N/A | Community and Social services
[6 empty] | Purchasing of 1 x 8 Ton Tipper Truck |  | % Complete of the project | Outsources |  |  |  |  | Draw up specification and approved Bid Committee | Purchasing of Ton Tipper Truck ( Oder is issued) | Ton tipper Truck is delivered | N/A | Community and Social services
|  | KFA 2.2 | TRAFFIC SERVICES(Drivers licensing and law enforcement) | Expanding services | IDP 2.06 | % Complete theproject | Current drive test yard in need extension | Extension of drive testing yard by June 2014 | Service provider |  |  |  |  | 90% complete | 100% Complete | N/A | N/A | Community and Social services
|  |  |  | Upgrading of offices | IDP 2.07 | implementation Action plan |  |  | 10%(Procument Phase) |  |  |  |  | 50% Contruction Phase0 | 100 Complete | N/A | N/A | Community and Social services
|  |  |  | Replacement of fleet | IDP 2.08 | Purchasing of 2 X vehicles |  | 2 X sed vehicle are bought in 2013-2014 financial year. | Outsources |  |  |  |  | Draw up specification and approved Bid Committee | Purchasing of 2X sed vehicle ( Oder is issued) | 2 X sed vehicle is delivered | N/A | Community and Social services
|  |  | TRAFFIC SERVICES(Roadworthy/Signage) | Road safety and Community awareness programs | IDP 2.09 | No of awareness programs organised | Continuously | All awareness programs in the plan are implemented as per schedule. | In-house |  |  |  |  | Plan ispresented to portfolionCommittee and Quarterly Report on the number of Community awareness programs implemented | Quarterly Report on the number of Community awareness programs implemented | Quarterly Report on the number of Community awareness programs implemented | Quarterly Report on the number of Community awareness programs implemented | Community and Social services
|  |  |  | Public awarenss | IDP 2.10 | No of leaners participating in the schoolar education program |  | 200 | in-hose |  |  |  |  | 50 | 50 | 50 | 50 | Community and Social services
|  | KFA 2.3 | ENVIRONMENTAL MANAGEMENT | Community engagement on environmenta awarness program | IDP 2.12 | No of environmental education programs implemented Qauterly |  | 8 | In-house |  |  |  |  | Quately report on the No of community engag 2 ment facillitated are submitted to Portfolio committee | Quately report on the No of 2 community engagment facillitated are submitted to Portfolio committee | Quately report on the No of 2 community engagment facillitated are submitted to Portfolio committee | Quately report on the No of 32community engagment facillitated are submitted to Portfolio committee | Community and Social services
|  |  |  | Implementation of environmental education & training strategy (Eco Schools ) | IDP 2.13 | No of environmental programs implemented in schools Quaterly |  | Target 10 School | In partnership with Rhodes University |  |  |  |  | Quaterly report are submitted to Portfolio committtee | Quaterly report are submitted to Portfolio committtee | Quaterly report are submitted to Portfolio committtee | Quaterly report are submitted to Portfolio committtee | Community and Social services
|  |  |  | Stakehoders paricpation on environmental activities | IDP 2.14 | No of Environmental forum held Annual |  | 4 | In-house |  |  |  |  | 1 | 1 | 1 | 1 | Community and Social services
|  |  |  | Establishement of environmental co-op | IDP 2.15 | No of Co-op identified and registered |  | Register environmental co-op to relevent | In-house |  |  |  |  | Identified & establish register for co-op | Organise training | Develop of Business Plans | Register with relavent outhorities | Community and Social services
|  | KFA 2.4 | Fire and Rescue Services | Upgrading of Fire stations | IDP 2.17 | Upgrading of Fires station is complete by the fourth qaurter of 2013-2014 finacial year. | Continuously | All 5 items are purchased by the second quarter | [5 empty] | Draw-up specification and are approved by Bid Committee. | Issue order and start construction | Complete projects |  | Community and Social services
|  |  |  | Community awareness campagns | IDP 2.18 | No camagns undertaken |  | 4 Annaly | In-house |  |  |  |  | 1 | 1 | 1 | 1 | Community and Social services
|  |  |  | Fire inspection at commescial and industrial premises | IDP 2.19 | No inspection undertaken |  | 200 | In-house |  |  |  |  | 50 | 50 | 50 | 50 | Community and Social services
|  |  |  | Upgrading of offices | IDP 2.20 | % Completing the project |  | 100% complete | Outsources |  |  |  |  | 10%(Procument Phase) | 50% Contruction Phase | 100% Complete | N/A | Community and Social services
| Promote culture of reading and learning | KFA 2.5 | LIBRARY SERVICES | Outridge programs | IDP 2.22 | No of outreach programs conducted | Continuously | Three event are hosted | In-house |  |  |  |  | Hosting of Illiteracy day | N/A | Hosting Library week | Hosting World book day | Community and Social services
|  |  |  | Upgrading and renovation libraries | IDP 2.23 | No of equipment and libraries upgraded | Check priroitiesation | 100% Expenditure | Outsources |  |  |  |  | Draw up specification | Evaultion and isuiing oders are issued) | 50% Equipment is delivery and office are upgraded | 50% Equipment is delivery and office are upgraded | Community and Social services
|  |  |  | Inrease new librayr patrons | IDP 2.24 | Increase on the number of new patrons regiterd on year to year basis |  | 10% increase in the number of patrons registered | In-house |  |  |  |  | 10 % Increase | 10% | 10% | 10% | Community and Social services
| Improve the access and quality of community recreational facilities | KFA 2.6 | PARKS AND RECREATION(Sport/play ground) | Upgrading and maintenance of sport fields and play grounds | IDP 2.25 | Upgrading of play ground and sport fields | Continuously | Construction /Re-instate play grounds at Kwanonzwakazi | Outsourced |  |  |  |  | 1x play gound are constructed/re-instated | Prepare specification and advertise for Tender | 100% Complete | N/A | Community and Social services
|  |  |  | Renovations at Ablutions Dlepu Stadium | IDP 2.26 | Renovate Ablutions in Dlepu stadium |  | Renovate Ablutions Dlepu Stadium in | Outsourced |  |  |  |  | N/A | Prepare specification and advertise for tender | 100% Complete | N/A | Community and Social services
Community and Social services
[6 empty] | Renovate Pavillion Dlepu Stadium |  | % Complete of the project | Outsourced |  |  |  |  | N/A | Prepare specification and advertise for Quataions | 50% Complete | 100% Complete | Community and Social services
|  |  |  | Convert Tennis Court In Curries Street | IDP 2.27 | Upgrading of Tennis Court |  | % Complete of the project | Outsourced |  |  |  |  | N/A | Prepare specification and advertise for Quatations | 50% Complete | 100% Complete | Community and Social services
|  |  |  | Clean up project | IDP 2.28 | Mowing of verges |  | Mowing of all identified areas | Oussourced |  |  |  |  | N/A | N/A | 50% Complete | 100% Complete | Community and Social services
|  | KFA 2.7 | Commonage | Biodiversity Conservation | IDP 2.30 | Blocks cleared of AIP's | On going issue of contract as per SLA | Issue contracts to Albany Working for Water each quarter | SLA with Albany Working for Water |  |  |  |  | SLA with Albany Working for Water | Issue contracts to AWFW | Issue contracts to AWFW | Issue contracts to AWFW | Community and Social services
|  | KFA 2.8 | Cemetery | New cemetery Infrastructure in Kwanonzwakazi | IDP 2.31 | Construction of cemetery at Kwanonzwakazi | New cemetery is needed | Construction of new cemetery at kwanonzwakazi | Service provider |  |  |  |  | Appiontment consultant | Feasibility study is cunducted | Report to Council on Recommnedations | N/A | Community and Social services
|  |  |  | Extension of Mayfield's Boundary Fence and construction of gravel roads | IDP 2.32 | Fencing and developing of gravel road of Mayfield Cemetery | Cemetery need extension to increase capacity | Extension of Mayfield's Boundary Fence and construction of gravel roads | In-house |  |  |  |  | Appiontment service provider | 50% Complete | 100% Complete the project | N/A | Community and Social services
| Ensure Community safety | KFA 2.9 | Disaster Management and Communty Safety | Implementation Community Awarrness program | IDP 2.34 | No of Community program implemented |  | 12 | In-house |  |  |  |  | 3 | 3 | 3 | 3

## National Indicators (hidden)
NATIONAL INDICATORS FOR MUNICIPAL PERFORMANCE INFORMATION
Development Strategy | Key Performance Indicator | Milestones |  |  |  | Annual Target | Project Register ID | Projects/ Programs | Performance Area | Budget | Source of Funding | GFS
|  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Local Government: Municipal Planning and Performance Management Regulations, 2001
Overall performance of local government | % of households with access to basic level of water |  |  |  |  | 95% households have access to a basic level of water |  | MSA sections 26(i) and 41(1)(b); Municipal Planning and Performance Regulation 12; National Outcome 9: Output 2- Improving access to basic services | Service Delivery
| % of households with access to basic level of sanitation |  |  |  |  | 82% of households have access to a basic level of sanitation | [6 empty] | N
| % of households with access to basic level of electricity |  |  |  |  | 90% of households have access to a basic level of electricity
| % of households with access to basic level of solid waste removal |  |  |  |  | 75%
| % of households earning less than R1 100 per month with access to free basic services | [6 empty] | MSA sections 26(i) and 41(1)(b); Municipal Planning and Performance Regulation 12
| % of a municipality’s capital budget actually spent on capital projects identified for a particular financial year in terms of the municipality’s Integrated Development Plan; | [7 empty] | Finances & Management
| Number of jobs created through municipality’s local economic development initiatives including capital projects; | [7 empty] | LED with Finances & Management
| Number of people from employment equity target groups employed in the senior level of management in compliance with a municipality’s approved employment equity plan |  |  |  |  | 6 Senior Managers employed according to employment equity targets |  |  | Institutional Transformation & Organisational Development
| % of a municipality’s budget actually spent on implementing its workplace skills plan | 25% of workplace skills plan in line with budget | 50% of workplace skills plan in line with budget | 75% of workplace skills plan in line with budget | 100% of workplace skills plan in line with budget | Workplace skills plan in line with municipal budget |  |  | Finances & Management with Institutional Transformation & Organisational Development
Outcome 8: Sustainable Human Settlements and An Improved Quality of Household Life, 2010
Provision, improvement, and facilitation of accommodation units and land for settlement purposes | Number of units of accommodation upgraded within informal settlements | No units will be upgraded during this period | No units will be upgraded during this period | An application to Provincial Housing Dept. submitted | Applications submitted by beneficiaries |  |  | Output 1- Upgrading units of accommodation within informal settlements | Service Delivery
| Number of accommodation units within the gap market for people earning between R3 500 and R12 800 | [6 empty] | Output 3- Facilitate the provision of accommodation units within the gap market for people earning between R3 500 and R12 800
| Number of Hectares of public land available for low and medium income housing to support 60 units per ha. | [6 empty] | Output 4- Mobilisation of well located public land for low income and affordable housing with increased densities on this land and in general
Outcome 9: Responsive, Accountable, Effective and Efficient Local Government System, 2010
Deepen democracy through a refined Ward Committee model | [7 empty] | Output 5- Deepen democracy through a refined Ward Committee model | Public Participation & Good Governance with Finances and Management
Avg. Amount of funding per ward committee
| % of Ward Committees that are fully functional | Support to Ward committees | Support to Ward committees | Support to Ward committees | 100% of ward committees functional | 100% ward committees are fully functional
Administrative and financial capability | Avg. Monthly collection rate on billings | 82% | 86% | 90% | 95% | 95% Avg. Collection rate of billings |  | Output 6- Administrative and financial capability | Finances and Management
% of municipal revenue with debtors
| % of municipal spending on opex | 25% of budget to date | 50% of budget to date | 75% of budget to date | 100% of budget to date | 100% of municipal OPEX budget spent
| % of municipal spending on capex | 20% of budget to date | 45% of budget to date | 70% of budget to date | 95% of budget to date | 95% of municipal CAPEX budget spent
| % of municipal spending of opex on repairs | Comprehensive infrastructure maintenance plan finalized | 33% | 33% | 33% | 100%

## LED (hidden)
Objectives | Strategy | VOTE | KFA NO | Key Focus Areas | BUDGET | Sources | Projects Register ID | Project/Program | Key Performance Indicator | Annual Target | Service Delivery Model | Status Achieved or Not Achieved | Actual Perfomance | Deviation N/A | Corrective Action | Milestones |  |  |  | Responsible Directorate
[16 empty] | Annual Target | Quarter 2 | Quarter 3 | Quarter 4
Promote and support agricultural development to stimulate economic growth and development that will result in the creation of jobs | Promote and support co-op development and capacity building | 10/01/75/6915034 | KFA 3.1 | Makana Micro agriculture | R20 000 000 | Operational | IDP 3.01 | a) Co-operative development and capacity building(b) | No of emerging farmers capacitated | 30 Emerging farmers trained | Service Provider |  |  |  |  | Develop TORs for service providers | Appointment of Service providers | Training of 20 emerging farmers | Project completion | LED Directorate
[5 empty] | 120000 | Operational | IDP 3.02 | Promote and support co-operatives through seed funding (Provide seed funding through competitions) | No of co-operatives that benefited from Municipal programmes | 7 co-ops benefited | In house |  |  |  |  | Develop criteria for competition | Identify co-ops | Provide seed funding for agricultural co-ops | Project closure | LED Directorate
| Co-funding government projects |  |  |  | 100000 |  | IDP 3.03 | Co-fund projects funded by other government Depts. (e.g. poultry abattoir) | No of projects co-funded | 1 project | In-house |  |  |  |  | identify stakeholder/ strategic partners | Develop TORs for service providers | appointment of service provide | Project completion | LED Directorate
| Promote urban agriculture |  |  |  | 130000 | Operational | IDP 3.04 | Promote green economy through sustainable Urban Agriculture (SUA) both in urban an rural areas (2 wards in urban and 2 in the rural area. | No of Community gardens established and supported | 2 Community gardens established in Urban areas and 2 in rural areas | Service Provider/ In house |  |  |  |  | identify community gardens | Appoint a Service provider | Service provider on site | Implementation & Finalise the project | LED Directorate
| Promote the involvement of youth in agriculture |  |  |  | 140000 | Operational | IDP 3.05 | Promotion of women and Youth in Agriculture.( Nursery establishment ) | No of youth and women in rural areas that have benefit from the establishment of nursery | At least 1 group (with women and youth) benefiting | service provider /In house |  |  |  |  | Develop TORs for service providers | appoint a service provide | service provider on site | Project closure | LED Directorate
| Promote and support emerging farmers |  |  |  |  | Operational | IDP 3.06 | To unlock and to facilitate land at Thornpark | Steps taken to unlock land for Thornpark | 12 emerging farmers farming at Thornpark | In house |  |  |  |  | Draw up a locality plan | Draw up application form of emerging farmers (criteria) | Lease agreements and Commonage Management Plan in place | emerging farmers at Thornpark | LED Directorate
[7 empty] | IDP 3.07 | Conduct audit/assessment on Makana Municipality commonages | No of stock owners given land on commonages | 10 stock owners on three commonages | [5 empty] | identify stock owners that owner livestock | identify commonages | Lease agreements and Commonage Management Plan in place | stock owners on the commonages
[5 empty] | 120000 | Operational | IDP 3.08 | To promote and support commodity’s in Makana Areas | No of commodities to benefit from municipal programmes | 3 commodity groups from Municipality receive support | Service Provider /In house |  |  |  |  | identify stakeholder/ strategic partners | Lease agreements and Commonage Management Plan in place | Apply for a mentorship programme at CACADU District Municipality | Mentor on site | LED Directorate
[6 empty] | Operational | IDP 3.09 | Facilitate access to finance for emerging farmers | No of walk-ins assisted in seeking access to finance | 12 referrals made | In house |  |  |  |  | Walk-ins referred to financial institutions (on-going) | Walk-ins referred to financial institutions (on-going) | Walk-ins referred to financial institutions (on-going) | Walk-ins referred to financial institutions (on-going) | LED Directorate
|  |  |  | Support agricultural Infrastructure development | 800000 | Capital | IDP 3.11 | Infrastructure development for emerging farmers (e.g. Fencing for Thornpark Farm/ tunnel provided) | Infrastructure provided to emerging farmers | 25 hectares fenced , 2 tunnels provided to emerging farmers, construction of 3 broiler units, construction of 2 pig units | Service provider |  |  |  |  | Identify stakeholders/ strategic partners | Service Provider/ Contractor appointed | Contractor on the site | Project implementation & closure | LED Directorate
| Promote agricultural development |  |  |  | 300000 | Operational | IDP 3.12 | MOU with strategic partners to promote agriculture | No of MOU signed | 1 MOU signed | In house |  |  |  |  | Identify strategic partner | Compile MOU | MOU signed | closure project | LED Directorate
Promote and support enterprise development to stimulate economic growth and development that will result in the creation of jobs | Support enterprise development | 10/01/75/6915050 | KFA 3.2 | SMME Development | 300000 | External (Seda) | IDP 3.13 | Capacitate women and youth through training proegrammes | Number of youth and women owned enteprises capacitated through training programmes | 4 trainings conducted | Service provider |  |  |  |  | Develop a training intervention programme | 2 Training conducted | 1 Training conducted | 1 Training conducted | LED Directorate
[7 empty] | IDP 3.14 | Assist SMME's and Co-ops with advise, information and business registrations | (Number of referrals)SMMEs and Co-Ops assisted with advice and information and business registrations | Number of SMMEs and Co-operatives-Walk-ins, Refferals for finance and support | Inhouse |  |  |  |  | Number of SMMEs and Co-operatives-Walk-ins, Refferals for finance and support | Number of SMMEs and Co-operatives-Walk-ins, Refferals for finance and support | Number of SMMEs and Co-operatives-Walk-ins, Refferals for finance and support | Number of SMMEs and Co-operatives-Walk-ins, Refferals for finance and support | LED Directorate
[7 empty] | IDP 3.15 | Capacitate SMME's and Co-ops through training proegrammes | Number of SMMEs and Co-ops beneficiaries assisted through capacity building workshops | 4 workshops conducted | In-house |  |  |  |  | Needs Assessment completed and 1 Workshop Done | 1 Workshop Done | 1 Workshop Done | 1 Workshop Done
|  | 10/01/75/6915050 |  |  | 150000 | Operational | IDP 3.16 | Support SMME's through the Business Services Partnership Fund | Number of SMMEs supported through the Business Services Partnership Fund | 10 SMMEs benefit from the Business Partnership Fund | Inhouse and External Funding |  |  |  |  | Formualte Proposal for the Implementation of the Partnership Fund and secure partnership | Advertise the Business Partnership Fund and identify beneficiaries | Implement the funding | Develop a report on the implementation of the fund | LED Directorate
[5 empty] | 400000 | Operational | IDP 3.17 | Establish an SMME Hive/Information Centre | Establishment of an SMME Hive/Information Centre | SMME Hive/Information Centre Established | Co-funding |  |  |  |  | Submit a proposal to Partners | Finalise Arrangement for the establishment of the centre/Signing of Contracts | Establish the centre | Project Closure | LED Directorate
[5 empty] | 100000 | Operational | IDP 3.18 | SMME market access study | SMME market access study | SMME Access Study Developed | Service provider |  |  |  |  | ToR Developed and Advertised | Serice Provide Appointed | SMME Access Study Conducted | Project Closure | LED Directorate
| Promote and support co-op development | 10/01/75/6915050 |  |  | 50000 | Operational | IDP 3.19 | Support Co-op development | Number of Co-operatives accessed funding and support | 4 Business Plans developed and 4 co-operatives accessed funding and support | Inhouse |  |  |  |  | Secure support for the development of the business plans | Business Plans Developed | Business Plans submitted for Funding and Support | Project Implemention Report | LED Directorate
| Promore and support the development of the informal sector | 10/01/75/6915050 |  |  | 100000 | Operational | IDP 3.20 | Informal Sector Development | Number of Hawkers and Informal Traders Capacitated | 20 Hawkers and Informal Traders Capacitated | In-House |  |  |  |  | Develop Informal Sector Development Implementation Plan | Implemented the Informal Sector Development Implementation Plan | Implemented the Informal Sector Development Implementation Plan | Project Closure | LED Directorate
|  | 90/75/05/9386 |  |  | 400000 | Capital | IDP 3.21 | Enhace the growth and development of informal economy | Number of structures for informal sector created | 7 Hawker Stalls Constructed | Service provider |  |  |  |  | Construction of structures | Construction of structures | Allocation of Stalls to Hawkers | Project closure | LED Directorate
| Ensure the creation of 1000 jobs for the unemployed |  |  |  | 0 |  | IDP 3.22 | Facilitate the implementation of CWP | No of jobs created | 900 jobs created | In-house |  |  |  |  | Monitor and Evaluate CWP Projects | Monitor and Evaluate CWP Projects | Monitor and Evaluate CWP Projects | Monitor and Evaluate CWP Projects | LED Directorate
[7 empty] | IDP 3.23 | Facilitate the implementation of EPWP projects | No of jobs created | 100 jobs created | [5 empty] | Submit a business plan for EPWP projects | Report on no of jobs created | Report on no of jobs created | Report on no of jobs created | LED Directorate
| Promote investment attraction | 75/05/6915/023 |  |  | 250000 | Operational | IDP 3.24 | Investment attraction | Makana Investment Guide and DVD | Develop Makana Investment Guide and DVD | Service Provider |  |  |  |  | Draft TOR and advertise for the appointment of service provider | Appointment of service provider | Project Conducted | Project closure | LED Directorate
[5 empty] | 0 | Operational | IDP 3.25 | Conduct assessment of business confidence | Number of business confidence levels assessement done | 2 Annualbusiness confidence levels assessement done | In-house/service provider |  |  |  |  | Request assistance from Rhodes University Community Engangement Office/Grahamstown Business Forum | Conduct business confidence assessments | Conduct business confidence assessments | Overall Report of the asssessments | LED Directorate
[6 empty] | Capital | IDP 3.26 | Implement the last phase of the NDPG | % Expenditure of the cial gazetted amount for the 2013/14 financial year | 90 % Expenditure | Contractors |  |  |  |  | 20% Expenditure | 40% Expenditure | 70% Expenditure | 90% Expenditure | LED Directorate
|  | 75/05/6915/025 |  |  | 300000 | Operational | IDP 3.27 | Inner City Regeneration | Business plan for inner city regenration | Business plan for inner city regenration available in order to raise funding for the project | In-house/service provider |  |  |  |  | Buy-in for project internally and id scope of project | Buy-in from external stakeholders | N/A | N/A | LED Directorate
| Support the Kaolin Mining Initiatives in the Municipality | 75/05/6915/023 |  |  | 50000 | Operational | IDP 3.28 | Establish a ceramic studio | A ceramic studio is established | Ceramic Studio Established | In-house/service provider |  |  |  |  | Identify Land and Support for the Kaolin Ceramic Studio | Roll-out the ceramic Studio | Ceramic Studio Operational | Ceramic Studio Operational | LED Directorate
[7 empty] | IDP 3.29 | Source Funding /Partnership for Kaolin Incubation Facility | R value of funsding support received for incubation centre | Funding Secured | In-house |  |  |  |  | 1 Funding Request Developed and Submitted to a potential Funder | 1 Funding Request Developed and Submitted to a potential Funder | 1 Funding Request Developed and Submitted to a potential Funder | Funding Request Developed and Submitted to a potential Funder | LED Directorate
[7 empty] | IDP 3.30 | Training for Kaolin Mining Co-operatives | No of Kaolin Mining Co-ops trained | Support Kaolin Training Initiatives | In-house |  |  |  |  | Identify areas of training support with Makana Mining Trust | Facilitate training support to kaolin mining co-operatives | Facilitate training support to kaolin mining co-operatives | Facilitate training support to kaolin mining co-operatives | LED Directorate
|  | 75/05/6915/023 |  |  | 250000 | Operational | IDP 3.31 | Support the Mining Trust | Formal agreement, expenditure reports to the Trust, financial statements from the Trust | Support to Makana Mining Trust | In-house |  |  |  |  | Identify areas of support to Makana Minig Trust | Formalise Agreement for the support | Distribute Fund for the support to Makana Minig Trust | Report on the use of the fund | LED Directorate
[7 empty] | IDP 3.32 | Secreteriat for the Kaolin Project Steering Committee | Minutes of PSC Meetings | 4 Kaolin Mining PSC held | In-house |  |  |  |  | I Kaolin PSC held | I Kaolin PSC held | I Kaolin PSC held | I Kaolin PSC held | LED Directorate
Promote and support tourism and heritage development to stimulate economic growth and development that will result in the creation of jobs | Promotion of arts and culture to create jobs | 10/75/05/6915/049 | KFA 3.3 | TOURISM DEVELOPMENT | 1500000 | Operational | IDP 3.33 | Creative City Project | Number of quick - win initiatives implemented through the streams | Successful implementation of Creative City Project | Partnership with National Arts Festival and Cacadu District Municipality |  |  |  |  | submit reports on the streams and present implementation plans | Present inception reports on the streams | Submit reports on the r implementation of quick win initiatives | Submit reports on the implementation of quick - win initiatives | LED Directorate
[5 empty] | 300000 | Operational | IDP 3.34 | Craft Sector Development Programme | Number of crafters trained, craft route map and a brochure | Training of 20 crafters, production of a craft route map and a brochure | Service provider |  |  |  |  | invite potential participants to register | Advertise and evaluate bids | Appoint a service provider, present inception report | Implement the programme | LED Directorate
[5 empty] | 150000 | Operational | IDP 3.35 | National Arts Festival marketing programme | Number of people visiting the MM stand at the NAF | Marketing the Municipality at the NAF | In house and service provider |  |  |  |  | secure a space from NAF | Advertise a bid for the design of stand | Appoint a service provider to design a stand, source SMMEs to exhibit at the NAF | Participate in the NAF | LED Directorate
| Create jobs for emerging tourist guides |  |  |  | 120000 | Operational | IDP 3.36 | Tourism Internship Programme | Portfolio Committee reports | 8 unemployed tourism graduates absorbed for experiential learning | Partnership with the National Arts Festival and Makana Tourism |  |  |  |  | Finalise Agreements | Advertise and appoint first batch of participants | Advertise and appoint second batch of participants | Prepare and submit Progress reports | LED Directorate
[5 empty] | 200000 | Operational | IDP 3.37 | Partnership opportunities with the Game Reserves | Report on potential partnership with the Game Reserves | identification of partnership opportunities with the Game Reserves | Service Provider |  |  |  |  | Formulate Terms of Reference | Advertise a bid | Appoint a service provider | Implement the project | LED Directorate
| Heritage Promotion |  |  |  | 150000 | Operational | IDP 3.38 | Heritage Promotion | Produce a heritage route map | Heritage route map | Service provider |  |  |  |  | Formulate Project Terms of Reference | Advertise and appoint a service provider | Submit project inception report, submit a draft map | submit a project close out report | LED Directorate
| Support to emerging tourism SMME's |  |  |  | 150000 | Operational | IDP 3.39 | Community based tourism support programme | Number of tourism SMMEs and Projects supported | 2 SMMEs, 2 Events and 1 heritage project supported | In house |  |  |  |  | formulate a roll out plan | Advertise a call for proposals | short list and award funding to eligible beneficiaries | Submit monitoring reports | LED Directorate
| Provide tourism infrastructure |  | KFA 3.4 | TOURISM INFRASTRUCTURE | 150000 | Capital | IDP 3.40 | Tourism Infrastructure Development | 3 tourism signboards installed | Installation of 3 tourism signs boards at various points in Makana | Service provider |  |  |  |  | Confirm installation points | Formulate Project Term of Reference | Advertise and appoint a service provider | Install signs | LED Directorate
|  | 90/10/53 |  | Spatial Palnning | 200000 | Capital |  | Spatial Development Framework Review | Complete Review SDF
|  | No vote number |  | Properties and estate | 5000000 | Capital |  | Upgrading of offices | Upgrading City Hall, DTIS,LED Buliding

## DTIS (hidden)
Objective | Strategy | KFA No | Key focus Areas |  |  | Project/Program | Projects Register ID | Key Perfomance Indicator |  | Annual Target | Service Develivery Model | Status Achieved or Not Achieved | Actual Perfomance | Deviation N/A | Corective Action | Milestones |  |  |  | Reponsible Directorate
[9 empty] | Annual Budget | [6 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Well structured, efficient provision of basic services and that supports sustainable human settlement by 2017 | Provide quality road and stormwater | KFA 1.1 | Roads and Stomwater | 400000 | Capital | Development Stormwater Master Plan and Design | IDP 1.00 | Compile a Stormwater Master Plan and Design |  | N/A
|  | KFA 1.1 | Roads and Stomwater | R 3000000-500 000 for EPWP | Operational | Construction of kerbs using EPWP Model | IDP 1.01 | Number of meters construcuted and number of temporal job created | 500000 | 150 Meters | Outsorced |  |  |  |  | 10% (Procument) | 50% Complete | 100% Complete | N/A | Technical and Infrastructure
|  |  |  | 2000000 | Capital | Resealing of roads | IDP 1.01 | No of square meters for SLURRY SEAL and number of temporal jobs created | 2000000 | 3500 m² | Outsorced |  |  |  |  | N/A | 10% (Procument) | 100% Complete | N/A | Technical and Infrastructure
[6 empty] | Repairs of sidewalks | IDP 1.03 | No of meters repairs | 500000 | 500 Meters | Outsorced |  |  |  |  | 10% (Procument) | 50% Complete | 100% Complete | N/A | Technical and Infrastructure
|  |  |  | 1000000 | Capital | Construction of new sidewalks | IDP 1.04 | No of Km of Sidewalks Constructed and number of temporal job created | 500000 | 200 Meters | Outsorced |  |  |  |  | 10% (Procument) | 50% Complete | 100% Complete | N/A | Technical and Infrastructure
[7 empty] | IDP 1.05 | SANI Street upgrade | 6000000 | 1500 Meters | Outsorced |  |  |  |  | 10% (Procument) | 50% Partially complete | 100% Complete | N/A | Technical and Infrastructure
|  |  |  | 180000 | Capital | Upgrading and updating of GIS |  | Upgrading of GIS | No Budget | [9 empty] | N/A | Technical and Infrastructure
|  | KPI 1.3 | Properties and land Estate | 5000000 | Capital | Upgrading of offices | IDP 1.07 | Upgrading City Hall, DTIS,LED Buliding | 10000000 |  | Outsorced | [5 empty] | 10% (Procument) | 10% Partially complete | 15% Partially complete | Technical and Infrastructure
| Ensure that all communities of Makana have access, constant and safe provision to adequate basic services | KFA 1.4 | WATER AND SANITATION(administration) | 200000 | Capitla | Pumping and Purification | IDP 1.12 | Waainek WTW: Lining of Storage Dams | 3156513 | One Dam lined: Waainek | Outsourced |  |  |  |  | 10% (Procument) | 50% Partially complete | 100% Complete | N/A | Technical and Infrastructure
|  |  |  | R12 275 500.00 Plus R 43 000 000.00 | MIG/DBSA | Upgrading of bulk water James Kleyhans | IDP 1.13 | Installation of water pipe line and construction of a new reservoir | 37648625 | 9.2km Pipeline & 1x New Reservoir | Outsourced |  |  |  |  | 75% Partially complete | 100% Complete | N/A | N/A | Technical and Infrastructure
|  |  |  | 2000000 | Operational | Replacement of AC pipes | IDP 1.14 | Replacement AC pipe | 940000 | 250 Meters | [5 empty] | 50% Partially complete | 75% Partially complete | 100% Complete | N/A | Technical and Infrastructure
[6 empty] | Manhole Covers - Sewer | IDP 1.15 | % of Manholes covered | 150000 | 10 Manhole Covers | Outsorced |  |  |  |  | 10% (Procument) | 100% Complete | N/A | N/A | Technical and Infrastructure
[6 empty] | Replacing Sewer Main - KwaThatha | IDP 1.16 | % of complete project | 800000 | Sewer Main Line installed | Outsorced |  |  |  |  | 10% (Procument) | 100% Complete | N/A | N/A | Technical and Infrastructure
[6 empty] | Relief Rising Main at Town to Treatment works | IDP 1.17 | % of complete project | 1900000 | 1x Rising Main Installed | Outsorced |  |  |  |  | 10% (Procument) | 75% Partially complete | 100% Complete | N/A | Technical and Infrastructure
[6 empty] | New Drying Beds Pumps & Line Main | IDP 1.18 | % of complete project | 1000000 | 1x Dry bed pumps constructed | Outsorced |  |  |  |  | 10% (Procument) | 75% Partially complete | 100% Complete | N/A | Technical and Infrastructure
[6 empty] | Replace bidim & sand on drying beds | IDP 1.19 | % of complete project | 338933 | 1x Dry bed pumps repaired | Outsorced |  |  |  |  | 10% (Procument) | 100% Complete | N/A | N/A | Technical and Infrastructure
[6 empty] | Replace mechanical screen with rotary drum | IDP 1.20 | % of complete project | 300000 | 1x rotary drum replaced | Outsorced |  |  |  |  | 10% (Procument) | 100% Complete | N/A | N/A | Technical and Infrastructure
|  |  | MIG PROJECTS | 1880000 | MIG | Conversion of VIP's Waterborne sanitation at Lower Makana | IDP 1.21 | % Complete the projects | 2800000 | 1x waterborne sanitation corverted | Outsorced |  |  |  |  | 50% Partially complete | 75% Partially complete | 100% Complete | N/A | Technical and Infrastructure
|  |  |  | 10000000 | MIG | Extesion 6 Sewer reticulation Phase 2 - Stage 2 | IDP 1.22 | % Complete the projects | 6446379.55 | 1x Ext. 6 Sewer Ret. Complete. | Outsorced |  |  |  |  | 50% Partially complete | 75% Partially complete | 100% Complete | N/A | Technical and Infrastructure
|  |  |  | 3860000 | MIG | Construction of Oxidation ponds | IDP 1.23 | Construction of Oxidation ponds at Riebeeck East | 2361740.51 | 1x Oxidation Pond constructed | Outsorced |  |  |  |  | 50% Partially complete | 75% Partially complete | 100% Complete | N/A | Technical and Infrastructure
|  |  |  | 200000 | Capital | Extesion 6 Sewer reticulation Phase 2 - Stage 3 | IDP 1.24 | % of complete project | 6000000 | 1x Ext. 6 Sewer Ret. Complete. | Outsorced |  |  |  |  | 10% (Procument) | 50% Partially complete | 100% Complete | N/A | Technical and Infrastructure
|  |  |  | 100000 | Capital | Construction of Extension 6 Toilet Structures | IDP 1.25 | % of complete project | 7802265 | 400 toilet structure constructed | Outsorced |  |  |  |  | 10% (Procument) | 50% Partially complete | 100% Complete | N/A | Technical and Infrastructure
|  |  |  | 80000 | Capital | Social services Projects | IDP 1.26 | % of complete project | 3987715 | 1x Recreation Centre constructed | Outsorced |  |  |  |  | 10% (Procument) | 50% Partially complete | 100% Complete | N/A | Technical and Infrastructure
|  |  | Electricity | R 945 000 | Operational | Refurbishing and upgrading of street and Highmast | IDP 1.30 | 1. Upgrade & Replace S/lights @ High Street 2. Ext. of DR J. Zuma Dr. S/light 3. Replace High Mast Bases | 950000 |  | Outsorced |  |  |  |  | 10% (Procument) | 50% Partially complete | 100% Complete | N/A | Technical and Infrastructure
|  |  |  | R 4 500 000 | Capital | 66 KV Network Refurbishment | IDP 1.31 | 1. 2x5 MVA G'town Transformer 2. Summit Drainage 3. refurbish 3MVA Transformer | 3625000 | 2x 5MVA Transformer and 1x 3MVA Transformer | Outsorced |  |  |  |  | 10% (Procument) | 50% Partially complete | 100% Complete | N/A | Technical and Infrastructure
|  |  |  | 100000 | Capital | Electrification | IDP 1.32 | 1. Infill Areas 2. Ethembeni 3. Mayfield | 3500000 | 3x Areas electrified | Outsorced |  |  |  |  | 10% (Procument) | 50% Partially complete | 100% Complete | N/A | Technical and Infrastructure
| Ensure well structured quality housed across municipality |  | Housing provision |  |  | Housing development, Mayfiled phase II | IDP 1.33 | 1000 Units Housing Constructed & 1000 sites serviced | No budget | 1 000 Houses constructed & 1 000 site services | Outsorced |  |  |  |  | 50% Partially complete | 75% Partially complete | 100% Complete | N/A | Technical and Infrastructure
[6 empty] | Unblock and facilitate other housing development projects | IDP 1.34 | Report to Council Quarter on the Portfolio Committee on the progress made | No budget | 1. Eluxolweni 2. Fingo Village 237 3. KwaNdancama 4. Alicedale 22 5. R/East 16, 6.Seven fountains, 7. Fort brown | In-house |  |  |  |  | Quarterly report is submitted to Portfolio Committee | Quarterly report is submitted to Portfolio Committee | Quarterly report is submitted to Portfolio Committee | Quarterly report is submitted to Portfolio Committee | Technical and Infrastructure
[6 empty] | Housing Rectification program | IDP 1.35 | Report to Council Quarter on the Portfolio Committee on the progress made |  | 1.Disaster 2006-2008, 2.Scotts farm,3 Ghost Town , 4 New Town 5.Vukani, 6. Ext 7 | In-house |  |  |  |  | Quarterly report is submitted to Portfolio Committee | Quarterly report is submitted to Portfolio Committee | Quarterly report is submitted to Portfolio Committee | Quarterly report is submitted to Portfolio Committee | Technical and Infrastructure