REVISED

INTEGRATED IDP/BUDGET AND PERFORMANCE MANAGEMENT REVIEW PROCESS PLAN

2015-2016

CONTENTS PAGE

SECTION:		TITLE 						PAGE

Section	1:		Background

  - The Integrated Development Planning 	         3

Process

Section	2:		Objective and Approach

  - Objective of the IDP Review Process	         4

  - Approach to the 2015/2016 IDP Review	         4

Section	3:		Organisational structures/institutional

Arrangements

  - IDP Steering Committee				5

  - The IDP Manager and Responsibility		5

  - IDP Representative Forums				6

Section	4:		Distribution of roles and Responsibilities

  - Summary of Role Players/Responsibilities 	7

Table 1	Roles and responsibilities (Internal)	    	8

Table 2	Roles and responsibilities (External)		9

Section	5:		Integrated IDP/Budget and Performance

Management Action Programme with timeframes (Annexure A)

Section 	6:		Mechanisms for Community and 			10

Stakeholder Participation

Section 	7:		Mechanisms for Alignment                               11

SECTION 1: BACKGROUND

  - THE INTEGRATED DEVELOPMENT PLANNING PROCESS

The Integrated Development Planning (IDP) Process is a process through which Municipalities prepare strategic development plans for a five year period.  An IDP is one of the key tools for Local Government to cope with its developmental role and seek to arrive at decisions on issues such as municipal budget, land management, promotion of local economic development and institutional transformation in a consultative, systematic and strategic manner.

According to the Municipal Systems Act (MSA) of 2000, all Municipalities have to undertake the preparation of an IDP process plan to guide the development of an Integrated Development Plan.  As the IDP is a legislative requirement, it has a legal status and it supersedes all other plans that guide development at Local Government level.

Section 26 of the MSA, stipulates the core components of the IDP as following:

- The Municipal Council’s vision for the long term development of the municipality with special emphasis on the municipality’s most critical development and internal transformation needs.

- An assessment of the existing level of development in the municipality, which must include and identification of communities which do not have access to municipal service.

- The Council’s development priorities and objectives for its elected term, including the local economic development aims and its internal transformation needs.

- The Council’s development strategies which must be aligned with any national and provincial sectoral plans and planning requirements binding on the Municipality.

- The spatial development framework, which must include the provision of basic guidelines for a land use management system for the Municipality.

- The Council’s operational strategies.

- Applicable disaster management plans.

- A Financial plan, which must include a budget projection for at least the next three years, and the key performance indicators and performance targets determined in terms of Section 41 of the MSA.

SECTION 2:  OBJECTIVES AND APPROACH

  - OBJECTIVE OF THE IDP REVIEW PROCESS

The Makana Municipality wants to continue to develop the IDP as an effective management tool for the municipality, this includes:

- Creating a greater level of focus and thereby improving on the strategic nature of the document.

- Aligning this strategic document with the realities of the resources available i.e. financial and human,

- Alignment of the IDP with the activities of the Sector Departments and other service providers (and vice versa) and

- Alignment of the IDP with the various sector plans.

  - APPROACH TO THE 2015/16 IDP REVIEW

- Strategic review of the content of the 2015-2016

- Review of Sector plans

- Community Based Planning Approach

- Sector Alignment

- IDP –Budget Alignment

- Sector Alignment

- Community Engagement(Public Participation) for approval

- Finally, the preparation of the IDP which consists of Core and Non-core elements. These are define as follows:

- CORE ELEMENTS

The ‘core elements’ of the IDP correspond to the core function of municipalities as outlined in the Municipal Systems Act and other legislation, the DPLG’s Guide Pack III (DPLG, 2000), critical elements that have arisen from the preparation of the IDP’s over the past years, as well as the comments from the MEC for the Department Cooperative Government and Traditional Affairs.

The core components of the 2015/16 IDP process are grouped as follows:

- Comments received from the various role players in the IDP process including the comments from the MEC.

- Medium Term Planning Framework

- Six Key Performance areas as outlined in the IDP Assessment tool.

- Areas including additional attention in terms of legislative requirement.

- Areas identified through self-assessment.

- The update of the IDP objective, strategies and projects.

- The preparation of the Sector Plans and incorporation of recommendations into the new IDP.

- Performance Management System (PMS)

- The Spatial Development Framework

- District/Local Municipality’s alignment strategies and

- Integrated Communication Plan

- NON-CORE ELEMENTS

Non-core elements are those programmes and Sector Plans that have been prescribed by various Government Departments, but guidelines for the preparation and /or funds have been set aside for the preparation of these Plans.

SECTION 3:	ORGANISATIONAL STRUCTURES/ INSTITUTIONAL

ARRANGEMENTS

3.1. IDP STEERING COMMITTEE

As part of the IDP preparation process, the IDP Steering Committee will be revived and will perform the function of internal co-ordination and alignment.

The Chairperson of the Committee will be the Chairperson of Budget, Treasury and IDP Portfolio Committee. The Secretariat will be the function of the IDP Manager.  The Committee will comprise Heads of Departments, relevant Senior Officials and the (Mayoral Committee including the Executive Mayor).

In terms of the guideline IDP manual, the IDP Steering Committee is intended to be a working group made up of dedicated Heads of Department and other senior officials, who support the IDP Manager and ensure a smooth planning process. Although the IDP Manager is responsible for the IDP process, functions can be delegated to a member of the Steering Committee.

The IDP Steering Committee has no decision making powers, but is an advisory body to the Representative Forums. For instance, it can consider and comment on the inputs from subcommittees, National, Provincial Department and Service Providers.

3.2. THE IDP MANAGER AND RESPONSIBILITIES

Amongst other, the following responsibilities have been allocated to the IDP Manager for the IDP Process:

- To ensure that the Process Plan is finalised and adopted by Council.

- To adjust the IDP according to the proposals of the MEC.

- To identify additional role players to sit on the IDP Representative Forums.

- To ensure the continuous participation of role players.

- To ensure appropriate procedures are followed.

- To ensure documentation is prepared properly.

- To oversee the day to day management of the IDP Process.

- To respond to comment and enquiries.

- To ensure alignment of the IDP with other IDP’s within the District Municipality.

- To co-ordinate the preparation of the Sector Plans and their inclusion into IDP documentation.

- To co-ordinate the inclusion of the Performance Management Systems (PMS) into the IDP.

- To submit the reviewed IDP to the relevant authorities.

3.3   IDP REPRESENTATIVE FORUM

The IDP Representative Forum that was constituted for the previous IDP Process will be utilised and continue to function throughout this IDP Process.  Additional effort will need to be made to include more organisations and ensure their continued participation throughout the IDP Review. It is therefore recommended that advertisements be placed in the local newspaper, on notice boards and over the radio stations to inform the community members of the IDP participation process through the IDP representative forum.

    - Suggested Public Participation Representative Forums:

  - Community Stakeholder Forum

  - Sector Alignment Forum(to be clustered according development needs)

  - Business and Non Governmental Organisation(to Categorised)

SECTION 4: DISTRIBUTION OF ROLES AND RESPONSIBILITIES

  - SUMMARY OF ROLE PLAYERS /RESPONSIBILITIES

The following are the role players in the IDP Process:

- Council and the Executive Committee

- Mayor

- Municipal Manager

- IDP Manager

- IDP Technical Committee (New)

- IDP Steering Committee

- Municipal Officials

- Representative Forum

- The District Municipality

- Relevant Government Departments and Service Providers.

The main roles and responsibilities allocated to each of the role players are set out in the following table:

TABLE 1:  ROLES AND RESPONSIBILITIES (INTERNAL)

| ROLE PLAYERS | ROLES AND RESPONSIBILITIES |
| --- | --- |
| Council | - Final decision making - Approval of the reviewed IDP documentation. |
| Ward Councillor | - Linking the IDP process with their constituencies. - Organising public participation at ward level. |
| Mayor | - Manage the drafting of the IDP. - Assign responsibilities to the MM. - Submit the IDP Process Plan to Council for approval. - Chairs the IDP Technical and IDP Rep Forum. |
| Municipal Manager | - Prepare IDP process plan. - Ensure that timeframes are adhered to. - Decide on and monitor IDP process. - Overall management and co-ordination. |
| Mayoral Committee | - To help to harness common understanding between political and administrative component before the IDP reports are considered at Council meeting. - Makes recommendations to the IDP Representative Forum. |
| IDP Manager | - Day to day management of the IDP process. - Co-ordinate technical or sector expertise. - Co-ordinate Sector plan inputs - Prepare draft progress reports. |
| IDP/Budget and Performance Management Steering Committee | - Assist and support the Municipal Manager/CFO/IDP Manager and IDP Representative Forum. - Information “GAP” identification. - Oversee the alignment of the planning process internally with those of the Local Municipality areas. - Portfolio head to lead related Portfolio matters - Assist in prioritisation IDP strategies and Budget. |
| The District Council | - Co-ordination role with all Local Municipalities within the District. - Ensuring horizontal and vertical alignment of the IDP’s of the Municipalities in the District Council area. - Facilitation of vertical alignment of IDP’s with other spheres of Government and Sector Departments. - Provide events for joint strategy workshops with Local municipalities, Provincial and National role players and other subject matter specialist. |

TABLE 2: ROLES AND RESPONSIBILITIES (EXTERNAL)

| ROLE PLAYERS | ROLES AND RESPONSIBILITIES |
| --- | --- |
| Ward Committees | - To be consulted on an individual or collective basis to establish community needs and reach consensus on IDP Projects/Initiatives and Priorities. |
| IDP Representative Forum | - Representing public interest and contributing knowledge and ideas. |
| Government Departments, Parastatals and NGO’s | - Provide data and information. - Budget information - Alignment of budget with the IDP - Provide professional and technical support. - To assist in facilitating the CBP |
| DBSA Planning Expert and Sarah Baartman DM | Methodology guidance and professional support in: - Strategic and Town Planning - Sector Plan Inputs - IDP Document preparation. - Alignment with National, Provincial and CDM |

SECTION 5:  INTEGRATED IDP/BUDGET AND PERFORMANCE MANAGEMENT PROCESSES PLAN ACTION PROGRAMME

A detailed activity and associated timelines is attached as:  Annexure A

SECTION 6:	MECHANISMS FOR COMMUNITY AND STAKEHOLDER PARTICIPATION

| PHASE | PARTICIPATION MECHANISMS |
| --- | --- |
| Analysis | Community Based Planning |
|  | IDP Representative Forum (Community Stakeholder Forum) |
|  | IDP Representative Forum (Stakeholders Alignment engagement) |
|  | IDP Representative Forum (Business/Non Governmental Forum) |
| Strategies and Objectives | District Level Strategy workshops |
|  | IDP Representative Forum meetings |
|  | Steering Committee Meeting |
| Project Proposals | IDP Representative Forum Meeting |
|  | Steering Committee Meeting |
| Integration | IDP Representative Forum (Sector Stakeholder Alignment Forum) |
| Approval | Mayoral Imbizo’s Community Engagement on budget |
|  | Opportunity for comments from residents and stakeholder organisations |

SECTION 7:	MECHANISMS FOR ALIGNMENT

| SPHERE | DEVELOPMENT PLANNING INSTRUMENT | RESOURCE ALLOCATION | ANNUAL CYCLE | REVIEW CYCLE |
| --- | --- | --- | --- | --- |
| National | Medium Term Strategic Framework (MTSF) | National Budget: Medium Term Expenditure Framework (3 years) | 1 April – 31 March | July - September |
| Provincial | Provincial Growth and Development Strategies | Medium Term Expenditure Framework (3 years) | 1 April – 31 March | July - September |
| Sector | Strategic Plans for sector departments | MTREF (3 years) | 1 April – 31 March | July – September |
| Local/Rhodes University | Integrated Development Plan | Municipal Budget (5 year plan) | 1 July -30 June | September – February |

Makana Recovery Plan

According to the Status Quo Report compiled in October 2014 the situation has not improved but rather seems to be regressing rapidly.  The Eastern Cape Provincial Planning and Treasury (PT), deployed an acting CFO to the municipality as well as 2 other support staff to enhance the Budget and Treasury office, while at the same time the Department of Local Government and Traditional Affairs (DLGTA) also deployed an acting municipal manager.

Given the seriousness of the challenges and in an attempt to halt the decline, the Eastern Cape Provincial Executive has instituted an intervention in terms of section 139(1) (b) of the Constitution.

An Administrator was appointed and assumed duty on 6 October 2014 and an Acting Chief Financial Officer was deployed by Province to Makana in April 2014.

The intervention occurred in response to many crises Makana is facing including difficulties in providing basic services and long term financial sustainability.

The Municipality is specifically challenged in the following areas:

- Infrastructure (water and electricity outages; poor infrastructure operations and management; dilapidated roads, housing backlogs; poor waste management)

- Governance (4 disclaimers; compliance challenges; lack of political oversight, non-effective performance management; community protests; allegations of corruption and nepotism and lack of compliance with prescripts, no adopted and aligned SDBIP;)

- Institutional (skills and capacity gaps; non effective performance management system, local labour forum not fully functional; Council Committees and management structures not meeting regularly and often shifted; high overtime spending; no strong links with communities);

- Financial (The municipality is not able to meet its current and statutory obligations and expenditure far exceeds revenue collected resulting in rising levels of unpaid creditors; litigation by creditors; declining Audit Outcomes – the Municipality has had 4 multiple disclaimers from the Auditor General, inadequate internal controls and non-adherence to policies and procedures; inadequate revenue collection and overreliance on grant funding and has used earmarked funding for operational expenses; systems and processes not adequate; poor and weak supply chain and contract management).

Given the above and the urgency to ensure service delivery to communities and financial viability and sustainability, the development of a Financial Recovery Plan has now been seen as a critical way forward for Makana.

A Status Quo Assessment Report has been developed as a first step towards developing the financial recovery plan, the assessment focused on the institutional, service delivery, infrastructure, and financial challenges impacting on the performance and service delivery imperatives of Makana, with a view to inform the development of a holistic financial recovery plan for Makana to enable a turnaround, stabilisation and sustainability of the municipality.

Analysis of information which included the budget, financial, organisational and service delivery has been undertaken and used to inform the status quo report. This was also supplemented by a two day workshop at the municipality on the 15 and 16 October 2014.

The case for change: Changing the status quo at MLM is not negotiable.  Bringing the municipality from a state of being categorized as dysfunctional to a well-performing and responsive municipality is the cornerstone of the intervention plan. The Section 139 (1) (b) intervention must be seen as a platform to introduce a change agenda which can be seen as a short term (6 months) intervention however with a specific purpose of altering the current trajectory towards a sustainable, responsive and viable municipality.

The Section 139 (1) (b) intervention plan is premised on the following fundamentals:

•	Stabilize the institution and ensure organization wide compliance;

•	Develop an organization wide change management process;

•	Restore service delivery using the back to basics approach;

•	Improve communication and connection through effective stakeholder and Community engagements;

•	Develop a transparent monitoring and accountability framework.

The change approach: The diagram below illustrates the approach to be followed:

- Reconnecting with communities

- Ensuring financial sustainability

- Driving service delivery

- Improve oversight and governance

- Capacitate the municipality

ANNEXURE A: TIME SCHEDULE

| IDP/PMS and Budget Process Plan 2015-16 |  |  |  |  |  | Status | Revised/ Proposed Dates |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CATEGORY | ACTION | PURPOSE |  | RESPONSIBILITY | DATE |  |  |
| Meeting Schedule – July to December 2015 | Council |  | Support and oversight | Makana Local Municipality | 20 July 2015 |  |  |
|  | Aesthetic Committee |  |  |  | 21 July 2015 |  |  |
|  | LLF |  |  |  | 28 July 2015 |  |  |
|  | Tourism & Cultural Industries |  |  |  | 29 July 2015 |  |  |
|  | Social Development |  |  |  | 30 July 2015 |  |  |
|  | Infrastructure Development |  |  |  | 17 July 2015 |  |  |
|  | Local Economic Development |  |  |  |  |  |  |
|  | Finance, Admin, Mon & Ev (F&C) |  |  |  |  |  |  |
|  | Mayoral Committee |  |  |  | 14 July 2015 |  |  |
|  | Training Committee |  |  |  |  |  |  |
|  | Library Advisory |  |  |  |  |  |  |
|  | Budget Steering Committee |  |  |  | 13 July 2015 |  |  |
|  | Audit Committee |  |  |  | 23 July 2015 |  |  |
|  | Local Aids Council |  |  |  |  |  |  |
| Meeting Schedule: July – December 2015 | Council |  | Support and Oversight | Makana Local Municipality | 21 Aug 2015 |  |  |
|  | Aesthetic Committee |  |  |  | 31 Aug 2015 |  |  |
|  | LLF |  |  |  |  |  |  |
|  | Tourism & Cultural Industries |  |  |  |  |  |  |
|  | Social Development |  |  |  |  |  |  |
|  | Infrastructure Development |  |  |  |  |  |  |
|  | Local Economic Development |  |  |  | 04 Aug 2015 |  |  |
|  | Finance, Admin, Mon & Ev (F&C) |  |  |  | 06 Aug 2015 |  |  |
|  | Mayoral Committee |  |  |  | 18 Aug 2015 |  |  |
|  | Training Committee |  |  |  | 25 Aug 2015 |  |  |
|  | Library Advisory |  |  |  | 27 Aug 2015 |  |  |
|  | Budget Steering Committee |  |  |  | 12 Aug 2015 |  |  |
|  | Audit Committee |  |  |  | 25 Aug 2015 |  |  |
|  | Local Aids Council |  |  |  | 14 Aug 2015 |  |  |
| IDP/Budget | Preparation tabling of timelines to Council an IDP/ Budget Time table |  | Review Process Plan and develop IDP/PMS and Budget time schedule for 2015/16 (MFA S35 (1). | IDP/PMS Manager and CFO | 21 Aug 2015 | Done |  |
| IDP/Budget | Upload Process Plan 2014/15 on Website and publicise in local newspaper |  | Notify the public of on key planning process | IDP/PMS Manager and CFO | 28 August 2015 | Note | 24 February |
| IDP and Budget | Planning of the next three year budget in accordance with ordination role of the budget process ( Budget plans, capital / operational budget to have been consolidated (based on the budget inputs submitted by Departments)) |  | Consultation internal stakeholders | Accounting officer and Sec 57 Directors | 30 August 2015 | Not Done | 31 March 2016 |
| IDP | Consultation with Sarah Baartman DM, IDP & Planning Unit | To track progress and render support |  | IDP/ PMS Manager | Monthly | Done |  |
| EM | Mayors’ Forum |  |  | SBDM | 12 August 2015 | Done |  |
| Community & Social Cohesion | Disaster Management Advisory Forum |  |  | SBDM | 13 August 2015 |  |  |
| IDP n Public Participation | Call for civil society to register for Representation on Rep Forum; Update database and reconstitute public participation structures (e.g. IDP Representatives Forum) (Same advert as above) | Legislative requirement to ensure inclusivity in budgetary and planning processes. |  | Accounting officer CFO, IDP Official | 28 August 2015 or 04 Sept 2015 |  |  |
|  | Council | Support and Oversight |  | Makana Local Municipality | 03 Sept 2015 |  |  |
|  | MPAC |  |  |  |  |  |  |
|  | Aesthetic Committee |  |  |  |  |  |  |
|  | LLF |  |  |  | 01 Sept 2015 |  |  |
|  | Tourism & Cultural Industries |  |  |  | 08 Sept 2015 |  |  |
|  | Social Development |  |  |  | 09 Sept 2015 |  |  |
|  | Infrastructure Development |  |  |  | 10 Sept 2015 |  |  |
|  | Local Economic Development |  |  |  | 15 Sept 2015 |  |  |
|  | Finance, Admin, Mon & Ev (F&C) |  |  |  | 17 Sept 2015 |  |  |
|  | Mayoral Committee |  |  |  | 29 Sept 2015 |  |  |
|  | Training Committee |  |  |  |  |  |  |
|  | Library Advisory |  |  |  |  |  |  |
|  | Budget Steering Committee |  |  |  | 11 Sept 2015 |  |  |
|  | Audit Committee |  |  |  |  |  |  |
|  | Local Aids Council |  |  |  |  |  |  |
| IDP Public Participation | Undertake ward-wide Community Base Planning workshops. | Present IDP Process Plan / Time Schedule; Present 2014/15 ward priorities; report back on project progress; cost implications and challenges. Obtain new needs to be prioritised for 2015/16. |  | Accounting Officer | 7 – 11 Sept 2015 | Done |  |
| IDP Public Participation | Integrated Development Planning Community and Stakeholder engagement | Report on the Community on the development of IDP Review Process and Development of Recovery Plan |  | Accounting officer | Sept/ Oct 2015 | Done |  |
| Meeting Schedule: July – December 2015 | Council | Support and Oversight |  | Makana Local Municipality |  |  |  |
|  | MPAC |  |  |  |  |  |  |
|  | Aesthetic Committee |  |  |  |  |  |  |
|  | LLF |  |  |  |  |  |  |
|  | Tourism & Cultural Industries |  |  |  | 12 Oct 2015 |  |  |
|  | Social Development |  |  |  | 12 Oct 2015 |  |  |
|  | Infrastructure Development |  |  |  | 12 Oct 2015 |  |  |
|  | Local Economic Development |  |  |  | 19 Oct 2015 |  |  |
|  | Finance, Admin, Mon & Ev (F&C) |  |  |  | 19 Oct 2015 |  |  |
|  | Mayoral Committee |  |  |  |  |  |  |
|  | Training Committee |  |  |  |  |  |  |
|  | Library Advisory |  |  |  |  |  |  |
|  | Budget Steering Committee |  |  |  |  |  |  |
|  | Audit Committee |  |  |  |  |  |  |
|  | Local Aids Council |  |  |  |  |  |  |
| MM | Municipal Managers’ Forum |  |  | SBDM | 07 October 2015 |  |  |
| CFO | Chief Financial Officers’ Forum |  |  | SBDM | 08 October 2015 |  |  |
| PMS | Signing and uploading of SDBIP 2014/15 on Website and publicise | Notify the public of set targets and performance indicators |  | PMS Official | 26 June 2015 | Done |  |
| PMS | First Quarter Performance Review | Legislative requirement |  | Accounting officer | Within 30 days after end of the Quarter | Done |  |
| PMS | Review of performance by Internal Audit | First Quarter Performance Evaluation Reports in preparation for Councils consideration for adoption |  | Council | Within 15days after every quarter (Reports & POEs handed to PMS office within 10days after each quarter; 5 days later handed over to Internal Audit). | Done | 29 April 2016 |
| PMS | Submission of Draft Performance Agreements (2014/15) Managers reporting to the Administrator and Submit to MEC, upload on Website and publicise. | Legal requirement |  | Municipal Manger | August 2015 | Done |  |
| PMS | Signing Performance Agreements and Submit to MEC, upload on Website and publicise | Legal requirement |  | Administrator | August 2015 | Done |  |
| PMS | Q1 Performance Assessment | Evaluation Sec 56/57 managers, lower levels if applicable and institution PMS - Legal compliance |  | MM and PMS Officer | 15 Oct 2015 | Done |  |
|  | Council | Support and Oversight |  | Makana Local Municipality |  |  |  |
|  | MPAC |  |  |  | 20 Nov 2015 |  |  |
|  | Aesthetic Committee |  |  |  | 09 Nov 2015 |  |  |
|  | LLF |  |  |  | 11 Nov 2015 |  |  |
|  | Tourism & Cultural Industries |  |  |  | 17 Nov 2015 |  |  |
|  | Social Development |  |  |  | 18 Nov 2015 |  |  |
|  | Infrastructure Development |  |  |  | 19 Nov 2015 |  |  |
|  | Local Economic Development |  |  |  | 24 Nov 2015 |  |  |
|  | Finance, Admin, Mon & Ev (F&C) |  |  |  | 26 Nov 2015 |  |  |
|  | Mayoral Committee |  |  |  | 10 Nov 2015 |  |  |
|  | Training Committee |  |  |  | 03 Nov 2015 |  |  |
|  | Library Advisory |  |  |  | 26 Nov 2015 |  |  |
|  | Budget Steering Committee |  |  |  | 12 Nov 2015 |  |  |
|  | Audit Committee |  |  |  | 26 Nov 201 |  |  |
|  | Local Aids Council |  |  |  |  |  |  |
| PMS | Review of Mid-inyear performance Report and Annual Report of previous year by MPAC and adoption by Council | Moderate Performance evaluation Reports in preparation for Council |  | MPAC and Council | 20 Nov 2015 | Done |  |
| EM | Mayors’ Forum | Support and Oversight |  | SBDM | 11 Nov 2015 |  |  |
| EM | District Aids Council |  |  | SBDM | 18 Nov 2015 |  |  |
| Community & Social Services | Disaster Management Advisory Forum |  |  | SBDM | 12 Nov 2015 |  |  |
|  | Council |  |  |  | 03 Dec 2015 |  |  |
|  | MPAC |  |  |  |  |  |  |
|  | Aesthetic Committee |  |  |  |  |  |  |
|  | LLF |  |  |  |  |  |  |
|  | Tourism & Cultural Industries |  |  |  |  |  |  |
|  | Social Development |  |  |  |  |  |  |
|  | Infrastructure Development |  |  |  |  |  |  |
|  | Local Economic Development |  |  |  |  |  |  |
|  | Finance, Admin, Mon & Ev (F&C) |  |  |  |  |  |  |
|  | Mayoral Committee |  |  |  | 08 Dec 2015 |  |  |
|  | Training Committee |  |  |  |  |  |  |
|  | Library Advisory |  |  |  |  |  |  |
|  | Budget Steering Committee |  |  |  | 11 Dec 2015 |  |  |
|  | Audit Committee |  |  |  | 04 Dec 2015 |  |  |
|  | Local Aids Council |  |  |  |  |  |  |
| IDP/Budget | Determine the funding/ revenue projections for the next three years; The Executive Mayor to determine the strategic objectives for service delivery and development for the next three years (IDP reviews) | Budget preparation |  | CFO | 1 Sept 2015 | In progress |  |
| IDP | Strategic Planning Session | Track progress on implementation sees if targets are met. Review institutional functionality and verify level of Service Delivery. Facts and figures for consolidation with ward analysis. Review of the financial strategies and key economic and financial planning assumptions. Project scoping and budget allocations. |  | Municipal Manager, Directors, Council and Union | January 2016 | Not Done | March 2016 |
| IDP | Organogram review | Legal Compliance to Enable the IDP implementation |  | Municipal Manager, Directors, Council and Unions | Awaiting labour forum decision | Done |  |
| Budget | Directors to have met with their HOD’s and any relevant staff members to discuss draft capital / operational budget to ensure that anticipated expenditure meets parameters set out byNational / Provincial Government. | Legal requirement |  | Directors / Budget Office | Feb-16 | Not Done | 23-29 February 2016 |
| IDP/Budget | Submit proposed DRAFT 2016/17 Operating and Capital Budget requirements by directorates to the CFO | Preparation of the proposed budget and indicative 2016/17 forecast. |  | Municipal Manager, CFO and Section 56 Managers (Directors) | 14 March 2016 |  |  |
| IDP/Budget | Review Budget related policies and by-laws | Legal Compliance -review, update and check relevance |  | CFO | By end November 2015 | Done | N/A |
| Budget | Finalise the annual review of tariffs, fees and charges | To determined increase to be undertaken to cover services delivery. |  | Municipal Manager, CFO and Directors | 02 January 2016 | In progress | 29 February 2016 |
| IDP | Convene the IDP and Budget Steering Committee meeting. | Report on refined objectives and strategies, planned strategic interventions and proposed amendments to the organogram in response to overcome challenges. P+C47resent consolidated proposed Directorate projects and budget needs. |  | Municipal Manager and CFO | Monthly | 11 March 2016 |  |
| IDP | Convene the second IDP Representatives Forum meeting (community engagement) | Report on community needs; Report on interventions and strategies to deal with developmental challenges. Sectors to report on project progress for 2015/16 and submit Sector projects and indicative budget allocations for 2015/16 |  | Municipal Manager, Mayor and IDP Official | 13 Nov 2015 |  |  |
| IDP | Submission of the Sec 72 Performance Report | Legal compliance |  | MM, CFO and Mayor | 25 January 2016 | Done |  |
| All | Prepare and submit audit action plan. | To address the shortfalls identified by the AG. |  | Municipal Manager and CFO | May 2015 |  |  |
| PMS | Q2 Performance Reporting. | Evaluation Sec 56 managers, lower levels if applicable and institution PMS - Legal compliance |  | MM and PMS Officer | Jan-25 | Done |  |
| PMS | Q2 review by Internal Audit | Preparation of Annual Performance Report for MPAC |  | MM, PMS Manager and Internal Audit Unit | Jan 2016 |  |  |
| IDP | IGR Session to facilitate alignment | Align provincial and national programmes with IDP |  | Municipal Manager | By end February 2016 |  |  |
| Budget | Review proposed National and Provincial Government allocations to the Municipality for incorporation into the Draft Budget for tabling | Budget Preparation |  | CFO | Publication of DORA Mid – March 2016 |  |  |
| PMS and Finance | Mid- year budget and performance assessment visits | Tabling Mid- Inyear assessment report |  | Directors / Budget Office | January 25, 2016 | Done |  |
| EM | Mayors’ Forum |  |  | SBDM | 11 Feb 2016 |  |  |
| MM | Municipal Managers’ Forum |  |  | SBDM | 20 Jan 2016 |  |  |
| CFO | Chief Financial Officers’ Forum |  |  | SBDM | 14 Jan 2016 |  |  |
| DTIS | District Wide Infrastructure Forum |  |  | SBDM | 23 Jan 2016 |  |  |
| IDP | Convene the third IDP and Budget Steering Committee - alignment | Finalise internal alignment and project register. Ensure budget alignment between the Draft IDP and Draft SDBIP with agreed upon targets and performance indicators per project. |  | All Managers / Directors | Early March 2016 |  |  |
| IDP | Convene the third IDP Representatives Forum meeting - alignment | Present the Final Draft IDP and Draft SDBIP. Sector Dept. report on project implementation for 2014/15 and confirm project and budget allocations for 2015/16. (Finalise external project alignment) |  | Municipal Manager, Mayor and IDP Official | 10 March 2016 |  |  |
| IDP | In collaboration with Council develop and publicise the final Draft IDP and Budget 2016/17 Roadshow Programme | Make citizens aware of IDP / outreaches, prior to the adoption of the final Draft IDP and Budget. Secure venues and arrange logistics for scheduled meetings. |  | Office of the Mayor, Municipal Manager, IDP Officer and CFO | 31 March 2016 |  |  |
| IDP/.Budget | Submit 2016/17 Draft Capital and Operating Budgets, Draft IDP and Draft SDBIP Standing Committee | For scrutiny before tabling to Council |  | Municipal Manager and CFO | 18 Mar 2016 7 days before tabling |  |  |
| IDP/.Budget | Table 2015/16 Final Draft IDP and Capital and Operating Budgets | Council to consider and adopt the final Draft IDP. |  | Municipal Manager and CFO | 30 March 2016 |  |  |
| IDP/.Budget | Submit adopted draft IDP to the MEC for local government | Pre assessment interaction. |  | MM and IDP Officer | By 12 April 2015 Within 10 days after adoption |  |  |
| IDP/.Budget | Upload the Council approved Draft IDP and Budget (2016/17) on the municipal website and place a notice in local newspapers for public inspection (21days). | Legal Requirement to allow public to raise objections / comments on the adopted Draft IDP and Budget. |  | Municipal Manager; CFO and IDP Officer | 8 April 2016 Within ten days of adoption |  |  |
| IDP/.Budget | Forward 2015/16 Draft Capital and Operating Budgets and Draft IDP to National Treasury and Provincial Treasury and any prescribed national or provincial organs of state and other municipalities affected by the budget | Legal compliance as a control measure between Treasury and the LM. |  | Municipal Manager and CFO | 08 April 2016 Within ten days of adoption |  |  |
| IDP/.Budget | All Draft Budget Documents, Draft IDP, Draft SDBIP and relevant items must be ready for the Council meeting of end March 2016. | IDP and Budget preparing |  | IDP/PMS Manager and CFO | Mar- 2016 |  |  |
| IDP/.Budget | Executive Mayor to have tabled draft budget, resolution, plans and changes to the IDP to Council + MM to ensure that all Draft Documents are forwarded to the relevant stakeholders (e.g. Government Departments, District Municipality, etc.). | IDP and Budget preparing |  | Executive Mayor / Municipal Manager | Mar- 2016 |  |  |
| IDP/.Budget | Mayor to have completed public hearings on the budget + IDP where the Executive Mayor and Councillors present budget + IDP to the communities for comments or contributions (public participation process). | IDP and Budget preparing |  | Executive Mayor / All Councillors / Senior Management / HOD’s | Apr/ May 2016 |  |  |
| CFO | Chief Financial Officers’ Forum |  |  | SBDM | 02 Mar 2016 |  |  |
| CSS | Disaster Management Advisory Forum |  |  | SBDM | 10 Mar 2016 |  |  |
| EM | District Aids Council |  |  | SBDM | 16 Mar 2016 |  |  |
| PMS | Q3 Performance Reporting. | Evaluation Sec 56 managers, lower levels if applicable and institution PMS - Legal compliance |  | MM and PMS Officer | 2016 -04-15 |  |  |
| PMS | Q3 review by Internal Audit | Preparation of Annual Performance Report for MPAC |  | MM, PMS Manager and Internal Audit Unit | End April 2016 |  |  |
| PMS | Review of performance by MPAC | Moderate Performance evaluation Reports |  | MPAC and MM | End April 2016 |  |  |
| IDP and Budget | IDP Pre assessment interaction. | Monitor state of readiness to adopt Final IDP and Budget. |  | CoGTA and LM | During April 2016 |  |  |
| IDP and Budget | Undertake IDP and Budget Roadshows. | Allow opportunity for community to be part of municipal planning and be informed of the impact of IDP within their ward. |  | Mayor, Ward Councillors, Municipal Manager, CFO and Directors | Second to third week in April 2016 |  |  |
| IDP and Budget | Consolidate all public participation inputs and comments in respect of 2016/17 Draft IDP and Budget | Table to Mayor for consideration before the adoption of the Final 2015/16 IDP and Budget. |  | Municipal Manager and CFO | Early May 2016 |  |  |
| IDP and Budget | Budget Documents, IDP, SDBIP and relevant items must be ready for the Council meeting of end May 2016. | IDP and Budget preparing |  | IDP/PMS Manager and CFO | May-16 |  |  |
| IDP and Budget | Mayor to have presented final budget to Council for adoption and to have included operating / capital budget, resolutions, tariffs, capital implementation plans, operational objectives, changes to IDP and budget plans. | IDP and Budget preparing |  | Executive Mayor / CFO and IDP/PMS Manager | May-16 |  |  |
| IDP and Budget | Convene 4th IDP and Budget Steering Committee - consider comments and finalise | Interrogate community inputs and finalise SDBIP/IDP alignment and any necessary amendments to the IDP and budget. |  | Municipal Manager and IDP Official and CFO | Mid May 2016 |  |  |
| IDP and Budget | Convene the 4th IDP Representatives Forum meeting to present final IDP for consideration | Present the FINAL IDP. Report on public engagement and outcome of the 21-days public inspection and invite any last changes or additions to sector project register. |  | Municipal Manager, Mayor and IDP Official | 1 Week after above meeting. |  |  |
| IDP and Budget | Submit 2015/16 IDP and Budget to the Standing Committee | Oversight before adoption. |  | Municipal Manager, CFO and Mayor | Mid May 2016 |  |  |
| IDP and Budget | Adopt the Final 2015/16 IDP and MTEF Budget. | Legal compliance. Council to consider and approve. |  | Municipal Manager, CFO and Council | Before end May 2016 |  |  |
| IDP and Budget | Upload adopted Final 2015/16 IDP and MTEF Budget on the municipal website | Legal compliance and access to strategic documents. |  | Municipal Manager and CFO | 10 days after adoption |  |  |
| IDP and Budget | Submit approved IDP and Budget to the MEC for local government | Legal compliance |  | Municipal Manager | Within ten days of adoption -. |  |  |
| IDP and Budget | MM to have ensured that all Budget / IDP documents are forwarded to the relevant stakeholders (e.g. Government Departments such as National and Provincial Treasuries, DPLG, etc.) in the correct formats, and that tariffs are published. | Legal compliance |  | MM / IDP Manager / CFO | Jun-16 |  |  |
| IDP and Budget | Draft SDBIP to have been tabled by the MM to the Executive Mayor | Legal compliance |  | MM | Jun-16 |  |  |
| IDP and Budget | Final SDBIP’s completed and KPI’s drawn or finalised | Preparation of SDBIP |  | IDP and PMS Managers | Jun-16 |  |  |
| IDP and Budget | Final SDBIP, Performance Plans, Rating Calculators and Performance Agreement completed and signed for implementation as from the 1 July 2015 (2015/2016 Financial Year) | Preparation SDBIP and Finalise of Performance agreements |  | All Directors and Heads of Departments End the process starts again for the 2015/16 financial year... | Jun-16 |  |  |
| IDP and Budget | Final IDP Provincial Assessment 2015 | MEC comments |  | DM, LM, KPA leaders, CoGTA, Sector Departments | July 2016 |  |  |
| EM | Mayor’s Forum |  |  | SBDM | 18 May 2016 |  |  |
|  | District Aids Council |  |  | SBDM | 18 May 2016 |  |  |
| CSS | Disaster Management Advisory Forum |  |  | SBDM | 09 June 2016 |  |  |
| DIS | District Wide Infrastructure Forum |  |  | SBDM | 21 June 2016 |  |  |
| CFO | Chief Financial Officers’ Forum |  |  | SBDM | 26 May 2016 |  |  |